## experts
Name | Comment
Alojzy | 1 task per day
Eugeniusz | 2 tasks per day
Ignacy | 3 tasks per day
Pafnucy | 4 tasks per day
Romuald | 5 tasks per day

## tasks
Name | Start | End | Work
p1 | 2024-12-16 | 2025-04-02 | 400
p5 | 2024-12-16 | 2025-03-02 | 200
p6 | 2024-12-16 | 2025-04-02 | 200
p13 | 2024-12-16 | 2025-03-02 | 200
p14 | 2024-12-16 | 2025-04-02 | 200
p15 | 2024-12-16 | 2025-05-02 | 200
p20 | 2024-12-16 | 2025-03-02 | 200
p21 | 2024-12-16 | 2025-04-02 | 200
p22 | 2024-12-16 | 2025-05-02 | 200
p23 | 2024-12-16 | 2025-06-02 | 200
p30 | 2024-12-16 | 2025-03-02 | 200
p31 | 2024-12-16 | 2025-04-02 | 200
p32 | 2024-12-16 | 2025-05-02 | 200
p33 | 2024-12-16 | 2025-06-02 | 200
p34 | 2024-12-16 | 2025-07-02 | 200

## links
Expert | Task
Alojzy | p1
Eugeniusz | p5
Eugeniusz | p6
Ignacy | p13
Ignacy | p14
Ignacy | p15
Pafnucy | p20
Pafnucy | p21
Pafnucy | p22
Pafnucy | p23
Romuald | p30
Romuald | p31
Romuald | p32
Romuald | p33
Romuald | p34

## xbday
Expert | Task | Start | End | Lower | Upper
Alojzy | p1 | 2024-12-16 | 2025-01-16 | 2 | 2
Eugeniusz | p5 | 2024-12-16 | 2025-01-16 | 2 | 2
Eugeniusz | p6 | 2024-12-16 | 2025-01-16 | 2 | 2
Ignacy | p13 | 2024-12-16 | 2025-01-16 | 2 | 2
Ignacy | p14 | 2024-12-16 | 2025-01-16 | 2 | 2
Ignacy | p15 | 2024-12-16 | 2025-01-16 | 2 | 2
Pafnucy | p20 | 2024-12-16 | 2025-01-16 | 2 | 2
Pafnucy | p21 | 2024-12-16 | 2025-01-16 | 2 | 2
Pafnucy | p22 | 2024-12-16 | 2025-01-16 | 2 | 2
Pafnucy | p23 | 2024-12-16 | 2025-01-16 | 2 | 2
Romuald | p30 | 2024-12-16 | 2025-01-16 | 1 | 1
Romuald | p31 | 2024-12-16 | 2025-01-16 | 1 | 1
Romuald | p32 | 2024-12-16 | 2025-01-16 | 2 | 2
Romuald | p33 | 2024-12-16 | 2025-01-16 | 2 | 2
Romuald | p34 | 2024-12-16 | 2025-01-16 | 2 | 2

## xbsum
Expert | Task | Start | End | Lower | Upper

## ubday
Expert | Start | End | Lower | Upper

## ubsum
Expert | Task | Start | End | Lower | Upper

## expert bounds
Expert | Start | End | Lower | Upper

## invoicing periods
Name | Start | End
25.Jan | 2024-12-11 | 2025-01-15
25.Feb | 2025-01-16 | 2025-02-13
25.Mar | 2025-02-14 | 2025-03-16
25.Apr | 2025-03-17 | 2025-04-14
25.May | 2025-04-15 | 2025-05-18

## invoicing periods bounds
Expert | Period | Lower | Upper
Alojzy | 25.Jan | 0 | 200
Eugeniusz | 25.Jan | 0 | 200
Ignacy | 25.Jan | 0 | 200
Pafnucy | 25.Jan | 0 | 200
Romuald | 25.Jan | 0 | 200

## public holidays
Date
2024-12-25

## misc
Today | Hours per day | Solver | Last day
2024-12-15 | 8 | scip | 2025-07-02

## himg
Hours per day | Width | Height | Dpi | Start | End | Bar:color | Bar:hatch | Bar:alpha | Is Start OK? | Is End OK?
| 8 | 4 | 150 | 2024-12-16 | 2025-01-05 | #2ca02c | / | 0.3 | TRUE | TRUE
Formulas:
End = [Start]+20

## timg
Tasks per day | Width | Height | Dpi | Start | End | Bar:color | Bar:hatch | Bar:alpha | Is Start OK? | Is End OK?
| 8 | 4 | 150 | 2024-12-16 | 2025-01-05 | #d62728 | \ | 0.3 | TRUE | TRUE
Formulas:
End = [Start]+20

## simg
Hours per day stacked | Width | Height | Dpi | Start | End | Bar:alpha | Is Start OK? | Is End OK?
| 8 | 4 | 150 | 2024-12-16 | 2025-01-05 | 0.6 | TRUE | TRUE
Formulas:
End = [Start]+20

## gimg
Task's Gantt Chart | Width | Height | Dpi | Barh:color | Barh:height | Barh:alpha
| 8 | 4 | 150 | #ff7f0e | 0.9 | 0.6

## wimg
Invoicing Periods Workload | Width | Height | Dpi | Bar:color | Bar:ecolor | Bar:capsize
| 8 | 4 | 150 | #7BC8F6 | #EE0000 | 4

## bimg
Task with bounds | Width | Height | Dpi | Fill:color | Fill:hatch | Fill:alpha | Plot:format | Plot:markeredgewidth | Step:linewidth
| 8 | 4 | 150 | #90EE90 | / | 0.2 | o | 0.5 | 0.5

## eimg
Experts per day stacked | Width | Height | Dpi | Bar:alpha
| 8 | 4 | 150 | 0.6