## experts
Name | Comment | TRUE
DEV.Alojzy | 1 task, no bounds | TRUE
DEV.Barłomiej | 1 task, 1 xbday | TRUE
DEV.Cezary | 1 task, 2 xbday | TRUE
DEV.Dariusz | 1 task, 1 xbsum | TRUE
DEV.Eugenius | 2 tasks, no bounds | TRUE
DEV.Franciszek | 2 tasks, 1 ubday | TRUE
DEV.Gustaw | 2 tasks, 1 ubsum | TRUE
DEV.Hubert | 2 tasks, 1 ubday, 1 ubsum | TRUE
DEV.Ignacy | 3 tasks, no bounds | TRUE
DEV.Jarosław | 3 tasks, 1 ubday(2), 2 ubsum | TRUE
DEV.Paweł | 3 tasks, 1 ubday(1), 2 ubsum | TRUE
Note on C1: Has Expert any task?

## tasks
Name | Start | End | Work | TRUE | TRUE | TRUE
DEV.p1.m | 2024-12-16 | 2025-04-02 | 400 | TRUE | TRUE | TRUE
DEV.p2.m | 2024-12-16 | 2025-04-02 | 420 | TRUE | TRUE | TRUE
DEV.p3.m | 2024-12-16 | 2025-04-02 | 430 | TRUE | TRUE | TRUE
DEV.p4.m | 2024-12-16 | 2025-04-02 | 440 | TRUE | TRUE | TRUE
DEV.p5.m | 2024-12-16 | 2025-03-02 | 200 | TRUE | TRUE | TRUE
DEV.p6.m | 2024-12-16 | 2025-04-02 | 200 | TRUE | TRUE | TRUE
DEV.p7.m | 2024-12-16 | 2025-03-02 | 200 | TRUE | TRUE | TRUE
DEV.p8.m | 2024-12-16 | 2025-04-02 | 200 | TRUE | TRUE | TRUE
DEV.p9.m | 2024-12-16 | 2025-03-02 | 200 | TRUE | TRUE | TRUE
DEV.p10.m | 2024-12-16 | 2025-04-02 | 200 | TRUE | TRUE | TRUE
DEV.p11.m | 2024-12-16 | 2025-03-02 | 200 | TRUE | TRUE | TRUE
DEV.p12.m | 2024-12-16 | 2025-04-02 | 200 | TRUE | TRUE | TRUE
DEV.p13.m | 2024-12-16 | 2025-03-02 | 200 | TRUE | TRUE | TRUE
DEV.p14.m | 2024-12-16 | 2025-04-02 | 200 | TRUE | TRUE | TRUE
DEV.p15.m | 2024-12-16 | 2025-05-02 | 200 | TRUE | TRUE | TRUE
DEV.p16.m | 2024-12-16 | 2025-03-02 | 200 | TRUE | TRUE | TRUE
DEV.p17.m | 2024-12-16 | 2025-04-02 | 200 | TRUE | TRUE | TRUE
DEV.p18.m | 2024-12-16 | 2025-05-02 | 200 | TRUE | TRUE | TRUE
DEV.p19.m | 2024-12-16 | 2025-03-02 | 200 | TRUE | TRUE | TRUE
DEV.p20.m | 2024-12-16 | 2025-04-02 | 200 | TRUE | TRUE | TRUE
DEV.p21.m | 2024-12-16 | 2025-05-02 | 200 | TRUE | TRUE | TRUE
Note on E1: Is task assign to an Expert?
Note on F1: Should task be included?
Note on G1: Are date OK?

## links
Expert | Task | TRUE | TRUE
DEV.Alojzy | DEV.p1.m | TRUE | TRUE
DEV.Barłomiej | DEV.p2.m | TRUE | TRUE
DEV.Cezary | DEV.p3.m | TRUE | TRUE
DEV.Dariusz | DEV.p4.m | TRUE | TRUE
DEV.Eugenius | DEV.p5.m | TRUE | TRUE
DEV.Eugenius | DEV.p6.m | TRUE | TRUE
DEV.Franciszek | DEV.p7.m | TRUE | TRUE
DEV.Franciszek | DEV.p8.m | TRUE | TRUE
DEV.Gustaw | DEV.p9.m | TRUE | TRUE
DEV.Gustaw | DEV.p10.m | TRUE | TRUE
DEV.Hubert | DEV.p11.m | TRUE | TRUE
DEV.Hubert | DEV.p12.m | TRUE | TRUE
DEV.Ignacy | DEV.p13.m | TRUE | TRUE
DEV.Ignacy | DEV.p14.m | TRUE | TRUE
DEV.Ignacy | DEV.p15.m | TRUE | TRUE
DEV.Jarosław | DEV.p16.m | TRUE | TRUE
DEV.Jarosław | DEV.p17.m | TRUE | TRUE
DEV.Jarosław | DEV.p18.m | TRUE | TRUE
DEV.Paweł | DEV.p19.m | TRUE | TRUE
DEV.Paweł | DEV.p20.m | TRUE | TRUE
DEV.Paweł | DEV.p21.m | TRUE | TRUE
Note on C1: Valid expert?
Note on D1: Valid task?

## xbday
Expert | Task | Start | End | Lower | Upper | TRUE | TRUE | TRUE
DEV.Barłomiej | DEV.p2.m | 2024-12-16 | 2024-12-27 | 6 | 6 | TRUE | TRUE | TRUE
DEV.Cezary | DEV.p3.m | 2024-12-16 | 2024-12-20 | 5 | 5 | TRUE | TRUE | TRUE
DEV.Cezary | DEV.p3.m | 2024-12-23 | 2024-12-27 | 3 | 3 | TRUE | TRUE | TRUE
Note on G1: Valid expert?
Note on H1: Valid task?
Note on I1: Are date OK?

## xbsum
Expert | Task | Start | End | Lower | Upper | TRUE | TRUE | TRUE
DEV.Dariusz | DEV.p4.m | 2024-12-16 | 2024-12-20 | 16 | 16 | TRUE | TRUE | TRUE
Note on G1: Valid expert?
Note on H1: Valid task?
Note on I1: Are date OK?

## ubday
Expert | Start | End | Lower | Upper | TRUE | TRUE
DEV.Franciszek | 2024-12-16 | 2024-12-27 | 2 | 2 | TRUE | TRUE
DEV.Hubert | 2024-12-16 | 2024-12-27 | 1 | 1 | TRUE | TRUE
DEV.Jarosław | 2024-12-16 | 2024-12-27 | 2 | 2 | TRUE | TRUE
DEV.Paweł | 2024-12-16 | 2024-12-27 | 1 | 1 | TRUE | TRUE
Note on F1: Valid expert?
Note on G1: Are date OK?

## ubsum
Expert | Task | Start | End | Lower | Upper | TRUE | TRUE | TRUE
DEV.Gustaw | DEV.p9.m | 2024-12-16 | 2024-12-20 | 4 | 4 | TRUE | TRUE | TRUE
DEV.Hubert | DEV.p11.m | 2024-12-16 | 2024-12-20 | 3 | 3 | TRUE | TRUE | TRUE
DEV.Jarosław | DEV.p16.m | 2024-12-16 | 2024-12-20 | 3 | 3 | TRUE | TRUE | TRUE
DEV.Jarosław | DEV.p18.m | 2024-12-16 | 2024-12-20 | 3 | 3 | TRUE | TRUE | TRUE
DEV.Paweł | DEV.p19.m | 2024-12-16 | 2024-12-20 | 2 | 2 | TRUE | TRUE | TRUE
Note on G1: Valid expert?
Note on H1: Valid task?
Note on I1: Are date OK?

## expert bounds
Expert | Start | End | Lower | Upper | TRUE | TRUE
DEV.Alojzy | 2024-12-16 | 2025-02-01 | 0 | 5 | TRUE | TRUE
DEV.Alojzy | 2025-02-02 | 2025-03-01 | 0 | 7
Note on F1: Valid expert?
Note on G1: Are date OK?

## invoicing periods
Name | Start | End | TRUE
25.Jan | 2024-12-11 | 2025-01-15 | TRUE
25.Feb | 2025-01-16 | 2025-02-13 | TRUE
25.Mar | 2025-02-14 | 2025-03-16 | TRUE
25.Apr | 2025-03-17 | 2025-04-14 | TRUE
25.May | 2025-04-15 | 2025-05-18 | TRUE
Note on D1: Are dates OK?

## invoicing periods bounds
Expert | Period | Lower | Upper | TRUE | TRUE
DEV.Paweł | 25.Jan | 0 | 200 | TRUE | TRUE
DEV.Paweł | 25.Feb | 0 | 200 | TRUE | TRUE
DEV.Paweł | 25.Mar | 0 | 200 | TRUE | TRUE
DEV.Paweł | 25.Apr | 0 | 200 | TRUE | TRUE
DEV.Paweł | 25.May | 0 | 200 | TRUE | TRUE
DEV.Alojzy | 25.Jan | 0 | 200 | TRUE | TRUE
DEV.Alojzy | 25.Feb | 0 | 200 | TRUE | TRUE
DEV.Alojzy | 25.Mar | 0 | 200 | TRUE | TRUE
DEV.Alojzy | 25.Apr | 0 | 200 | TRUE | TRUE
DEV.Alojzy | 25.May | 0 | 200 | TRUE | TRUE
DEV.Barłomiej | 25.Jan | 0 | 200 | TRUE | TRUE
DEV.Cezary | 25.Jan | 0 | 200 | TRUE | TRUE
DEV.Dariusz | 25.Jan | 0 | 200 | TRUE | TRUE
DEV.Eugenius | 25.Jan | 0 | 200 | TRUE | TRUE
DEV.Franciszek | 25.Jan | 0 | 200 | TRUE | TRUE
DEV.Gustaw | 25.Jan | 0 | 200 | TRUE | TRUE
DEV.Hubert | 25.Jan | 0 | 200 | TRUE | TRUE
DEV.Ignacy | 25.Jan | 0 | 200 | TRUE | TRUE
DEV.Jarosław | 25.Jan | 0 | 200 | TRUE | TRUE
Note on E1: Valid expert?
Note on F1: Valid period?

## public holidays
Date | TRUE
2024-12-25 | TRUE
Note on B1: Are dates OK?

## misc
Today | Hours per day | Solver | Last day
2024-12-15 | 8 | highs | 2025-05-18

## himg
Hours per day | Width | Height | Dpi | Start | End | Bar:color | Bar:hatch | Bar:alpha | Is Start OK? | Is End OK?
| 12 | 6 | 300 | 2024-12-16 | 2025-01-05 | #2ca02c | / | 0.3 | TRUE | TRUE
Formulas:
End = [Start]+20

## timg
Tasks per day | Width | Height | Dpi | Start | End | Bar:color | Bar:hatch | Bar:alpha | Is Start OK? | Is End OK?
| 12 | 6 | 300 | 2024-12-16 | 2025-01-05 | #d62728 | \ | 0.3 | TRUE | TRUE
Formulas:
End = [Start]+20

## simg
Stacked hours per day | Width | Height | Dpi | Start | End | Bar:alpha | Is Start OK? | Is End OK?
| 12 | 6 | 300 | 2024-12-16 | 2025-01-05 | 0.6 | TRUE | TRUE
Formulas:
End = [Start]+20

## gimg
Task's Gantt Chart | Width | Height | Dpi | Barh:color | Barh:height | Barh:alpha
| 8 | 4 | 150 | #ff7f0e | 0.9 | 0.6

## wimg
Invoicing Periods Workload | Width | Height | Dpi | Bar:color | Bar:ecolor | Bar:capsize
| 8 | 4 | 150 | #7BC8F6 | #EE0000 | 4

## bimg
Task with bounds | Width | Height | Dpi | Fill:color | Fill:hatch | Fill:alpha | Plot:format | Plot:markeredgewidth | Step:linewidth
| 8 | 4 | 150 | #90EE90 | / | 0.2 | o | 0.5 | 0.5

## eimg
Experts per day stacked | Width | Height | Dpi | Bar:alpha
| 8 | 4 | 150 | 0.6