## experts
Name | Comment | TRUE
PM.Angel | the 1st unit | 1
Note on C1: Has Expert any task?

## tasks
Name | Start | End | Work | Days | Workdays | Avg[h/day] | Lower | Upper | TRUE | TRUE | TRUE
charlie.pm | 2025-01-01 | 2025-06-05 | 80 | 156 | 110 | 0.72727 | 0.5 | 0.75 | TRUE | TRUE | TRUE
charlie.pf | 2025-06-06 | 2025-07-06 | 10 | 31 | 21 | 0.47619 | 0.25 | 0.5 | TRUE | TRUE | TRUE
delta.pm | 2025-01-01 | 2025-02-25 | 25 | 56 | 39 | 0.64103 | 0.5 | 0.75 | TRUE | TRUE | TRUE
delta.pf | 2025-02-26 | 2025-04-12 | 5 | 46 | 33 | 0.15152 | 0 | 0.25 | TRUE | TRUE | TRUE
juliet.pe | 2025-02-10 | 2025-02-27 | 10 | 18 | 14 | 0.71429 | 0.5 | 0.75 | TRUE | TRUE | TRUE
juliet.pm | 2025-02-28 | 2025-06-30 | 50 | 123 | 86 | 0.5814 | 0.5 | 0.75 | TRUE | TRUE | TRUE
juliet.pf | 2025-07-01 | 2025-08-15 | 5 | 46 | 34 | 0.14706 | 0 | 0.25 | TRUE | TRUE | TRUE
mike.pe | 2025-04-10 | 2025-04-20 | 10 | 11 | 7 | 1.4286 | 1.25 | 1.5 | TRUE | TRUE | TRUE
mike.pm | 2025-04-21 | 2025-09-25 | 50 | 158 | 113 | 0.44248 | 0.25 | 0.5 | TRUE | TRUE | TRUE
mike.pf | 2025-09-26 | 2025-10-30 | 5 | 35 | 25 | 0.2 | 0 | 0.25 | TRUE | TRUE | TRUE
november.pe | 2025-05-26 | 2025-06-14 | 10 | 20 | 15 | 0.66667 | 0.5 | 0.75 | TRUE | TRUE | TRUE
november.pm | 2025-06-15 | 2025-12-30 | 55 | 199 | 142 | 0.38732 | 0.25 | 0.5 | TRUE | TRUE | TRUE
november.pf | 2025-12-31 | 2026-01-31 | 5 | 32 | 23 | 0.21739 | 0 | 0.25 | TRUE | TRUE | TRUE
oscar2.pm | 2025-01-01 | 2025-06-20 | 60 | 171 | 121 | 0.49587 | 0.25 | 0.5 | TRUE | TRUE | TRUE
oscar2.pf | 2025-06-21 | 2025-06-30 | 20 | 10 | 6 | 3.3333 | 3.25 | 3.5 | TRUE | TRUE | TRUE
papa2.pm | 2025-01-01 | 2025-06-20 | 100 | 171 | 121 | 0.82645 | 0.75 | 1 | TRUE | TRUE | TRUE
papa2.pf | 2025-06-21 | 2025-06-30 | 20 | 10 | 6 | 3.3333 | 3.25 | 3.5 | TRUE | TRUE | TRUE
quebec2.pe | 2025-06-01 | 2025-06-26 | 25 | 26 | 19 | 1.3158 | 1.25 | 1.5 | TRUE | TRUE | TRUE
quebec2.pm | 2025-06-27 | 2026-11-09 | 120 | 501 | 357 | 0.33613 | 0.25 | 0.5 | TRUE | TRUE | TRUE
quebec2.pf | 2026-11-10 | 2027-01-04 | 20 | 56 | 40 | 0.5 | 0.5 | 0.75 | TRUE | TRUE | TRUE
sierra2.pm | 2025-01-01 | 2025-03-02 | 40 | 61 | 42 | 0.95238 | 0.75 | 1 | TRUE | TRUE | TRUE
sierra2.pf | 2025-03-03 | 2025-03-10 | 10 | 8 | 6 | 1.6667 | 1.5 | 1.75 | TRUE | TRUE | TRUE
xray2.pe | 2025-07-15 | 2025-08-09 | 25 | 26 | 19 | 1.3158 | 1.25 | 1.5 | TRUE | TRUE | TRUE
xray2.pm | 2025-08-10 | 2026-01-07 | 120 | 151 | 108 | 1.1111 | 1 | 1.25 | TRUE | TRUE | TRUE
xray2.pf | 2026-01-08 | 2026-02-01 | 10 | 25 | 17 | 0.58824 | 0.5 | 0.75 | TRUE | TRUE | TRUE
Note on J1: Is task assign to an Expert?
Note on K1: Should task be included?
Note on L1: Are date OK?

## links
Expert | Task | TRUE | TRUE
PM.Angel | charlie.pf | 1 | 1
PM.Angel | charlie.pm | 1 | 1
PM.Angel | delta.pf | 1 | 1
PM.Angel | delta.pm | 1 | 1
PM.Angel | juliet.pe | 1 | 1
PM.Angel | juliet.pf | 1 | 1
PM.Angel | juliet.pm | 1 | 1
PM.Angel | mike.pe | 1 | 1
PM.Angel | mike.pf | 1 | 1
PM.Angel | mike.pm | 1 | 1
PM.Angel | november.pe | 1 | 1
PM.Angel | november.pf | 1 | 1
PM.Angel | november.pm | 1 | 1
PM.Angel | oscar2.pf | 1 | 1
PM.Angel | oscar2.pm | 1 | 1
PM.Angel | papa2.pf | 1 | 1
PM.Angel | papa2.pm | 1 | 1
PM.Angel | quebec2.pe | 1 | 1
PM.Angel | quebec2.pf | 1 | 1
PM.Angel | quebec2.pm | 1 | 1
PM.Angel | sierra2.pf | 1 | 1
PM.Angel | sierra2.pm | 1 | 1
PM.Angel | xray2.pe | 1 | 1
PM.Angel | xray2.pm | 1 | 1
PM.Angel | xray2.pf | 1 | 1
Note on C1: Valid expert?
Note on D1: Valid task?

## xbday
Expert | Task | Start | End | Lower | Upper | TRUE | TRUE | TRUE
PM.Angel | charlie.pf | 2025-06-06 | 2025-07-06 | 0.25 | 0.5 | TRUE | TRUE | TRUE
PM.Angel | charlie.pm | 2025-01-01 | 2025-06-05 | 0.5 | 0.75 | TRUE | TRUE | TRUE
PM.Angel | delta.pf | 2025-02-26 | 2025-04-12 | 0 | 0.25 | TRUE | TRUE | TRUE
PM.Angel | delta.pm | 2025-01-01 | 2025-02-25 | 0.5 | 0.75 | TRUE | TRUE | TRUE
PM.Angel | juliet.pe | 2025-01-01 | 2025-06-05 | 0.5 | 0.75 | TRUE | TRUE | TRUE
PM.Angel | juliet.pf | 2025-02-28 | 2025-06-30 | 0 | 0.25 | TRUE | TRUE | TRUE
PM.Angel | juliet.pm | 2025-02-10 | 2025-02-27 | 0.5 | 0.75 | TRUE | TRUE | TRUE
PM.Angel | mike.pe | 2025-07-01 | 2025-08-15 | 1.25 | 1.5 | TRUE | TRUE | TRUE
PM.Angel | mike.pf | 2025-09-26 | 2025-10-30 | 0 | 0.25 | TRUE | TRUE | TRUE
PM.Angel | mike.pm | 2025-04-21 | 2025-09-25 | 0.25 | 0.5 | TRUE | TRUE | TRUE
PM.Angel | november.pe | 2025-05-26 | 2025-06-14 | 0.5 | 0.75 | TRUE | TRUE | TRUE
PM.Angel | november.pf | 2025-12-31 | 2026-01-31 | 0 | 0.25 | TRUE | TRUE | TRUE
PM.Angel | november.pm | 2025-06-15 | 2025-12-30 | 0.25 | 0.5 | TRUE | TRUE | TRUE
PM.Angel | oscar2.pf | 2025-06-21 | 2025-06-30 | 3.25 | 3.5 | TRUE | TRUE | TRUE
PM.Angel | oscar2.pm | 2025-01-01 | 2025-06-20 | 0.25 | 0.5 | TRUE | TRUE | TRUE
PM.Angel | papa2.pf | 2025-06-21 | 2025-06-30 | 3.25 | 3.5 | TRUE | TRUE | TRUE
PM.Angel | papa2.pm | 2025-01-01 | 2025-06-20 | 0.75 | 1 | TRUE | TRUE | TRUE
PM.Angel | quebec2.pe | 2025-06-01 | 2025-06-26 | 0.5 | 1.5 | TRUE | TRUE | TRUE
PM.Angel | quebec2.pf | 2026-11-10 | 2027-01-04 | 0.5 | 0.75 | TRUE | TRUE | TRUE
PM.Angel | quebec2.pm | 2025-06-27 | 2026-11-09 | 0 | 0.5 | TRUE | TRUE | TRUE
PM.Angel | sierra2.pf | 2025-03-03 | 2025-03-10 | 1.5 | 1.75 | TRUE | TRUE | TRUE
PM.Angel | sierra2.pm | 2025-01-01 | 2025-03-02 | 0.75 | 1 | TRUE | TRUE | TRUE
PM.Angel | xray2.pe | 2025-07-15 | 2025-08-09 | 1.25 | 1.5 | TRUE | TRUE | TRUE
PM.Angel | xray2.pm | 2025-08-10 | 2026-01-07 | 1 | 1.25 | TRUE | TRUE | TRUE
PM.Angel | xray2.pf | 2026-01-08 | 2026-02-01 | 0.5 | 0.75 | TRUE | TRUE | TRUE
Note on G1: Valid expert?
Note on H1: Valid task?
Note on I1: Are date OK?

## xbsum
Expert | Task | Start | End | Lower | Upper

## ubday
Expert | Start | End | Lower | Upper

## ubsum
Expert | Task | Start | End | Lower | Upper

## expert bounds
Expert | Start | End | Lower | Upper

## invoicing periods
Name | Start | End | TRUE
Jan.25 | 2024-12-11 | 2025-01-15 | TRUE
Feb.25 | 2025-01-16 | 2025-02-13 | TRUE
Mar.25 | 2025-02-14 | 2025-03-16 | TRUE
Apr.25 | 2025-03-17 | 2025-04-14 | TRUE
May.25 | 2025-04-15 | 2025-05-18 | TRUE
Jun.25 | 2025-05-19 | 2025-06-18 | TRUE
Jul.25 | 2025-06-19 | 2025-07-17 | TRUE
Aug.25 | 2025-07-18 | 2025-08-17 | TRUE
Sep.25 | 2025-08-18 | 2025-09-15 | TRUE
Oct.25 | 2025-09-16 | 2025-10-15 | TRUE
Nov.25 | 2025-10-16 | 2025-11-12 | TRUE
Dec.25 | 2025-11-13 | 2025-12-11 | TRUE
Note on D1: Are dates OK?

## invoicing periods bounds
Expert | Period | Lower | Upper | TRUE | TRUE
PM.Angel | Jan.25 | 0 | 180 | TRUE | TRUE
PM.Angel | Feb.25 | 0 | 180 | TRUE | TRUE
PM.Angel | Mar.25 | 0 | 180 | TRUE | TRUE
PM.Angel | Apr.25 | 0 | 180 | TRUE | TRUE
PM.Angel | May.25 | 0 | 180 | TRUE | TRUE
PM.Angel | Jun.25 | 0 | 180 | TRUE | TRUE
PM.Angel | Jul.25 | 0 | 180 | TRUE | TRUE
PM.Angel | Aug.25 | 0 | 180 | TRUE | TRUE
PM.Angel | Sep.25 | 0 | 180 | TRUE | TRUE
PM.Angel | Oct.25 | 0 | 180 | TRUE | TRUE
PM.Angel | Nov.25 | 0 | 180 | TRUE | TRUE
PM.Angel | Dec.25 | 0 | 180 | TRUE | TRUE
Note on E1: Valid expert?
Note on F1: Valid period?

## public holidays
Date | TRUE
2025-01-01 | TRUE
2025-04-20 | TRUE
2025-05-01 | TRUE
Note on B1: Are dates OK?

## misc
Today | Hours per day | Solver | Last day
2024-12-30 | 8 | highs | 2027-01-04

## himg
Hours per day | Width | Height | Dpi | Start | End | Bar:color | Bar:hatch | Bar:alpha | Is Start OK? | Is End OK?
| 8 | 4 | 150 | 2024-12-31 | 2027-01-04 | #2ca02c | / | 0.3 | TRUE | TRUE

## timg
Tasks per day | Width | Height | Dpi | Start | End | Bar:color | Bar:hatch | Bar:alpha | Is Start OK? | Is End OK?
| 8 | 4 | 150 | 2024-12-31 | 2027-01-04 | #d62728 | \ | 0.3 | TRUE | TRUE

## simg
Hours per day stacked | Width | Height | Dpi | Start | End | Bar:alpha | Is Start OK? | Is End OK?
| 8 | 4 | 150 | 2024-12-31 | 2027-01-04 | 0.6 | TRUE | TRUE

## gimg
Task's Gantt Chart | Width | Height | Dpi | Barh:color | Barh:height | Barh:alpha
| 8 | 4 | 150 | #ff7f0e | 0.9 | 0.6

## wimg
Invoicing Periods Workload | Width | Height | Dpi | Bar:color | Bar:ecolor | Bar:capsize
| 8 | 4 | 150 | #7BC8F6 | #EE0000 | 4

## bimg
Task with bounds | Width | Height | Dpi | Fill:color | Fill:hatch | Fill:alpha | Plot:format | Plot:markeredgewidth | Step:linewidth
| 8 | 4 | 150 | #90EE90 | / | 0.2 | o | 0.5 | 0.5

## eimg
Experts per day stacked | Width | Height | Dpi | Bar:alpha
| 8 | 4 | 150 | 0.6