## experts
Name | Comment | TRUE
SA.Melanie | the 2nd unit | 1
Note on C1: Has Expert any task?

## tasks
Name | Start | End | Work | Days | Workdays | Avg[h/day] | Lower | Upper | TRUE | TRUE | TRUE
delta2.sm | 2025-01-01 | 2025-06-20 | 20 | 171 | 121 | 0.16529 | 0 | 0.25 | 1 | TRUE | TRUE
delta2.sf | 2025-06-21 | 2025-07-01 | 10 | 11 | 7 | 1.4286 | 1.25 | 1.5 | TRUE | TRUE | TRUE
echo2.sm | 2025-01-01 | 2025-01-21 | 10 | 21 | 14 | 0.71429 | 0.5 | 0.75 | TRUE | TRUE | TRUE
echo2.sf | 2025-01-22 | 2025-03-10 | 5 | 48 | 34 | 0.14706 | 0 | 0.25 | TRUE | TRUE | TRUE
foxtrot2.sm | 2025-01-01 | 2025-03-22 | 50 | 81 | 57 | 0.87719 | 0.75 | 1 | TRUE | TRUE | TRUE
foxtrot2.sf | 2025-03-23 | 2025-04-01 | 30 | 10 | 7 | 4.2857 | 4.25 | 4.5 | TRUE | TRUE | TRUE
hotel2.sm | 2025-01-01 | 2025-02-15 | 10 | 46 | 32 | 0.3125 | 0.25 | 0.5 | TRUE | TRUE | TRUE
hotel2.sf | 2025-02-16 | 2025-02-25 | 5 | 10 | 7 | 0.71429 | 0.5 | 0.75 | TRUE | TRUE | TRUE
mike2.se | 2025-01-10 | 2025-01-25 | 40 | 16 | 11 | 3.6364 | 3.5 | 3.75 | TRUE | TRUE | TRUE
mike2.sm | 2025-01-26 | 2025-05-16 | 20 | 111 | 79 | 0.25316 | 0.25 | 0.5 | TRUE | TRUE | TRUE
mike2.sf | 2025-05-17 | 2025-06-01 | 10 | 16 | 10 | 1 | 1 | 1.25 | TRUE | TRUE | TRUE
Note on J1: Is task assign to an Expert?
Note on K1: Should task be included?
Note on L1: Are date OK?

## links
Expert | Task | TRUE | TRUE
SA.Melanie | delta2.sf | 1 | 1
SA.Melanie | delta2.sm | 1 | 1
SA.Melanie | echo2.sf | 1 | 1
SA.Melanie | echo2.sm | 1 | 1
SA.Melanie | foxtrot2.sf | 1 | 1
SA.Melanie | foxtrot2.sm | 1 | 1
SA.Melanie | hotel2.sf | 1 | 1
SA.Melanie | hotel2.sm | 1 | 1
SA.Melanie | mike2.se | 1 | 1
SA.Melanie | mike2.sf | 1 | 1
SA.Melanie | mike2.sm | 1 | 1
Note on C1: Valid expert?
Note on D1: Valid task?

## xbday
Expert | Task | Start | End | Lower | Upper | TRUE | TRUE | TRUE
SA.Melanie | delta2.sm | 2025-01-01 | 2025-06-20 | 0 | 0.25 | TRUE | TRUE | TRUE
SA.Melanie | delta2.sf | 2025-06-21 | 2025-07-01 | 1.25 | 1.5 | TRUE | TRUE | TRUE
SA.Melanie | echo2.sm | 2025-01-01 | 2025-01-21 | 0.5 | 0.75 | TRUE | TRUE | TRUE
SA.Melanie | echo2.sf | 2025-01-22 | 2025-03-10 | 0 | 0.25 | TRUE | TRUE | TRUE
SA.Melanie | foxtrot2.sm | 2025-01-01 | 2025-03-22 | 0.75 | 1 | TRUE | TRUE | TRUE
SA.Melanie | foxtrot2.sf | 2025-03-23 | 2025-04-01 | 4.25 | 4.5 | TRUE | TRUE | TRUE
SA.Melanie | hotel2.sm | 2025-01-01 | 2025-02-15 | 0.25 | 0.5 | TRUE | TRUE | TRUE
SA.Melanie | hotel2.sf | 2025-02-16 | 2025-02-25 | 0.5 | 0.75 | TRUE | TRUE | TRUE
SA.Melanie | mike2.se | 2025-01-10 | 2025-01-15 | 3.5 | 3.75 | TRUE | TRUE | TRUE
SA.Melanie | mike2.sm | 2025-01-16 | 2025-05-16 | 0.25 | 0.5 | TRUE | TRUE | TRUE
SA.Melanie | mike2.sf | 2025-05-17 | 2025-06-01 | 1 | 1.25 | TRUE | TRUE | TRUE
Note on G1: Valid expert?
Note on H1: Valid task?
Note on I1: Are date OK?

## xbsum
Expert | Task | Start | End | Lower | Upper

## ubday
Expert | Start | End | Lower | Upper

## ubsum
Expert | Task | Start | End | Lower | Upper

## expert bounds
Expert | Start | End | Lower | Upper

## invoicing periods
Name | Start | End | TRUE
Jan.25 | 2024-12-11 | 2025-01-15 | TRUE
Feb.25 | 2025-01-16 | 2025-02-13 | TRUE
Mar.25 | 2025-02-14 | 2025-03-16 | TRUE
Apr.25 | 2025-03-17 | 2025-04-14 | TRUE
May.25 | 2025-04-15 | 2025-05-18 | TRUE
Jun.25 | 2025-05-19 | 2025-06-18 | TRUE
Jul.25 | 2025-06-19 | 2025-07-17 | TRUE
Aug.25 | 2025-07-18 | 2025-08-17 | TRUE
Sep.25 | 2025-08-18 | 2025-09-15 | TRUE
Oct.25 | 2025-09-16 | 2025-10-15 | TRUE
Nov.25 | 2025-10-16 | 2025-11-12 | TRUE
Dec.25 | 2025-11-13 | 2025-12-11 | TRUE
Note on D1: Are dates OK?

## invoicing periods bounds
Expert | Period | Lower | Upper | TRUE | TRUE
SA.Melanie | Jan.25 | 0 | 180 | TRUE | TRUE
SA.Melanie | Feb.25 | 0 | 180 | TRUE | TRUE
SA.Melanie | Mar.25 | 0 | 180 | TRUE | TRUE
SA.Melanie | Apr.25 | 0 | 180 | TRUE | TRUE
SA.Melanie | May.25 | 0 | 180 | TRUE | TRUE
SA.Melanie | Jun.25 | 0 | 180 | TRUE | TRUE
SA.Melanie | Jul.25 | 0 | 180 | TRUE | TRUE
SA.Melanie | Aug.25 | 0 | 180 | TRUE | TRUE
SA.Melanie | Sep.25 | 0 | 180 | TRUE | TRUE
SA.Melanie | Oct.25 | 0 | 180 | TRUE | TRUE
SA.Melanie | Nov.25 | 0 | 180 | TRUE | TRUE
SA.Melanie | Dec.25 | 0 | 180 | TRUE | TRUE
Note on E1: Valid expert?
Note on F1: Valid period?

## public holidays
Date | TRUE
2025-01-01 | TRUE
2025-04-20 | TRUE
2025-05-01 | TRUE
Note on B1: Are dates OK?

## misc
Today | Hours per day | Solver | Last day
2024-12-30 | 8 | highs | 2025-12-11

## himg
Hours per day | Width | Height | Dpi | Start | End | Bar:color | Bar:hatch | Bar:alpha | Is Start OK? | Is End OK?
| 8 | 4 | 150 | 2024-12-31 | 2025-12-11 | #2ca02c | / | 0.3 | TRUE | TRUE

## timg
Tasks per day | Width | Height | Dpi | Start | End | Bar:color | Bar:hatch | Bar:alpha | Is Start OK? | Is End OK?
| 8 | 4 | 150 | 2024-12-31 | 2025-12-11 | #d62728 | \ | 0.3 | TRUE | TRUE

## simg
Hours per day stacked | Width | Height | Dpi | Start | End | Bar:alpha | Is Start OK? | Is End OK?
| 8 | 4 | 150 | 2024-12-31 | 2025-12-11 | 0.6 | TRUE | TRUE

## gimg
Task's Gantt Chart | Width | Height | Dpi | Barh:color | Barh:height | Barh:alpha
| 8 | 4 | 150 | #ff7f0e | 0.9 | 0.6

## wimg
Invoicing Periods Workload | Width | Height | Dpi | Bar:color | Bar:ecolor | Bar:capsize
| 8 | 4 | 150 | #7BC8F6 | #EE0000 | 4

## bimg
Task with bounds | Width | Height | Dpi | Fill:color | Fill:hatch | Fill:alpha | Plot:format | Plot:markeredgewidth | Step:linewidth
| 8 | 4 | 150 | #90EE90 | / | 0.2 | o | 0.5 | 0.5

## eimg
Experts per day stacked | Width | Height | Dpi | Bar:alpha
| 8 | 4 | 150 | 0.6