## expert
Name | Comment | TRUE
DEV.Adam | the 2nd unit | 1
DEV.Andrew | the 2nd unit | 1
DEV.Anna | the 2nd unit | 1
DEV.Ava | the 2nd unit | 1
DEV.Carl | the 1st unit | 1
DEV.Charles | the 1st unit | 1
DEV.Dorothy | the 2nd unit | 1
DEV.Edward | the 2nd unit | 1
DEV.Eric | the 2nd unit | 1
DEV.Frances | the 1st unit | 1
DEV.Francis | the 1st unit | 1
DEV.Fred | the 2nd unit | 1
DEV.Hugo | the 1st unit | 1
DEV.Jacob | the 2nd unit | 1
DEV.Lars | the 1st unit | 1
DEV.Lennart | the 1st unit | 1
DEV.Martin | the 1st unit | 1
DEV.Max | the 2nd unit | 1
DEV.Michael | the 1st unit | 1
DEV.Molly | the 2nd unit | 1
DEV.Paul | the 1st unit | 1
DEV.Sabina | the 1st unit | 1
DEV.Stefan | the 2nd unit | 1
DEV.Tom | the 1st unit | 1
DEV.Uma | the 2nd unit | 1
PM.Angel | the 1st unit | 1
PM.Anthony | the 2nd unit | 1
PM.Daniel | the 1st unit | 1
PM.Fabian | the 2nd unit | 1
PM.Henry | the 2nd unit | 1
PM.Lisa | the 1st unit | 1
SA.Adrian | the 1st unit | 1
SA.Albert | the 1st unit | 1
SA.Justin | the 2nd unit | 1
SA.Kate | the 1st unit | 1
SA.Kevin | the 2nd unit | 1
SA.Martha | the 2nd unit | 1
SA.Melanie | the 2nd unit | 1
SA.Peter | the 2nd unit | 1
SA.Robert | the 1st unit | 1
Note on C1: Has Expert any task?

## task
Name | Start | End | Work | Days | Workdays | Avg[h/day] | Lower | Upper | TRUE | TRUE | TRUE
charlie.pm | 2025-01-01 | 2025-06-05 | 80 | 156 | 110 | 0.72727 | 0.5 | 0.75 | TRUE | TRUE | TRUE
charlie.pf | 2025-06-06 | 2025-07-06 | 10 | 31 | 21 | 0.47619 | 0.25 | 0.5 | TRUE | TRUE | TRUE
delta.pm | 2025-01-01 | 2025-02-25 | 25 | 56 | 39 | 0.64103 | 0.5 | 0.75 | TRUE | TRUE | TRUE
delta.pf | 2025-02-26 | 2025-04-12 | 5 | 46 | 33 | 0.15152 | 0 | 0.25 | TRUE | TRUE | TRUE
juliet.pe | 2025-02-10 | 2025-02-27 | 10 | 18 | 14 | 0.71429 | 0.5 | 0.75 | TRUE | TRUE | TRUE
juliet.pm | 2025-02-28 | 2025-06-30 | 50 | 123 | 86 | 0.5814 | 0.5 | 0.75 | TRUE | TRUE | TRUE
juliet.pf | 2025-07-01 | 2025-08-15 | 5 | 46 | 34 | 0.14706 | 0 | 0.25 | TRUE | TRUE | TRUE
mike.pe | 2025-04-10 | 2025-04-20 | 10 | 11 | 7 | 1.4286 | 1.25 | 1.5 | TRUE | TRUE | TRUE
mike.pm | 2025-04-21 | 2025-09-25 | 50 | 158 | 113 | 0.44248 | 0.25 | 0.5 | TRUE | TRUE | TRUE
mike.pf | 2025-09-26 | 2025-10-30 | 5 | 35 | 25 | 0.2 | 0 | 0.25 | TRUE | TRUE | TRUE
november.pe | 2025-05-26 | 2025-06-14 | 10 | 20 | 15 | 0.66667 | 0.5 | 0.75 | TRUE | TRUE | TRUE
november.pm | 2025-06-15 | 2025-12-30 | 55 | 199 | 142 | 0.38732 | 0.25 | 0.5 | TRUE | TRUE | TRUE
november.pf | 2025-12-31 | 2026-01-31 | 5 | 32 | 23 | 0.21739 | 0 | 0.25 | TRUE | TRUE | TRUE
oscar2.pm | 2025-01-01 | 2025-06-20 | 60 | 171 | 121 | 0.49587 | 0.25 | 0.5 | TRUE | TRUE | TRUE
oscar2.pf | 2025-06-21 | 2025-06-30 | 20 | 10 | 6 | 3.3333 | 3.25 | 3.5 | TRUE | TRUE | TRUE
papa2.pm | 2025-01-01 | 2025-06-20 | 100 | 171 | 121 | 0.82645 | 0.75 | 1 | TRUE | TRUE | TRUE
papa2.pf | 2025-06-21 | 2025-06-30 | 20 | 10 | 6 | 3.3333 | 3.25 | 3.5 | TRUE | TRUE | TRUE
quebec2.pe | 2025-06-01 | 2025-06-26 | 25 | 26 | 19 | 1.3158 | 1.25 | 1.5 | TRUE | TRUE | TRUE
quebec2.pm | 2025-06-27 | 2026-11-09 | 120 | 501 | 357 | 0.33613 | 0.25 | 0.5 | TRUE | TRUE | TRUE
quebec2.pf | 2026-11-10 | 2027-01-04 | 20 | 56 | 40 | 0.5 | 0.5 | 0.75 | TRUE | TRUE | TRUE
sierra2.pm | 2025-01-01 | 2025-03-02 | 40 | 61 | 42 | 0.95238 | 0.75 | 1 | TRUE | TRUE | TRUE
sierra2.pf | 2025-03-03 | 2025-03-10 | 10 | 8 | 6 | 1.6667 | 1.5 | 1.75 | TRUE | TRUE | TRUE
xray2.pe | 2025-07-15 | 2025-08-09 | 25 | 26 | 19 | 1.3158 | 1.25 | 1.5 | TRUE | TRUE | TRUE
xray2.pm | 2025-08-10 | 2026-01-07 | 120 | 151 | 108 | 1.1111 | 1 | 1.25 | TRUE | TRUE | TRUE
xray2.pf | 2026-01-08 | 2026-02-01 | 10 | 25 | 17 | 0.58824 | 0.5 | 0.75 | TRUE | TRUE | TRUE
alpha.pm | 2025-01-01 | 2025-04-01 | 45 | 91 | 64 | 0.70312 | 0.5 | 0.75 | TRUE | TRUE | TRUE
alpha.pf | 2025-04-02 | 2025-05-02 | 5 | 31 | 22 | 0.22727 | 0 | 0.25 | TRUE | TRUE | TRUE
beta.pm | 2025-01-01 | 2025-06-20 | 65 | 171 | 121 | 0.53719 | 0.5 | 0.75 | TRUE | TRUE | TRUE
beta.pf | 2025-06-21 | 2025-08-05 | 5 | 46 | 32 | 0.15625 | 0 | 0.25 | TRUE | TRUE | TRUE
india.pm | 2025-01-01 | 2025-10-01 | 130 | 274 | 194 | 0.6701 | 0.5 | 0.75 | TRUE | TRUE | TRUE
india.pf | 2025-10-02 | 2025-11-01 | 25 | 31 | 22 | 1.1364 | 1 | 1.25 | TRUE | TRUE | TRUE
oscar.pe | 2025-06-25 | 2025-07-09 | 15 | 15 | 11 | 1.3636 | 1.25 | 1.5 | TRUE | TRUE | TRUE
oscar.pm | 2025-07-10 | 2025-12-30 | 70 | 174 | 124 | 0.56452 | 0.5 | 0.75 | TRUE | TRUE | TRUE
oscar.pf | 2025-12-31 | 2026-01-31 | 10 | 32 | 23 | 0.43478 | 0.25 | 0.5 | TRUE | TRUE | TRUE
lima2.pm | 2025-01-01 | 2025-02-25 | 25 | 56 | 39 | 0.64103 | 0.5 | 0.75 | TRUE | TRUE | TRUE
lima2.pf | 2025-02-26 | 2025-03-03 | 15 | 6 | 4 | 3.75 | 3.75 | 4 | TRUE | TRUE | TRUE
mike2.pe | 2025-01-10 | 2025-01-15 | 20 | 6 | 4 | 5 | 5 | 5.25 | TRUE | TRUE | TRUE
mike2.pm | 2025-01-16 | 2025-05-16 | 80 | 121 | 86 | 0.93023 | 0.75 | 1 | TRUE | TRUE | TRUE
mike2.pf | 2025-05-17 | 2025-06-01 | 20 | 16 | 10 | 2 | 2 | 2.25 | TRUE | TRUE | TRUE
whisky2.pe | 2025-06-25 | 2025-07-10 | 60 | 16 | 12 | 5 | 5 | 5.25 | TRUE | TRUE | TRUE
whisky2.pm | 2025-07-11 | 2026-04-07 | 200 | 271 | 193 | 1.0363 | 1 | 1.25 | TRUE | TRUE | TRUE
whisky2.pf | 2026-04-08 | 2026-04-30 | 20 | 23 | 17 | 1.1765 | 1 | 1.25 | TRUE | TRUE | TRUE
echo.pm | 2025-01-01 | 2025-03-15 | 20 | 74 | 52 | 0.38462 | 0.25 | 0.5 | TRUE | TRUE | TRUE
echo.pf | 2025-04-02 | 2025-05-17 | 5 | 46 | 32 | 0.15625 | 0 | 0.25 | TRUE | TRUE | TRUE
foxtrot.pm | 2025-01-01 | 2025-04-01 | 20 | 91 | 64 | 0.3125 | 0.25 | 0.5 | TRUE | TRUE | TRUE
foxtrot.pf | 2025-04-02 | 2025-05-02 | 5 | 31 | 22 | 0.22727 | 0 | 0.25 | TRUE | TRUE | TRUE
golf.pm | 2025-01-01 | 2025-05-12 | 40 | 132 | 92 | 0.43478 | 0.25 | 0.5 | TRUE | TRUE | TRUE
golf.pf | 2025-05-13 | 2025-06-27 | 10 | 46 | 34 | 0.29412 | 0.25 | 0.5 | TRUE | TRUE | TRUE
hotel.pm | 2025-01-01 | 2025-09-01 | 80 | 244 | 172 | 0.46512 | 0.25 | 0.5 | TRUE | TRUE | TRUE
hotel.pf | 2025-09-02 | 2025-10-17 | 10 | 46 | 34 | 0.29412 | 0.25 | 0.5 | TRUE | TRUE | TRUE
kilo.pe | 2025-03-01 | 2025-03-24 | 25 | 24 | 16 | 1.5625 | 1.5 | 1.75 | TRUE | TRUE | TRUE
kilo.pm | 2025-03-25 | 2025-08-01 | 15 | 130 | 93 | 0.16129 | 0 | 0.25 | TRUE | TRUE | TRUE
kilo.pf | 2025-08-02 | 2025-09-16 | 20 | 46 | 32 | 0.625 | 0.5 | 0.75 | TRUE | TRUE | TRUE
lima.pe | 2025-03-21 | 2025-04-19 | 25 | 30 | 21 | 1.1905 | 1 | 1.25 | TRUE | TRUE | TRUE
lima.pm | 2025-04-20 | 2025-11-01 | 100 | 196 | 139 | 0.71942 | 0.5 | 0.75 | TRUE | TRUE | TRUE
lima.pf | 2025-11-02 | 2025-11-30 | 20 | 29 | 20 | 1 | 1 | 1.25 | TRUE | TRUE | TRUE
zulu2.pe | 2025-06-15 | 2025-07-15 | 50 | 31 | 22 | 2.2727 | 2.25 | 2.5 | TRUE | TRUE | TRUE
zulu2.pm | 2025-07-16 | 2025-11-23 | 90 | 131 | 93 | 0.96774 | 0.75 | 1 | TRUE | TRUE | TRUE
zulu2.pf | 2025-11-24 | 2025-12-01 | 20 | 8 | 6 | 3.3333 | 3.25 | 3.5 | TRUE | TRUE | TRUE
alpha2.pe | 2025-01-27 | 2025-02-01 | 10 | 6 | 5 | 2 | 2 | 2.25 | TRUE | TRUE | TRUE
alpha2.pm | 2025-02-02 | 2025-03-19 | 40 | 46 | 33 | 1.2121 | 1 | 1.25 | TRUE | TRUE | TRUE
alpha2.pf | 2025-03-20 | 2025-04-01 | 10 | 13 | 9 | 1.1111 | 1 | 1.25 | TRUE | TRUE | TRUE
beta2.pe | 2025-01-05 | 2025-01-15 | 50 | 11 | 8 | 6.25 | 6.25 | 6.5 | TRUE | TRUE | TRUE
beta2.pm | 2025-01-16 | 2025-07-15 | 80 | 181 | 128 | 0.625 | 0.5 | 0.75 | TRUE | TRUE | TRUE
beta2.pf | 2025-07-16 | 2025-08-04 | 40 | 20 | 14 | 2.8571 | 2.75 | 3 | TRUE | TRUE | TRUE
juliet2.pm | 2025-01-01 | 2025-03-22 | 50 | 81 | 57 | 0.87719 | 0.75 | 1 | TRUE | TRUE | TRUE
juliet2.pf | 2025-03-23 | 2025-04-01 | 10 | 10 | 7 | 1.4286 | 1.25 | 1.5 | TRUE | TRUE | TRUE
delta2.pm | 2025-01-01 | 2025-06-20 | 30 | 171 | 121 | 0.24793 | 0 | 0.25 | TRUE | TRUE | TRUE
delta2.pf | 2025-06-21 | 2025-07-01 | 10 | 11 | 7 | 1.4286 | 1.25 | 1.5 | TRUE | TRUE | TRUE
echo2.pm | 2025-01-01 | 2025-01-21 | 20 | 21 | 14 | 1.4286 | 1.25 | 1.5 | TRUE | TRUE | TRUE
echo2.pf | 2025-01-22 | 2025-03-10 | 10 | 48 | 34 | 0.29412 | 0.25 | 0.5 | TRUE | TRUE | TRUE
foxtrot2.pm | 2025-01-01 | 2025-03-22 | 10 | 81 | 57 | 0.17544 | 0 | 0.25 | TRUE | TRUE | TRUE
foxtrot2.pf | 2025-03-23 | 2025-04-01 | 5 | 10 | 7 | 0.71429 | 0.5 | 0.75 | TRUE | TRUE | TRUE
gamma2.pm | 2025-01-01 | 2025-01-21 | 15 | 21 | 14 | 1.0714 | 1 | 1.25 | TRUE | TRUE | TRUE
gamma2.pf | 2025-01-22 | 2025-02-03 | 10 | 13 | 9 | 1.1111 | 1 | 1.25 | TRUE | TRUE | TRUE
golf2.pm | 2025-01-01 | 2025-03-22 | 40 | 81 | 57 | 0.70175 | 0.5 | 0.75 | TRUE | TRUE | TRUE
golf2.pf | 2025-03-23 | 2025-03-31 | 15 | 9 | 6 | 2.5 | 2.5 | 2.75 | TRUE | TRUE | TRUE
hotel2.pm | 2025-01-01 | 2025-02-15 | 10 | 46 | 32 | 0.3125 | 0.25 | 0.5 | TRUE | TRUE | TRUE
hotel2.pf | 2025-02-16 | 2025-02-25 | 5 | 10 | 7 | 0.71429 | 0.5 | 0.75 | TRUE | TRUE | TRUE
tango2.pe | 2025-02-01 | 2025-02-16 | 50 | 16 | 10 | 5 | 5 | 5.25 | TRUE | TRUE | TRUE
tango2.pm | 2025-02-17 | 2025-09-15 | 150 | 211 | 150 | 1 | 1 | 1.25 | TRUE | TRUE | TRUE
tango2.pf | 2025-09-16 | 2025-10-01 | 30 | 16 | 12 | 2.5 | 2.5 | 2.75 | TRUE | TRUE | TRUE
uniform2.pe | 2025-05-01 | 2025-05-16 | 50 | 16 | 11 | 4.5455 | 4.5 | 4.75 | TRUE | TRUE | TRUE
uniform2.pm | 2025-05-17 | 2026-02-11 | 160 | 271 | 193 | 0.82902 | 0.75 | 1 | TRUE | TRUE | TRUE
uniform2.pf | 2026-02-12 | 2026-03-02 | 20 | 19 | 13 | 1.5385 | 1.5 | 1.75 | TRUE | TRUE | TRUE
india2.pm | 2025-01-01 | 2025-03-17 | 40 | 76 | 53 | 0.75472 | 0.75 | 1 | TRUE | TRUE | TRUE
india2.pf | 2025-03-18 | 2025-03-25 | 10 | 8 | 6 | 1.6667 | 1.5 | 1.75 | TRUE | TRUE | TRUE
kilo2.pm | 2025-01-01 | 2025-02-25 | 30 | 56 | 39 | 0.76923 | 0.75 | 1 | TRUE | TRUE | TRUE
kilo2.pf | 2025-02-26 | 2025-03-03 | 15 | 6 | 4 | 3.75 | 3.75 | 4 | TRUE | TRUE | TRUE
november2.pm | 2025-01-01 | 2025-03-27 | 60 | 86 | 61 | 0.98361 | 0.75 | 1 | TRUE | TRUE | TRUE
november2.pf | 2025-03-28 | 2025-04-07 | 20 | 11 | 7 | 2.8571 | 2.75 | 3 | TRUE | TRUE | TRUE
romeo2.pm | 2025-01-01 | 2025-05-21 | 30 | 141 | 99 | 0.30303 | 0.25 | 0.5 | TRUE | TRUE | TRUE
romeo2.pf | 2025-05-22 | 2025-06-02 | 15 | 12 | 8 | 1.875 | 1.75 | 2 | TRUE | TRUE | TRUE
victor2.pe | 2025-03-15 | 2025-04-09 | 60 | 26 | 18 | 3.3333 | 3.25 | 3.5 | TRUE | TRUE | TRUE
victor2.pm | 2025-04-10 | 2025-08-18 | 90 | 131 | 92 | 0.97826 | 0.75 | 1 | TRUE | TRUE | TRUE
victor2.pf | 2025-08-19 | 2025-09-01 | 20 | 14 | 10 | 2 | 2 | 2.25 | TRUE | TRUE | TRUE
golf2.sm | 2025-01-01 | 2025-03-22 | 20 | 81 | 57 | 0.35088 | 0.25 | 0.5 | TRUE | TRUE | TRUE
golf2.sf | 2025-03-23 | 2025-03-31 | 10 | 9 | 6 | 1.6667 | 1.5 | 1.75 | TRUE | TRUE | TRUE
tango2.se | 2025-02-01 | 2025-02-16 | 60 | 16 | 10 | 6 | 6 | 6.25 | TRUE | TRUE | TRUE
tango2.sm | 2025-02-17 | 2025-09-15 | 60 | 211 | 150 | 0.4 | 0.25 | 0.5 | TRUE | TRUE | TRUE
tango2.sf | 2025-09-16 | 2025-10-01 | 20 | 16 | 12 | 1.6667 | 1.5 | 1.75 | TRUE | TRUE | TRUE
victor2.se | 2025-02-15 | 2025-03-02 | 20 | 16 | 10 | 2 | 2 | 2.25 | TRUE | TRUE | TRUE
victor2.sm | 2025-03-03 | 2025-08-20 | 20 | 171 | 122 | 0.16393 | 0 | 0.25 | TRUE | TRUE | TRUE
victor2.sf | 2025-08-21 | 2025-09-01 | 10 | 12 | 8 | 1.25 | 1.25 | 1.5 | TRUE | TRUE | TRUE
alpha.sm | 2025-01-01 | 2025-04-01 | 10 | 91 | 64 | 0.15625 | 0 | 0.25 | TRUE | TRUE | TRUE
alpha.sf | 2025-04-02 | 2025-05-02 | 5 | 31 | 22 | 0.22727 | 0 | 0.25 | TRUE | TRUE | TRUE
beta.sm | 2025-01-01 | 2025-06-20 | 10 | 171 | 121 | 0.082645 | 0 | 0.25 | TRUE | TRUE | TRUE
beta.sf | 2025-06-21 | 2025-08-05 | 5 | 46 | 32 | 0.15625 | 0 | 0.25 | TRUE | TRUE | TRUE
charlie.sm | 2025-01-01 | 2025-06-05 | 15 | 156 | 110 | 0.13636 | 0 | 0.25 | TRUE | TRUE | TRUE
charlie.sf | 2025-06-06 | 2025-07-06 | 5 | 31 | 21 | 0.2381 | 0 | 0.25 | TRUE | TRUE | TRUE
delta.sm | 2025-01-01 | 2025-02-25 | 5 | 56 | 39 | 0.12821 | 0 | 0.25 | TRUE | TRUE | TRUE
delta.sf | 2025-02-26 | 2025-04-12 | 5 | 46 | 33 | 0.15152 | 0 | 0.25 | TRUE | TRUE | TRUE
echo.sm | 2025-01-01 | 2025-03-15 | 5 | 74 | 52 | 0.096154 | 0 | 0.25 | TRUE | TRUE | TRUE
echo.sf | 2025-04-02 | 2025-05-17 | 8 | 46 | 32 | 0.25 | 0.25 | 0.5 | TRUE | TRUE | TRUE
golf.sm | 2025-01-01 | 2025-05-12 | 10 | 132 | 92 | 0.1087 | 0 | 0.25 | TRUE | TRUE | TRUE
golf.sf | 2025-05-13 | 2025-06-27 | 8 | 46 | 34 | 0.23529 | 0 | 0.25 | TRUE | TRUE | TRUE
kilo.se | 2025-03-01 | 2025-03-24 | 15 | 24 | 16 | 0.9375 | 0.75 | 1 | TRUE | TRUE | TRUE
kilo.sm | 2025-03-25 | 2025-08-01 | 10 | 130 | 93 | 0.10753 | 0 | 0.25 | TRUE | TRUE | TRUE
kilo.sf | 2025-08-02 | 2025-09-16 | 5 | 46 | 32 | 0.15625 | 0 | 0.25 | TRUE | TRUE | TRUE
lima.se | 2025-03-21 | 2025-04-19 | 36 | 30 | 21 | 1.7143 | 1.5 | 1.75 | TRUE | TRUE | TRUE
lima.sm | 2025-04-20 | 2025-11-01 | 10 | 196 | 139 | 0.071942 | 0 | 0.25 | TRUE | TRUE | TRUE
lima.sf | 2025-11-02 | 2025-11-30 | 5 | 29 | 20 | 0.25 | 0.25 | 0.5 | TRUE | TRUE | TRUE
mike.se | 2025-03-21 | 2025-04-19 | 15 | 30 | 21 | 0.71429 | 0.5 | 0.75 | TRUE | TRUE | TRUE
mike.sm | 2025-04-20 | 2025-11-01 | 10 | 196 | 139 | 0.071942 | 0 | 0.25 | TRUE | TRUE | TRUE
mike.sf | 2025-11-02 | 2025-11-30 | 5 | 29 | 20 | 0.25 | 0.25 | 0.5 | TRUE | TRUE | TRUE
foxtrot.sm | 2025-01-01 | 2025-04-01 | 8 | 91 | 64 | 0.125 | 0 | 0.25 | TRUE | TRUE | TRUE
foxtrot.sf | 2025-04-02 | 2025-05-02 | 8 | 31 | 22 | 0.36364 | 0.25 | 0.5 | TRUE | TRUE | TRUE
hotel.sm | 2025-01-01 | 2025-09-01 | 15 | 244 | 172 | 0.087209 | 0 | 0.25 | TRUE | TRUE | TRUE
hotel.sf | 2025-09-02 | 2025-10-17 | 5 | 46 | 34 | 0.14706 | 0 | 0.25 | TRUE | TRUE | TRUE
india.sm | 2025-01-01 | 2025-10-01 | 30 | 274 | 194 | 0.15464 | 0 | 0.25 | TRUE | TRUE | TRUE
india.sf | 2025-10-02 | 2025-11-01 | 12 | 31 | 22 | 0.54545 | 0.5 | 0.75 | TRUE | TRUE | TRUE
juliet.se | 2025-02-10 | 2025-02-27 | 10 | 18 | 14 | 0.71429 | 0.5 | 0.75 | TRUE | TRUE | TRUE
juliet.sm | 2025-02-28 | 2025-06-30 | 10 | 123 | 86 | 0.11628 | 0 | 0.25 | TRUE | TRUE | TRUE
juliet.sf | 2025-07-01 | 2025-08-15 | 5 | 46 | 34 | 0.14706 | 0 | 0.25 | TRUE | TRUE | TRUE
november.se | 2025-05-26 | 2025-06-14 | 10 | 20 | 15 | 0.66667 | 0.5 | 0.75 | TRUE | TRUE | TRUE
november.sm | 2025-06-15 | 2025-12-30 | 10 | 199 | 142 | 0.070423 | 0 | 0.25 | TRUE | TRUE | TRUE
november.sf | 2025-12-31 | 2026-01-31 | 5 | 32 | 23 | 0.21739 | 0 | 0.25 | TRUE | TRUE | TRUE
oscar.se | 2025-06-25 | 2025-07-09 | 10 | 15 | 11 | 0.90909 | 0.75 | 1 | TRUE | TRUE | TRUE
oscar.sm | 2025-07-10 | 2025-12-30 | 10 | 174 | 124 | 0.080645 | 0 | 0.25 | TRUE | TRUE | TRUE
oscar.sf | 2025-12-31 | 2026-01-31 | 8 | 32 | 23 | 0.34783 | 0.25 | 0.5 | TRUE | TRUE | TRUE
alpha2.se | 2025-01-27 | 2025-02-01 | 12 | 6 | 5 | 2.4 | 2.25 | 2.5 | TRUE | TRUE | TRUE
alpha2.sm | 2025-02-02 | 2025-03-19 | 24 | 46 | 33 | 0.72727 | 0.5 | 0.75 | TRUE | TRUE | TRUE
alpha2.sf | 2025-03-20 | 2025-04-01 | 8 | 13 | 9 | 0.88889 | 0.75 | 1 | TRUE | TRUE | TRUE
beta2.se | 2025-01-05 | 2025-01-15 | 30 | 11 | 8 | 3.75 | 3.75 | 4 | TRUE | TRUE | TRUE
beta2.sm | 2025-01-16 | 2025-07-15 | 60 | 181 | 128 | 0.46875 | 0.25 | 0.5 | TRUE | TRUE | TRUE
beta2.sf | 2025-07-16 | 2025-08-04 | 40 | 20 | 14 | 2.8571 | 2.75 | 3 | TRUE | TRUE | TRUE
gamma2.sm | 2025-01-01 | 2025-01-21 | 15 | 21 | 14 | 1.0714 | 1 | 1.25 | TRUE | TRUE | TRUE
gamma2.sf | 2025-01-22 | 2025-02-03 | 5 | 13 | 9 | 0.55556 | 0.5 | 0.75 | TRUE | TRUE | TRUE
quebec2.se | 2025-06-01 | 2025-06-26 | 40 | 26 | 19 | 2.1053 | 2 | 2.25 | TRUE | TRUE | TRUE
quebec2.sm | 2025-06-27 | 2026-11-09 | 20 | 501 | 357 | 0.056022 | 0 | 0.25 | TRUE | TRUE | TRUE
quebec2.sf | 2026-11-10 | 2027-01-04 | 20 | 56 | 40 | 0.5 | 0.5 | 0.75 | TRUE | TRUE | TRUE
uniform2.se | 2025-05-01 | 2025-05-16 | 60 | 16 | 11 | 5.4545 | 5.25 | 5.5 | TRUE | TRUE | TRUE
uniform2.sm | 2025-05-17 | 2026-02-11 | 50 | 271 | 193 | 0.25907 | 0.25 | 0.5 | TRUE | TRUE | TRUE
uniform2.sf | 2026-02-12 | 2026-03-02 | 20 | 19 | 13 | 1.5385 | 1.5 | 1.75 | TRUE | TRUE | TRUE
xray2.se | 2025-07-15 | 2025-08-09 | 20 | 26 | 19 | 1.0526 | 1 | 1.25 | TRUE | TRUE | TRUE
xray2.sm | 2025-08-10 | 2026-01-07 | 30 | 151 | 108 | 0.27778 | 0.25 | 0.5 | TRUE | TRUE | TRUE
xray2.sf | 2026-01-08 | 2026-02-01 | 20 | 25 | 17 | 1.1765 | 1 | 1.25 | TRUE | TRUE | TRUE
india2.sm | 2025-01-01 | 2025-03-17 | 10 | 76 | 53 | 0.18868 | 0 | 0.25 | TRUE | TRUE | TRUE
india2.sf | 2025-03-18 | 2025-03-25 | 10 | 8 | 6 | 1.6667 | 1.5 | 1.75 | TRUE | TRUE | TRUE
juliet2.sm | 2025-01-01 | 2025-03-22 | 20 | 81 | 57 | 0.35088 | 0.25 | 0.5 | TRUE | TRUE | TRUE
juliet2.sf | 2025-03-23 | 2025-04-01 | 15 | 10 | 7 | 2.1429 | 2 | 2.25 | TRUE | TRUE | TRUE
lima2.sm | 2025-01-01 | 2025-02-25 | 10 | 56 | 39 | 0.25641 | 0.25 | 0.5 | TRUE | TRUE | TRUE
lima2.sf | 2025-02-26 | 2025-03-03 | 10 | 6 | 4 | 2.5 | 2.5 | 2.75 | TRUE | TRUE | TRUE
kilo2.sm | 2025-01-01 | 2025-02-25 | 15 | 56 | 39 | 0.38462 | 0.25 | 0.5 | TRUE | TRUE | TRUE
kilo2.sf | 2025-02-26 | 2025-03-03 | 10 | 6 | 4 | 2.5 | 2.5 | 2.75 | TRUE | TRUE | TRUE
november2.sm | 2025-01-01 | 2025-03-27 | 30 | 86 | 61 | 0.4918 | 0.25 | 0.5 | TRUE | TRUE | TRUE
november2.sf | 2025-03-28 | 2025-04-07 | 15 | 11 | 7 | 2.1429 | 2 | 2.25 | TRUE | TRUE | TRUE
oscar2.sm | 2025-01-01 | 2025-06-20 | 30 | 171 | 121 | 0.24793 | 0 | 0.25 | TRUE | TRUE | TRUE
oscar2.sf | 2025-06-21 | 2025-06-30 | 10 | 10 | 6 | 1.6667 | 1.5 | 1.75 | TRUE | TRUE | TRUE
papa2.sm | 2025-01-01 | 2025-06-20 | 40 | 171 | 121 | 0.33058 | 0.25 | 0.5 | TRUE | TRUE | TRUE
papa2.sf | 2025-06-21 | 2025-06-30 | 15 | 10 | 6 | 2.5 | 2.5 | 2.75 | TRUE | TRUE | TRUE
zulu2.se | 2025-06-15 | 2025-07-15 | 50 | 31 | 22 | 2.2727 | 2.25 | 2.5 | TRUE | TRUE | TRUE
zulu2.sm | 2025-07-16 | 2025-11-23 | 20 | 131 | 93 | 0.21505 | 0 | 0.25 | TRUE | TRUE | TRUE
zulu2.sf | 2025-11-24 | 2025-12-01 | 10 | 8 | 6 | 1.6667 | 1.5 | 1.75 | TRUE | TRUE | TRUE
delta2.sm | 2025-01-01 | 2025-06-20 | 20 | 171 | 121 | 0.16529 | 0 | 0.25 | TRUE | TRUE | TRUE
delta2.sf | 2025-06-21 | 2025-07-01 | 10 | 11 | 7 | 1.4286 | 1.25 | 1.5 | TRUE | TRUE | TRUE
echo2.sm | 2025-01-01 | 2025-01-21 | 10 | 21 | 14 | 0.71429 | 0.5 | 0.75 | TRUE | TRUE | TRUE
echo2.sf | 2025-01-22 | 2025-03-10 | 5 | 48 | 34 | 0.14706 | 0 | 0.25 | TRUE | TRUE | TRUE
foxtrot2.sm | 2025-01-01 | 2025-03-22 | 50 | 81 | 57 | 0.87719 | 0.75 | 1 | TRUE | TRUE | TRUE
foxtrot2.sf | 2025-03-23 | 2025-04-01 | 30 | 10 | 7 | 4.2857 | 4.25 | 4.5 | TRUE | TRUE | TRUE
hotel2.sm | 2025-01-01 | 2025-02-15 | 10 | 46 | 32 | 0.3125 | 0.25 | 0.5 | TRUE | TRUE | TRUE
hotel2.sf | 2025-02-16 | 2025-02-25 | 5 | 10 | 7 | 0.71429 | 0.5 | 0.75 | TRUE | TRUE | TRUE
mike2.se | 2025-01-10 | 2025-01-25 | 40 | 16 | 11 | 3.6364 | 3.5 | 3.75 | TRUE | TRUE | TRUE
mike2.sm | 2025-01-26 | 2025-05-16 | 20 | 111 | 79 | 0.25316 | 0.25 | 0.5 | TRUE | TRUE | TRUE
mike2.sf | 2025-05-17 | 2025-06-01 | 10 | 16 | 10 | 1 | 1 | 1.25 | TRUE | TRUE | TRUE
alpha.m | 2025-01-01 | 2025-04-01 | 450 | 91 | 64 | 7.0312 | 7 | 7.25 | TRUE | TRUE | TRUE
alpha.f | 2025-04-02 | 2025-05-02 | 60 | 31 | 22 | 2.7273 | 2.5 | 2.75 | TRUE | TRUE | TRUE
beta.m | 2025-01-01 | 2025-06-20 | 650 | 171 | 121 | 5.3719 | 5.25 | 5.5 | TRUE | TRUE | TRUE
beta.f | 2025-06-21 | 2025-08-05 | 30 | 46 | 32 | 0.9375 | 0.75 | 1 | TRUE | TRUE | TRUE
charlie.m | 2025-01-01 | 2025-06-05 | 800 | 156 | 110 | 7.2727 | 7.25 | 7.5 | TRUE | TRUE | TRUE
charlie.f | 2025-06-06 | 2025-07-06 | 100 | 31 | 21 | 4.7619 | 4.75 | 5 | TRUE | TRUE | TRUE
delta.m | 2025-01-01 | 2025-02-25 | 220 | 56 | 39 | 5.641 | 5.5 | 5.75 | TRUE | TRUE | TRUE
delta.f | 2025-02-26 | 2025-04-12 | 20 | 46 | 33 | 0.60606 | 0.5 | 0.75 | TRUE | TRUE | TRUE
echo.m | 2025-01-01 | 2025-03-15 | 250 | 74 | 52 | 4.8077 | 4.75 | 5 | TRUE | TRUE | TRUE
echo.f | 2025-04-02 | 2025-05-17 | 25 | 46 | 32 | 0.78125 | 0.75 | 1 | TRUE | TRUE | TRUE
foxtrot.m | 2025-01-01 | 2025-04-01 | 150 | 91 | 64 | 2.3438 | 2.25 | 2.5 | TRUE | TRUE | TRUE
foxtrot.f | 2025-04-02 | 2025-05-02 | 25 | 31 | 22 | 1.1364 | 1 | 1.25 | TRUE | TRUE | TRUE
golf.m | 2025-01-01 | 2025-05-12 | 350 | 132 | 92 | 3.8043 | 3.75 | 4 | TRUE | TRUE | TRUE
golf.f | 2025-05-13 | 2025-06-27 | 30 | 46 | 34 | 0.88235 | 0.75 | 1 | TRUE | TRUE | TRUE
hotel.m | 2025-01-01 | 2025-09-01 | 750 | 244 | 172 | 4.3605 | 4.25 | 4.5 | TRUE | TRUE | TRUE
hotel.f | 2025-09-02 | 2025-10-17 | 70 | 46 | 34 | 2.0588 | 2 | 2.25 | TRUE | TRUE | TRUE
india.m | 2025-01-01 | 2025-10-01 | 1100 | 274 | 194 | 5.6701 | 5.5 | 5.75 | TRUE | TRUE | TRUE
india.f | 2025-10-02 | 2025-11-01 | 200 | 31 | 22 | 9.0909 | 9 | 9.25 | TRUE | TRUE | TRUE
juliet.e | 2025-02-10 | 2025-02-27 | 10 | 18 | 14 | 0.71429 | 0.5 | 0.75 | TRUE | TRUE | TRUE
juliet.m | 2025-02-28 | 2025-06-30 | 450 | 123 | 86 | 5.2326 | 5 | 5.25 | TRUE | TRUE | TRUE
juliet.f | 2025-07-01 | 2025-08-15 | 35 | 46 | 34 | 1.0294 | 1 | 1.25 | TRUE | TRUE | TRUE
kilo.e | 2025-03-01 | 2025-03-24 | 20 | 24 | 16 | 1.25 | 1.25 | 1.5 | TRUE | TRUE | TRUE
kilo.m | 2025-03-25 | 2025-08-01 | 550 | 130 | 93 | 5.914 | 5.75 | 6 | TRUE | TRUE | TRUE
kilo.f | 2025-08-02 | 2025-09-16 | 40 | 46 | 32 | 1.25 | 1.25 | 1.5 | TRUE | TRUE | TRUE
lima.e | 2025-03-21 | 2025-04-19 | 30 | 30 | 21 | 1.4286 | 1.25 | 1.5 | TRUE | TRUE | TRUE
lima.m | 2025-04-20 | 2025-11-01 | 1050 | 196 | 139 | 7.554 | 7.5 | 7.75 | TRUE | TRUE | TRUE
lima.f | 2025-11-02 | 2025-11-30 | 120 | 29 | 20 | 6 | 6 | 6.25 | TRUE | TRUE | TRUE
mike.e | 2025-04-10 | 2025-04-20 | 10 | 11 | 7 | 1.4286 | 1.25 | 1.5 | TRUE | TRUE | TRUE
mike.m | 2025-04-25 | 2025-09-25 | 450 | 154 | 109 | 4.1284 | 4 | 4.25 | TRUE | TRUE | TRUE
mike.f | 2025-09-26 | 2025-10-30 | 60 | 35 | 25 | 2.4 | 2.25 | 2.5 | TRUE | TRUE | TRUE
november.e | 2025-05-26 | 2025-06-14 | 10 | 20 | 15 | 0.66667 | 0.5 | 0.75 | TRUE | TRUE | TRUE
november.m | 2025-06-15 | 2025-12-30 | 550 | 199 | 142 | 3.8732 | 3.75 | 4 | TRUE | TRUE | TRUE
november.f | 2025-12-31 | 2026-01-31 | 30 | 32 | 23 | 1.3043 | 1.25 | 1.5 | TRUE | TRUE | TRUE
oscar.e | 2025-06-25 | 2025-07-09 | 15 | 15 | 11 | 1.3636 | 1.25 | 1.5 | TRUE | TRUE | TRUE
oscar.m | 2025-07-10 | 2025-12-30 | 600 | 174 | 124 | 4.8387 | 4.75 | 5 | TRUE | TRUE | TRUE
oscar.f | 2025-12-31 | 2026-01-31 | 40 | 32 | 23 | 1.7391 | 1.5 | 1.75 | TRUE | TRUE | TRUE
alpha2.e | 2025-01-27 | 2025-02-01 | 20 | 6 | 5 | 4 | 4 | 4.25 | TRUE | TRUE | TRUE
alpha2.m | 2025-02-02 | 2025-03-19 | 325 | 46 | 33 | 9.8485 | 9.75 | 10 | TRUE | TRUE | TRUE
alpha2.f | 2025-03-20 | 2025-04-01 | 30 | 13 | 9 | 3.3333 | 3.25 | 3.5 | TRUE | TRUE | TRUE
beta2.e | 2025-01-05 | 2025-01-15 | 50 | 11 | 8 | 6.25 | 6.25 | 6.5 | TRUE | TRUE | TRUE
beta2.m | 2025-01-16 | 2025-07-15 | 750 | 181 | 128 | 5.8594 | 5.75 | 6 | TRUE | TRUE | TRUE
beta2.f | 2025-07-16 | 2025-08-04 | 50 | 20 | 14 | 3.5714 | 3.5 | 3.75 | TRUE | TRUE | TRUE
delta2.m | 2025-01-01 | 2025-06-20 | 290 | 171 | 121 | 2.3967 | 2.25 | 2.5 | TRUE | TRUE | TRUE
delta2.f | 2025-06-21 | 2025-07-01 | 30 | 11 | 7 | 4.2857 | 4.25 | 4.5 | TRUE | TRUE | TRUE
echo2.m | 2025-01-01 | 2025-01-21 | 180 | 21 | 14 | 12.8571 | 12.75 | 13 | TRUE | TRUE | TRUE
echo2.f | 2025-01-22 | 2025-03-10 | 10 | 48 | 34 | 0.29412 | 0.25 | 0.5 | TRUE | TRUE | TRUE
foxtrot2.m | 2025-01-01 | 2025-03-22 | 90 | 81 | 57 | 1.5789 | 1.5 | 1.75 | TRUE | TRUE | TRUE
foxtrot2.f | 2025-03-23 | 2025-04-01 | 8 | 10 | 7 | 1.1429 | 1 | 1.25 | TRUE | TRUE | TRUE
gamma2.m | 2025-01-01 | 2025-01-21 | 150 | 21 | 14 | 10.7143 | 10.5 | 10.75 | TRUE | TRUE | TRUE
gamma2.f | 2025-01-22 | 2025-02-03 | 20 | 13 | 9 | 2.2222 | 2 | 2.25 | TRUE | TRUE | TRUE
golf2.m | 2025-01-01 | 2025-03-22 | 400 | 81 | 57 | 7.0175 | 7 | 7.25 | TRUE | TRUE | TRUE
golf2.f | 2025-03-23 | 2025-03-31 | 30 | 9 | 6 | 5 | 5 | 5.25 | TRUE | TRUE | TRUE
hotel2.m | 2025-01-01 | 2025-02-15 | 165 | 46 | 32 | 5.1562 | 5 | 5.25 | TRUE | TRUE | TRUE
hotel2.f | 2025-02-16 | 2025-02-25 | 5 | 10 | 7 | 0.71429 | 0.5 | 0.75 | TRUE | TRUE | TRUE
india2.m | 2025-01-01 | 2025-03-17 | 370 | 76 | 53 | 6.9811 | 6.75 | 7 | TRUE | TRUE | TRUE
india2.f | 2025-03-18 | 2025-03-25 | 20 | 8 | 6 | 3.3333 | 3.25 | 3.5 | TRUE | TRUE | TRUE
juliet2.m | 2025-01-01 | 2025-03-22 | 500 | 81 | 57 | 8.7719 | 8.75 | 9 | TRUE | TRUE | TRUE
juliet2.f | 2025-03-23 | 2025-04-01 | 25 | 10 | 7 | 3.5714 | 3.5 | 3.75 | TRUE | TRUE | TRUE
kilo2.m | 2025-01-01 | 2025-02-25 | 300 | 56 | 39 | 7.6923 | 7.5 | 7.75 | TRUE | TRUE | TRUE
kilo2.f | 2025-02-26 | 2025-03-03 | 30 | 6 | 4 | 7.5 | 7.5 | 7.75 | TRUE | TRUE | TRUE
lima2.m | 2025-01-01 | 2025-02-25 | 250 | 56 | 39 | 6.4103 | 6.25 | 6.5 | TRUE | TRUE | TRUE
lima2.f | 2025-02-26 | 2025-03-03 | 20 | 6 | 4 | 5 | 5 | 5.25 | TRUE | TRUE | TRUE
mike2.e | 2025-01-10 | 2025-01-25 | 20 | 16 | 11 | 1.8182 | 1.75 | 2 | TRUE | TRUE | TRUE
mike2.m | 2025-01-26 | 2025-05-16 | 720 | 111 | 79 | 9.1139 | 9 | 9.25 | TRUE | TRUE | TRUE
mike2.f | 2025-05-17 | 2025-06-01 | 50 | 16 | 10 | 5 | 5 | 5.25 | TRUE | TRUE | TRUE
november2.m | 2025-01-01 | 2025-03-27 | 600 | 86 | 61 | 9.8361 | 9.75 | 10 | TRUE | TRUE | TRUE
november2.f | 2025-03-28 | 2025-04-07 | 40 | 11 | 7 | 5.7143 | 5.5 | 5.75 | TRUE | TRUE | TRUE
oscar2.m | 2025-01-01 | 2025-06-20 | 560 | 171 | 121 | 4.6281 | 4.5 | 4.75 | TRUE | TRUE | TRUE
oscar2.f | 2025-06-21 | 2025-06-30 | 50 | 10 | 6 | 8.3333 | 8.25 | 8.5 | TRUE | TRUE | TRUE
papa2.m | 2025-01-01 | 2025-06-20 | 800 | 171 | 121 | 6.6116 | 6.5 | 6.75 | TRUE | TRUE | TRUE
papa2.f | 2025-06-21 | 2025-06-30 | 50 | 10 | 6 | 8.3333 | 8.25 | 8.5 | TRUE | TRUE | TRUE
quebec2.e | 2025-06-01 | 2025-06-26 | 75 | 26 | 19 | 3.9474 | 3.75 | 4 | TRUE | TRUE | TRUE
quebec2.m | 2025-06-27 | 2026-11-09 | 900 | 501 | 357 | 2.521 | 2.5 | 2.75 | TRUE | TRUE | TRUE
quebec2.f | 2026-11-10 | 2027-01-04 | 30 | 56 | 40 | 0.75 | 0.75 | 1 | TRUE | TRUE | TRUE
romeo2.m | 2025-01-01 | 2025-05-21 | 300 | 141 | 99 | 3.0303 | 3 | 3.25 | TRUE | TRUE | TRUE
romeo2.f | 2025-05-22 | 2025-06-02 | 25 | 12 | 8 | 3.125 | 3 | 3.25 | TRUE | TRUE | TRUE
sierra2.m | 2025-01-01 | 2025-03-02 | 330 | 61 | 42 | 7.8571 | 7.75 | 8 | TRUE | TRUE | TRUE
sierra2.f | 2025-03-03 | 2025-03-10 | 30 | 8 | 6 | 5 | 5 | 5.25 | TRUE | TRUE | TRUE
tango2.e | 2025-03-17 | 2025-03-31 | 60 | 15 | 11 | 5.4545 | 5.25 | 5.5 | TRUE | TRUE | TRUE
tango2.m | 2025-04-01 | 2025-09-15 | 1200 | 168 | 119 | 10.084 | 10 | 10.25 | TRUE | TRUE | TRUE
tango2.f | 2025-09-16 | 2025-10-01 | 80 | 16 | 12 | 6.6667 | 6.5 | 6.75 | TRUE | TRUE | TRUE
uniform2.e | 2025-05-01 | 2025-05-16 | 60 | 16 | 11 | 5.4545 | 5.25 | 5.5 | TRUE | TRUE | TRUE
uniform2.m | 2025-05-17 | 2026-02-11 | 1450 | 271 | 193 | 7.513 | 7.5 | 7.75 | TRUE | TRUE | TRUE
uniform2.f | 2026-02-12 | 2026-03-02 | 120 | 19 | 13 | 9.2308 | 9 | 9.25 | TRUE | TRUE | TRUE
victor2.e | 2025-02-15 | 2025-03-02 | 30 | 16 | 10 | 3 | 3 | 3.25 | TRUE | TRUE | TRUE
victor2.m | 2025-03-03 | 2025-08-20 | 875 | 171 | 122 | 7.1721 | 7 | 7.25 | TRUE | TRUE | TRUE
victor2.f | 2025-08-21 | 2025-09-01 | 40 | 12 | 8 | 5 | 5 | 5.25 | TRUE | TRUE | TRUE
whisky2.e | 2025-06-25 | 2025-07-10 | 50 | 16 | 12 | 4.1667 | 4 | 4.25 | TRUE | TRUE | TRUE
whisky2.m | 2025-07-11 | 2026-04-07 | 1500 | 271 | 193 | 7.772 | 7.75 | 8 | TRUE | TRUE | TRUE
whisky2.f | 2026-04-08 | 2026-04-30 | 120 | 23 | 17 | 7.0588 | 7 | 7.25 | TRUE | TRUE | TRUE
xray2.e | 2025-07-15 | 2025-08-09 | 50 | 26 | 19 | 2.6316 | 2.5 | 2.75 | TRUE | TRUE | TRUE
xray2.m | 2025-08-10 | 2026-01-07 | 960 | 151 | 108 | 8.8889 | 8.75 | 9 | TRUE | TRUE | TRUE
xray2.f | 2026-01-08 | 2026-02-01 | 50 | 25 | 17 | 2.9412 | 2.75 | 3 | TRUE | TRUE | TRUE
zulu2.e | 2025-06-15 | 2025-07-15 | 20 | 31 | 22 | 0.90909 | 0.75 | 1 | TRUE | TRUE | TRUE
zulu2.m | 2025-07-16 | 2025-11-23 | 750 | 131 | 93 | 8.0645 | 8 | 8.25 | TRUE | TRUE | TRUE
zulu2.f | 2025-11-24 | 2025-12-01 | 40 | 8 | 6 | 6.6667 | 6.5 | 6.75 | TRUE | TRUE | TRUE
Note on J1: Is task assign to an Expert?
Note on K1: Should task be included?
Note on L1: Are date OK?

## assign
Expert | Task | TRUE | TRUE
DEV.Adam | alpha2.e | 1 | 1
DEV.Adam | alpha2.f | 1 | 1
DEV.Adam | alpha2.m | 1 | 1
DEV.Adam | juliet2.m | 1 | 1
DEV.Adam | kilo2.m | 1 | 1
DEV.Adam | lima2.m | 1 | 1
DEV.Adam | november2.m | 1 | 1
DEV.Adam | quebec2.m | 1 | 1
DEV.Adam | uniform2.e | 1 | 1
DEV.Adam | uniform2.f | 1 | 1
DEV.Adam | uniform2.m | 1 | 1
DEV.Andrew | juliet2.f | 1 | 1
DEV.Andrew | juliet2.m | 1 | 1
DEV.Andrew | kilo2.f | 1 | 1
DEV.Andrew | kilo2.m | 1 | 1
DEV.Andrew | lima2.f | 1 | 1
DEV.Andrew | lima2.m | 1 | 1
DEV.Andrew | victor2.m | 1 | 1
DEV.Andrew | xray2.e | 1 | 1
DEV.Andrew | xray2.f | 1 | 1
DEV.Andrew | xray2.m | 1 | 1
DEV.Anna | delta2.f | 1 | 1
DEV.Anna | delta2.m | 1 | 1
DEV.Anna | echo2.f | 1 | 1
DEV.Anna | echo2.m | 1 | 1
DEV.Anna | uniform2.e | 1 | 1
DEV.Anna | uniform2.f | 1 | 1
DEV.Anna | uniform2.m | 1 | 1
DEV.Ava | hotel2.f | 1 | 1
DEV.Ava | hotel2.m | 1 | 1
DEV.Ava | india2.f | 1 | 1
DEV.Ava | india2.m | 1 | 1
DEV.Ava | juliet2.m | 1 | 1
DEV.Ava | kilo2.m | 1 | 1
DEV.Ava | lima2.m | 1 | 1
DEV.Ava | november2.m | 1 | 1
DEV.Ava | tango2.e | 1 | 1
DEV.Ava | tango2.f | 1 | 1
DEV.Ava | zulu2.e | 1 | 1
DEV.Ava | zulu2.f | 1 | 1
DEV.Ava | zulu2.m | 1 | 1
DEV.Carl | charlie.f | 1 | 1
DEV.Carl | charlie.m | 1 | 1
DEV.Carl | juliet.e | 1 | 1
DEV.Carl | juliet.f | 1 | 1
DEV.Carl | juliet.m | 1 | 1
DEV.Carl | mike2.m | 1 | 1
DEV.Carl | november.e | 1 | 1
DEV.Carl | november.f | 1 | 1
DEV.Carl | november.m | 1 | 1
DEV.Charles | charlie.f | 1 | 1
DEV.Charles | charlie.m | 1 | 1
DEV.Charles | gamma2.m | 1 | 1
DEV.Charles | india.f | 1 | 1
DEV.Charles | india.m | 1 | 1
DEV.Charles | uniform2.m | 1 | 1
DEV.Dorothy | gamma2.m | 1 | 1
DEV.Dorothy | golf2.m | 1 | 1
DEV.Dorothy | india2.m | 1 | 1
DEV.Dorothy | mike2.e | 1 | 1
DEV.Dorothy | mike2.f | 1 | 1
DEV.Dorothy | mike2.m | 1 | 1
DEV.Dorothy | whisky2.e | 1 | 1
DEV.Dorothy | whisky2.f | 1 | 1
DEV.Edward | beta2.e | 1 | 1
DEV.Edward | beta2.f | 1 | 1
DEV.Edward | beta2.m | 1 | 1
DEV.Edward | gamma2.f | 1 | 1
DEV.Edward | gamma2.m | 1 | 1
DEV.Edward | uniform2.m | 1 | 1
DEV.Eric | alpha2.m | 1 | 1
DEV.Eric | echo2.m | 1 | 1
DEV.Eric | india2.m | 1 | 1
DEV.Eric | tango2.e | 1 | 1
DEV.Eric | tango2.m | 1 | 1
DEV.Frances | beta.f | 1 | 1
DEV.Frances | beta.m | 1 | 1
DEV.Frances | lima.f | 1 | 1
DEV.Frances | lima.m | 1 | 1
DEV.Frances | xray2.m | 1 | 1
DEV.Francis | charlie.f | 1 | 1
DEV.Francis | charlie.m | 1 | 1
DEV.Francis | hotel.f | 1 | 1
DEV.Francis | hotel.m | 1 | 1
DEV.Francis | kilo.f | 1 | 1
DEV.Francis | kilo.m | 1 | 1
DEV.Fred | juliet2.m | 1 | 1
DEV.Fred | kilo2.m | 1 | 1
DEV.Fred | lima2.m | 1 | 1
DEV.Fred | november2.m | 1 | 1
DEV.Fred | tango2.m | 1 | 1
DEV.Fred | whisky2.m | 1 | 1
DEV.Hugo | alpha.f | 1 | 1
DEV.Hugo | alpha.m | 1 | 1
DEV.Hugo | golf.f | 1 | 1
DEV.Hugo | golf.m | 1 | 1
DEV.Hugo | juliet.f | 1 | 1
DEV.Hugo | juliet.m | 1 | 1
DEV.Hugo | november.f | 1 | 1
DEV.Hugo | november.m | 1 | 1
DEV.Jacob | foxtrot2.f | 1 | 1
DEV.Jacob | foxtrot2.m | 1 | 1
DEV.Jacob | golf2.f | 1 | 1
DEV.Jacob | golf2.m | 1 | 1
DEV.Jacob | tango2.m | 1 | 1
DEV.Jacob | whisky2.m | 1 | 1
DEV.Lars | delta.f | 1 | 1
DEV.Lars | delta.m | 1 | 1
DEV.Lars | india.f | 1 | 1
DEV.Lars | india.m | 1 | 1
DEV.Lars | mike2.m | 1 | 1
DEV.Lars | tango2.m | 1 | 1
DEV.Lars | whisky2.m | 1 | 1
DEV.Lennart | romeo2.f | 1 | 1
DEV.Lennart | romeo2.m | 1 | 1
DEV.Lennart | sierra2.f | 1 | 1
DEV.Lennart | sierra2.m | 1 | 1
DEV.Lennart | tango2.m | 1 | 1
DEV.Lennart | uniform2.f | 1 | 1
DEV.Lennart | uniform2.m | 1 | 1
DEV.Martin | echo.f | 1 | 1
DEV.Martin | echo.m | 1 | 1
DEV.Martin | hotel.f | 1 | 1
DEV.Martin | hotel.m | 1 | 1
DEV.Martin | kilo.e | 1 | 1
DEV.Martin | kilo.f | 1 | 1
DEV.Martin | kilo.m | 1 | 1
DEV.Martin | mike.e | 1 | 1
DEV.Martin | mike.f | 1 | 1
DEV.Martin | mike.m | 1 | 1
DEV.Max | juliet2.f | 1 | 1
DEV.Max | juliet2.m | 1 | 1
DEV.Max | kilo2.f | 1 | 1
DEV.Max | kilo2.m | 1 | 1
DEV.Max | lima2.f | 1 | 1
DEV.Max | lima2.m | 1 | 1
DEV.Max | mike2.f | 1 | 1
DEV.Max | mike2.m | 1 | 1
DEV.Max | november2.f | 1 | 1
DEV.Max | november2.m | 1 | 1
DEV.Max | quebec2.f | 1 | 1
DEV.Max | quebec2.m | 1 | 1
DEV.Michael | alpha.f | 1 | 1
DEV.Michael | alpha.m | 1 | 1
DEV.Michael | foxtrot.f | 1 | 1
DEV.Michael | foxtrot.m | 1 | 1
DEV.Michael | hotel.f | 1 | 1
DEV.Michael | hotel.m | 1 | 1
DEV.Michael | lima.f | 1 | 1
DEV.Michael | lima.m | 1 | 1
DEV.Michael | mike.f | 1 | 1
DEV.Michael | mike.m | 1 | 1
DEV.Michael | tango2.m | 1 | 1
DEV.Molly | hotel2.m | 1 | 1
DEV.Molly | victor2.e | 1 | 1
DEV.Molly | victor2.f | 1 | 1
DEV.Molly | victor2.m | 1 | 1
DEV.Molly | whisky2.m | 1 | 1
DEV.Paul | alpha.f | 1 | 1
DEV.Paul | alpha.m | 1 | 1
DEV.Paul | charlie.f | 1 | 1
DEV.Paul | charlie.m | 1 | 1
DEV.Paul | india.f | 1 | 1
DEV.Paul | india.m | 1 | 1
DEV.Paul | lima.e | 1 | 1
DEV.Paul | lima.f | 1 | 1
DEV.Paul | lima.m | 1 | 1
DEV.Paul | tango2.m | 1 | 1
DEV.Sabina | romeo2.m | 1 | 1
DEV.Sabina | sierra2.m | 1 | 1
DEV.Sabina | tango2.e | 1 | 1
DEV.Sabina | tango2.f | 1 | 1
DEV.Sabina | victor2.m | 1 | 1
DEV.Sabina | xray2.m | 1 | 1
DEV.Stefan | oscar2.f | 1 | 1
DEV.Stefan | oscar2.m | 1 | 1
DEV.Stefan | papa2.f | 1 | 1
DEV.Stefan | papa2.m | 1 | 1
DEV.Stefan | quebec2.m | 1 | 1
DEV.Stefan | whisky2.f | 1 | 1
DEV.Stefan | zulu2.m | 1 | 1
DEV.Tom | beta.f | 1 | 1
DEV.Tom | beta.m | 1 | 1
DEV.Tom | india.f | 1 | 1
DEV.Tom | india.m | 1 | 1
DEV.Tom | oscar.f | 1 | 1
DEV.Tom | oscar.m | 1 | 1
DEV.Uma | november2.f | 1 | 1
DEV.Uma | november2.m | 1 | 1
DEV.Uma | quebec2.e | 1 | 1
DEV.Uma | quebec2.f | 1 | 1
DEV.Uma | quebec2.m | 1 | 1
DEV.Uma | zulu2.m | 1 | 1
PM.Angel | charlie.pf | 1 | 1
PM.Angel | charlie.pm | 1 | 1
PM.Angel | delta.pf | 1 | 1
PM.Angel | delta.pm | 1 | 1
PM.Angel | juliet.pe | 1 | 1
PM.Angel | juliet.pf | 1 | 1
PM.Angel | juliet.pm | 1 | 1
PM.Angel | mike.pe | 1 | 1
PM.Angel | mike.pf | 1 | 1
PM.Angel | mike.pm | 1 | 1
PM.Angel | november.pe | 1 | 1
PM.Angel | november.pf | 1 | 1
PM.Angel | november.pm | 1 | 1
PM.Angel | oscar2.pf | 1 | 1
PM.Angel | oscar2.pm | 1 | 1
PM.Angel | papa2.pf | 1 | 1
PM.Angel | papa2.pm | 1 | 1
PM.Angel | quebec2.pe | 1 | 1
PM.Angel | quebec2.pf | 1 | 1
PM.Angel | quebec2.pm | 1 | 1
PM.Angel | sierra2.pf | 1 | 1
PM.Angel | sierra2.pm | 1 | 1
PM.Angel | xray2.pe | 1 | 1
PM.Angel | xray2.pf | 1 | 1
PM.Angel | xray2.pm | 1 | 1
PM.Anthony | delta2.pf | 1 | 1
PM.Anthony | delta2.pm | 1 | 1
PM.Anthony | echo2.pf | 1 | 1
PM.Anthony | echo2.pm | 1 | 1
PM.Anthony | foxtrot2.pf | 1 | 1
PM.Anthony | foxtrot2.pm | 1 | 1
PM.Anthony | gamma2.pf | 1 | 1
PM.Anthony | gamma2.pm | 1 | 1
PM.Anthony | golf2.pf | 1 | 1
PM.Anthony | golf2.pm | 1 | 1
PM.Anthony | hotel2.pf | 1 | 1
PM.Anthony | hotel2.pm | 1 | 1
PM.Anthony | tango2.pe | 1 | 1
PM.Anthony | tango2.pf | 1 | 1
PM.Anthony | tango2.pm | 1 | 1
PM.Anthony | uniform2.pe | 1 | 1
PM.Anthony | uniform2.pf | 1 | 1
PM.Anthony | uniform2.pm | 1 | 1
PM.Daniel | alpha.pf | 1 | 1
PM.Daniel | alpha.pm | 1 | 1
PM.Daniel | beta.pf | 1 | 1
PM.Daniel | beta.pm | 1 | 1
PM.Daniel | india.pf | 1 | 1
PM.Daniel | india.pm | 1 | 1
PM.Daniel | lima2.pf | 1 | 1
PM.Daniel | lima2.pm | 1 | 1
PM.Daniel | mike2.pe | 1 | 1
PM.Daniel | mike2.pf | 1 | 1
PM.Daniel | mike2.pm | 1 | 1
PM.Daniel | oscar.pe | 1 | 1
PM.Daniel | oscar.pf | 1 | 1
PM.Daniel | oscar.pm | 1 | 1
PM.Daniel | whisky2.pe | 1 | 1
PM.Daniel | whisky2.pf | 1 | 1
PM.Daniel | whisky2.pm | 1 | 1
PM.Fabian | india2.pf | 1 | 1
PM.Fabian | india2.pm | 1 | 1
PM.Fabian | kilo2.pf | 1 | 1
PM.Fabian | kilo2.pm | 1 | 1
PM.Fabian | november2.pf | 1 | 1
PM.Fabian | november2.pm | 1 | 1
PM.Fabian | romeo2.pf | 1 | 1
PM.Fabian | romeo2.pm | 1 | 1
PM.Fabian | victor2.pe | 1 | 1
PM.Fabian | victor2.pf | 1 | 1
PM.Fabian | victor2.pm | 1 | 1
PM.Henry | alpha2.pe | 1 | 1
PM.Henry | alpha2.pf | 1 | 1
PM.Henry | alpha2.pm | 1 | 1
PM.Henry | beta2.pe | 1 | 1
PM.Henry | beta2.pf | 1 | 1
PM.Henry | beta2.pm | 1 | 1
PM.Henry | juliet2.pf | 1 | 1
PM.Henry | juliet2.pm | 1 | 1
PM.Lisa | echo.pf | 1 | 1
PM.Lisa | echo.pm | 1 | 1
PM.Lisa | foxtrot.pf | 1 | 1
PM.Lisa | foxtrot.pm | 1 | 1
PM.Lisa | golf.pf | 1 | 1
PM.Lisa | golf.pm | 1 | 1
PM.Lisa | hotel.pf | 1 | 1
PM.Lisa | hotel.pm | 1 | 1
PM.Lisa | kilo.pe | 1 | 1
PM.Lisa | kilo.pf | 1 | 1
PM.Lisa | kilo.pm | 1 | 1
PM.Lisa | lima.pe | 1 | 1
PM.Lisa | lima.pf | 1 | 1
PM.Lisa | lima.pm | 1 | 1
PM.Lisa | zulu2.pe | 1 | 1
PM.Lisa | zulu2.pf | 1 | 1
PM.Lisa | zulu2.pm | 1 | 1
SA.Adrian | alpha.sf | 1 | 1
SA.Adrian | alpha.sm | 1 | 1
SA.Adrian | beta.sf | 1 | 1
SA.Adrian | beta.sm | 1 | 1
SA.Adrian | charlie.sf | 1 | 1
SA.Adrian | charlie.sm | 1 | 1
SA.Adrian | delta.sf | 1 | 1
SA.Adrian | delta.sm | 1 | 1
SA.Adrian | echo.sf | 1 | 1
SA.Adrian | echo.sm | 1 | 1
SA.Adrian | golf.f | 1 | 1
SA.Adrian | golf.m | 1 | 1
SA.Adrian | golf.sf | 1 | 1
SA.Adrian | golf.sm | 1 | 1
SA.Adrian | kilo.se | 1 | 1
SA.Adrian | kilo.sf | 1 | 1
SA.Adrian | kilo.sm | 1 | 1
SA.Adrian | lima.f | 1 | 1
SA.Adrian | lima.m | 1 | 1
SA.Adrian | lima.se | 1 | 1
SA.Adrian | lima.sf | 1 | 1
SA.Adrian | lima.sm | 1 | 1
SA.Adrian | mike.se | 1 | 1
SA.Adrian | mike.sf | 1 | 1
SA.Adrian | mike.sm | 1 | 1
SA.Albert | oscar2.f | 1 | 1
SA.Albert | oscar2.m | 1 | 1
SA.Albert | papa2.f | 1 | 1
SA.Albert | papa2.m | 1 | 1
SA.Albert | quebec2.m | 1 | 1
SA.Albert | romeo2.m | 1 | 1
SA.Albert | sierra2.m | 1 | 1
SA.Albert | tango2.m | 1 | 1
SA.Justin | india2.sf | 1 | 1
SA.Justin | india2.sm | 1 | 1
SA.Justin | juliet2.sf | 1 | 1
SA.Justin | juliet2.sm | 1 | 1
SA.Justin | lima2.sf | 1 | 1
SA.Justin | lima2.sm | 1 | 1
SA.Justin | oscar2.m | 1 | 1
SA.Justin | papa2.f | 1 | 1
SA.Justin | papa2.m | 1 | 1
SA.Kate | oscar2.m | 1 | 1
SA.Kate | papa2.f | 1 | 1
SA.Kate | papa2.m | 1 | 1
SA.Kate | quebec2.m | 1 | 1
SA.Kate | sierra2.m | 1 | 1
SA.Kate | tango2.m | 1 | 1
SA.Kevin | alpha2.se | 1 | 1
SA.Kevin | alpha2.sf | 1 | 1
SA.Kevin | alpha2.sm | 1 | 1
SA.Kevin | beta2.m | 1 | 1
SA.Kevin | beta2.se | 1 | 1
SA.Kevin | beta2.sf | 1 | 1
SA.Kevin | beta2.sm | 1 | 1
SA.Kevin | gamma2.sf | 1 | 1
SA.Kevin | gamma2.sm | 1 | 1
SA.Kevin | india2.m | 1 | 1
SA.Kevin | quebec2.se | 1 | 1
SA.Kevin | quebec2.sf | 1 | 1
SA.Kevin | quebec2.sm | 1 | 1
SA.Kevin | uniform2.se | 1 | 1
SA.Kevin | uniform2.sf | 1 | 1
SA.Kevin | uniform2.sm | 1 | 1
SA.Kevin | victor2.m | 1 | 1
SA.Kevin | xray2.se | 1 | 1
SA.Kevin | xray2.sf | 1 | 1
SA.Kevin | xray2.sm | 1 | 1
SA.Martha | juliet2.m | 1 | 1
SA.Martha | kilo2.m | 1 | 1
SA.Martha | kilo2.sf | 1 | 1
SA.Martha | kilo2.sm | 1 | 1
SA.Martha | lima2.m | 1 | 1
SA.Martha | mike2.m | 1 | 1
SA.Martha | november2.m | 1 | 1
SA.Martha | november2.sf | 1 | 1
SA.Martha | november2.sm | 1 | 1
SA.Martha | oscar2.sf | 1 | 1
SA.Martha | oscar2.sm | 1 | 1
SA.Martha | papa2.sf | 1 | 1
SA.Martha | papa2.sm | 1 | 1
SA.Martha | zulu2.se | 1 | 1
SA.Martha | zulu2.sf | 1 | 1
SA.Martha | zulu2.sm | 1 | 1
SA.Melanie | delta2.sf | 1 | 1
SA.Melanie | delta2.sm | 1 | 1
SA.Melanie | echo2.sf | 1 | 1
SA.Melanie | echo2.sm | 1 | 1
SA.Melanie | foxtrot2.sf | 1 | 1
SA.Melanie | foxtrot2.sm | 1 | 1
SA.Melanie | hotel2.sf | 1 | 1
SA.Melanie | hotel2.sm | 1 | 1
SA.Melanie | juliet2.m | 1 | 1
SA.Melanie | kilo2.m | 1 | 1
SA.Melanie | lima2.m | 1 | 1
SA.Melanie | mike2.m | 1 | 1
SA.Melanie | mike2.se | 1 | 1
SA.Melanie | mike2.sf | 1 | 1
SA.Melanie | mike2.sm | 1 | 1
SA.Melanie | november2.m | 1 | 1
SA.Melanie | uniform2.m | 1 | 1
SA.Peter | beta2.m | 1 | 1
SA.Peter | gamma2.m | 1 | 1
SA.Peter | golf2.sf | 1 | 1
SA.Peter | golf2.sm | 1 | 1
SA.Peter | tango2.se | 1 | 1
SA.Peter | tango2.sf | 1 | 1
SA.Peter | tango2.sm | 1 | 1
SA.Peter | victor2.se | 1 | 1
SA.Peter | victor2.sf | 1 | 1
SA.Peter | victor2.sm | 1 | 1
SA.Robert | beta.f | 1 | 1
SA.Robert | beta.m | 1 | 1
SA.Robert | foxtrot.sf | 1 | 1
SA.Robert | foxtrot.sm | 1 | 1
SA.Robert | hotel.sf | 1 | 1
SA.Robert | hotel.sm | 1 | 1
SA.Robert | india.f | 1 | 1
SA.Robert | india.m | 1 | 1
SA.Robert | india.sf | 1 | 1
SA.Robert | india.sm | 1 | 1
SA.Robert | juliet.se | 1 | 1
SA.Robert | juliet.sf | 1 | 1
SA.Robert | juliet.sm | 1 | 1
SA.Robert | november.se | 1 | 1
SA.Robert | november.sf | 1 | 1
SA.Robert | november.sm | 1 | 1
SA.Robert | oscar.e | 1 | 1
SA.Robert | oscar.f | 1 | 1
SA.Robert | oscar.m | 1 | 1
SA.Robert | oscar.se | 1 | 1
SA.Robert | oscar.sf | 1 | 1
SA.Robert | oscar.sm | 1 | 1
Note on C1: Valid expert?
Note on D1: Valid task?

## xbday
Expert | Task | Start | End | Lower | Upper | TRUE | TRUE | TRUE
PM.Angel | charlie.pf | 2025-06-06 | 2025-07-06 | 0.25 | 0.5 | TRUE | TRUE | TRUE
PM.Angel | charlie.pm | 2025-01-01 | 2025-06-05 | 0.5 | 0.75 | TRUE | TRUE | 1
PM.Angel | delta.pf | 2025-02-26 | 2025-04-12 | 0 | 0.25 | TRUE | TRUE | 1
PM.Angel | delta.pm | 2025-01-01 | 2025-02-25 | 0.5 | 0.75 | TRUE | TRUE | 1
PM.Angel | juliet.pe | 2025-02-10 | 2025-02-27 | 0.5 | 0.75 | TRUE | TRUE | 1
PM.Angel | juliet.pf | 2025-07-01 | 2025-08-15 | 0 | 0.25 | TRUE | TRUE | 1
PM.Angel | juliet.pm | 2025-02-28 | 2025-06-30 | 0.5 | 0.75 | TRUE | TRUE | 1
PM.Angel | mike.pe | 2025-04-10 | 2025-04-20 | 1.25 | 1.5 | TRUE | TRUE | 1
PM.Angel | mike.pf | 2025-09-26 | 2025-10-30 | 0 | 0.25 | TRUE | TRUE | 1
PM.Angel | mike.pm | 2025-04-21 | 2025-09-25 | 0.25 | 0.5 | TRUE | TRUE | 1
PM.Angel | november.pe | 2025-05-26 | 2025-06-14 | 0.5 | 0.75 | TRUE | TRUE | 1
PM.Angel | november.pf | 2025-12-31 | 2026-01-31 | 0 | 0.25 | TRUE | TRUE | 1
PM.Angel | november.pm | 2025-06-15 | 2025-12-30 | 0 | 0.5 | TRUE | TRUE | 1
PM.Angel | oscar2.pf | 2025-06-21 | 2025-06-30 | 3.25 | 3.5 | TRUE | TRUE | 1
PM.Angel | oscar2.pm | 2025-01-01 | 2025-06-20 | 0.25 | 0.5 | TRUE | TRUE | 1
PM.Angel | papa2.pf | 2025-06-21 | 2025-06-30 | 3.25 | 3.5 | TRUE | TRUE | 1
PM.Angel | papa2.pm | 2025-01-01 | 2025-06-20 | 0.75 | 1 | TRUE | TRUE | 1
PM.Angel | quebec2.pe | 2025-06-01 | 2025-06-26 | 0 | 1.75 | TRUE | TRUE | 1
PM.Angel | quebec2.pf | 2026-11-10 | 2027-01-04 | 0.5 | 0.75 | TRUE | TRUE | 1
PM.Angel | quebec2.pm | 2025-06-27 | 2026-11-09 | 0.25 | 0.5 | TRUE | TRUE | 1
PM.Angel | sierra2.pf | 2025-03-03 | 2025-03-10 | 1.5 | 1.75 | TRUE | TRUE | 1
PM.Angel | sierra2.pm | 2025-01-01 | 2025-03-02 | 0.75 | 1 | TRUE | TRUE | 1
PM.Angel | xray2.pe | 2025-07-15 | 2025-08-09 | 1.25 | 1.5 | TRUE | TRUE | 1
PM.Angel | xray2.pm | 2025-08-10 | 2026-01-07 | 1 | 1.25 | TRUE | TRUE | 1
PM.Angel | xray2.pf | 2026-01-08 | 2026-02-01 | 0.5 | 0.75 | TRUE | TRUE | 1
PM.Daniel | alpha.pm | 2025-01-01 | 2025-04-01 | 0.5 | 0.75 | TRUE | TRUE | 1
PM.Daniel | alpha.pf | 2025-04-02 | 2025-05-02 | 0 | 0.25 | TRUE | TRUE | 1
PM.Daniel | beta.pm | 2025-01-01 | 2025-06-20 | 0.5 | 0.75 | TRUE | TRUE | 1
PM.Daniel | beta.pf | 2025-06-21 | 2025-08-05 | 0 | 0.25 | TRUE | TRUE | 1
PM.Daniel | india.pm | 2025-01-01 | 2025-10-01 | 0.5 | 0.75 | TRUE | TRUE | 1
PM.Daniel | india.pf | 2025-10-02 | 2025-11-01 | 1 | 1.25 | TRUE | TRUE | 1
PM.Daniel | oscar.pe | 2025-06-25 | 2025-07-09 | 1.25 | 1.5 | TRUE | TRUE | 1
PM.Daniel | oscar.pm | 2025-07-10 | 2025-12-30 | 0.5 | 0.75 | TRUE | TRUE | 1
PM.Daniel | oscar.pf | 2025-12-31 | 2026-01-31 | 0.25 | 0.5 | TRUE | TRUE | 1
PM.Daniel | lima2.pm | 2025-01-01 | 2025-02-25 | 0.5 | 0.75 | TRUE | TRUE | 1
PM.Daniel | lima2.pf | 2025-02-26 | 2025-03-03 | 3.75 | 4 | TRUE | TRUE | 1
PM.Daniel | mike2.pe | 2025-01-10 | 2025-01-15 | 5 | 5.25 | TRUE | TRUE | 1
PM.Daniel | mike2.pm | 2025-01-16 | 2025-05-16 | 0.75 | 1 | TRUE | TRUE | 1
PM.Daniel | mike2.pf | 2025-05-17 | 2025-06-01 | 2 | 2.25 | TRUE | TRUE | 1
PM.Daniel | whisky2.pe | 2025-06-25 | 2025-07-10 | 5 | 5.25 | TRUE | TRUE | 1
PM.Daniel | whisky2.pm | 2025-07-11 | 2026-04-07 | 1 | 1.25 | TRUE | TRUE | 1
PM.Daniel | whisky2.pf | 2026-04-08 | 2026-04-30 | 1 | 1.25 | TRUE | TRUE | 1
PM.Lisa | echo.pm | 2025-01-01 | 2025-03-15 | 0.25 | 0.5 | TRUE | TRUE | 1
PM.Lisa | echo.pf | 2025-04-02 | 2025-05-17 | 0 | 0.25 | TRUE | TRUE | 1
PM.Lisa | foxtrot.pm | 2025-01-01 | 2025-04-01 | 0.25 | 0.5 | TRUE | TRUE | 1
PM.Lisa | foxtrot.pf | 2025-04-02 | 2025-05-02 | 0 | 0.25 | TRUE | TRUE | 1
PM.Lisa | golf.pm | 2025-01-01 | 2025-05-12 | 0.25 | 0.5 | TRUE | TRUE | 1
PM.Lisa | golf.pf | 2025-05-13 | 2025-06-27 | 0.25 | 0.5 | TRUE | TRUE | 1
PM.Lisa | hotel.pm | 2025-01-01 | 2025-09-01 | 0.25 | 0.5 | TRUE | TRUE | 1
PM.Lisa | hotel.pf | 2025-09-02 | 2025-10-17 | 0.25 | 0.5 | TRUE | TRUE | 1
PM.Lisa | kilo.pe | 2025-03-01 | 2025-03-24 | 1.5 | 1.75 | TRUE | TRUE | 1
PM.Lisa | kilo.pm | 2025-03-25 | 2025-08-01 | 0 | 0.25 | TRUE | TRUE | 1
PM.Lisa | kilo.pf | 2025-08-02 | 2025-09-16 | 0.5 | 0.75 | TRUE | TRUE | 1
PM.Lisa | lima.pe | 2025-03-21 | 2025-04-19 | 1 | 1.25 | TRUE | TRUE | 1
PM.Lisa | lima.pm | 2025-04-20 | 2025-11-01 | 0.5 | 0.75 | TRUE | TRUE | 1
PM.Lisa | lima.pf | 2025-11-02 | 2025-11-30 | 1 | 1.25 | TRUE | TRUE | 1
PM.Lisa | zulu2.pe | 2025-06-15 | 2025-07-15 | 2.25 | 2.5 | TRUE | TRUE | 1
PM.Lisa | zulu2.pm | 2025-07-16 | 2025-11-23 | 0.75 | 1 | TRUE | TRUE | 1
PM.Lisa | zulu2.pf | 2025-11-24 | 2025-12-01 | 3.25 | 3.5 | TRUE | TRUE | 1
PM.Henry | alpha2.pe | 2025-01-27 | 2025-02-01 | 2 | 2.25 | TRUE | TRUE | 1
PM.Henry | alpha2.pm | 2025-02-02 | 2025-03-19 | 1 | 1.25 | TRUE | TRUE | 1
PM.Henry | alpha2.pf | 2025-03-20 | 2025-04-01 | 1 | 1.25 | TRUE | TRUE | 1
PM.Henry | beta2.pe | 2025-01-05 | 2025-01-15 | 6.25 | 6.5 | TRUE | TRUE | 1
PM.Henry | beta2.pm | 2025-01-16 | 2025-07-15 | 0.5 | 0.75 | TRUE | TRUE | 1
PM.Henry | beta2.pf | 2025-07-16 | 2025-08-04 | 2.75 | 3 | TRUE | TRUE | 1
PM.Henry | juliet2.pm | 2025-01-01 | 2025-03-22 | 0.75 | 1 | TRUE | TRUE | 1
PM.Henry | juliet2.pf | 2025-03-23 | 2025-04-01 | 1.25 | 1.5 | TRUE | TRUE | 1
PM.Anthony | delta2.pm | 2025-01-01 | 2025-06-20 | 0 | 0.25 | TRUE | TRUE | 1
PM.Anthony | delta2.pf | 2025-06-21 | 2025-07-01 | 1.25 | 1.5 | TRUE | TRUE | 1
PM.Anthony | echo2.pm | 2025-01-01 | 2025-01-21 | 1.25 | 1.5 | TRUE | TRUE | 1
PM.Anthony | echo2.pf | 2025-01-22 | 2025-03-10 | 0.25 | 0.5 | TRUE | TRUE | 1
PM.Anthony | foxtrot2.pm | 2025-01-01 | 2025-03-22 | 0 | 0.25 | TRUE | TRUE | 1
PM.Anthony | foxtrot2.pf | 2025-03-23 | 2025-04-01 | 0.5 | 0.75 | TRUE | TRUE | 1
PM.Anthony | gamma2.pm | 2025-01-01 | 2025-01-21 | 1 | 1.25 | TRUE | TRUE | 1
PM.Anthony | gamma2.pf | 2025-01-22 | 2025-02-03 | 1 | 1.25 | TRUE | TRUE | 1
PM.Anthony | golf2.pm | 2025-01-01 | 2025-03-22 | 0.5 | 0.75 | TRUE | TRUE | 1
PM.Anthony | golf2.pf | 2025-03-23 | 2025-03-31 | 2.5 | 2.75 | TRUE | TRUE | 1
PM.Anthony | hotel2.pm | 2025-01-01 | 2025-02-15 | 0.25 | 0.5 | TRUE | TRUE | 1
PM.Anthony | hotel2.pf | 2025-02-16 | 2025-02-25 | 0.5 | 0.75 | TRUE | TRUE | 1
PM.Anthony | tango2.pe | 2025-02-01 | 2025-02-16 | 5 | 5.25 | TRUE | TRUE | 1
PM.Anthony | tango2.pm | 2025-02-17 | 2025-09-15 | 1 | 1.25 | TRUE | TRUE | 1
PM.Anthony | tango2.pf | 2025-09-16 | 2025-10-01 | 2.5 | 2.75 | TRUE | TRUE | 1
PM.Anthony | uniform2.pe | 2025-05-01 | 2025-05-16 | 4.5 | 4.75 | TRUE | TRUE | 1
PM.Anthony | uniform2.pm | 2025-05-17 | 2026-02-11 | 0.75 | 1 | TRUE | TRUE | 1
PM.Anthony | uniform2.pf | 2026-02-12 | 2026-03-02 | 1.5 | 1.75 | TRUE | TRUE | 1
PM.Fabian | india2.pm | 2025-01-01 | 2025-03-17 | 0.75 | 1 | TRUE | TRUE | 1
PM.Fabian | india2.pf | 2025-03-18 | 2025-03-25 | 1.5 | 1.75 | TRUE | TRUE | 1
PM.Fabian | kilo2.pm | 2025-01-01 | 2025-02-25 | 0.75 | 1 | TRUE | TRUE | 1
PM.Fabian | kilo2.pf | 2025-02-26 | 2025-03-03 | 3.75 | 4 | TRUE | TRUE | 1
PM.Fabian | november2.pm | 2025-01-01 | 2025-03-27 | 0.75 | 1 | TRUE | TRUE | 1
PM.Fabian | november2.pf | 2025-03-28 | 2025-04-07 | 2.75 | 3 | TRUE | TRUE | 1
PM.Fabian | romeo2.pm | 2025-01-01 | 2025-05-21 | 0.25 | 0.5 | TRUE | TRUE | 1
PM.Fabian | romeo2.pf | 2025-05-22 | 2025-06-02 | 1.75 | 2 | TRUE | TRUE | 1
PM.Fabian | victor2.pe | 2025-03-15 | 2025-04-09 | 3.25 | 3.5 | TRUE | TRUE | 1
PM.Fabian | victor2.pm | 2025-04-10 | 2025-08-18 | 0.75 | 1 | TRUE | TRUE | 1
PM.Fabian | victor2.pf | 2025-08-19 | 2025-09-01 | 2 | 2.25 | TRUE | TRUE | 1
SA.Peter | golf2.sm | 2025-01-01 | 2025-03-22 | 0.25 | 0.5 | TRUE | TRUE | 1
SA.Peter | golf2.sf | 2025-03-23 | 2025-03-31 | 1.5 | 1.75 | TRUE | TRUE | 1
SA.Peter | tango2.se | 2025-02-01 | 2025-02-16 | 6 | 6.25 | TRUE | TRUE | 1
SA.Peter | tango2.sm | 2025-02-17 | 2025-09-15 | 0.25 | 0.5 | TRUE | TRUE | 1
SA.Peter | tango2.sf | 2025-09-16 | 2025-10-01 | 1.5 | 1.75 | TRUE | TRUE | 1
SA.Peter | victor2.se | 2025-02-15 | 2025-03-02 | 2 | 2.25 | TRUE | TRUE | 1
SA.Peter | victor2.sm | 2025-03-03 | 2025-08-20 | 0 | 0.25 | TRUE | TRUE | 1
SA.Peter | victor2.sf | 2025-08-21 | 2025-09-01 | 1.25 | 1.5 | TRUE | TRUE | 1
SA.Adrian | alpha.sm | 2025-01-01 | 2025-04-01 | 0 | 0.25 | TRUE | TRUE | 1
SA.Adrian | alpha.sf | 2025-04-02 | 2025-05-02 | 0 | 0.25 | TRUE | TRUE | 1
SA.Adrian | beta.sm | 2025-01-01 | 2025-06-20 | 0 | 0.25 | TRUE | TRUE | 1
SA.Adrian | beta.sf | 2025-06-21 | 2025-08-05 | 0 | 0.25 | TRUE | TRUE | 1
SA.Adrian | charlie.sm | 2025-01-01 | 2025-06-05 | 0 | 0.25 | TRUE | TRUE | 1
SA.Adrian | charlie.sf | 2025-06-06 | 2025-07-06 | 0 | 0.25 | TRUE | TRUE | 1
SA.Adrian | delta.sm | 2025-01-01 | 2025-02-25 | 0 | 0.25 | TRUE | TRUE | 1
SA.Adrian | delta.sf | 2025-02-26 | 2025-04-12 | 0 | 0.25 | TRUE | TRUE | 1
SA.Adrian | echo.sm | 2025-01-01 | 2025-03-15 | 0 | 0.25 | TRUE | TRUE | 1
SA.Adrian | echo.sf | 2025-04-02 | 2025-05-17 | 0.25 | 0.5 | TRUE | TRUE | 1
SA.Adrian | golf.sm | 2025-01-01 | 2025-05-12 | 0 | 0.25 | TRUE | TRUE | 1
SA.Adrian | golf.sf | 2025-05-13 | 2025-06-27 | 0 | 0.25 | TRUE | TRUE | 1
SA.Adrian | kilo.se | 2025-03-01 | 2025-03-24 | 0.75 | 1 | TRUE | TRUE | 1
SA.Adrian | kilo.sm | 2025-03-25 | 2025-08-01 | 0 | 0.25 | TRUE | TRUE | 1
SA.Adrian | kilo.sf | 2025-08-02 | 2025-09-16 | 0 | 0.25 | TRUE | TRUE | 1
SA.Adrian | lima.se | 2025-03-21 | 2025-04-19 | 1.5 | 1.75 | TRUE | TRUE | 1
SA.Adrian | lima.sm | 2025-04-20 | 2025-11-01 | 0 | 0.25 | TRUE | TRUE | 1
SA.Adrian | lima.sf | 2025-11-02 | 2025-11-30 | 0.25 | 0.5 | TRUE | TRUE | 1
SA.Adrian | mike.se | 2025-03-21 | 2025-04-19 | 0.5 | 0.75 | TRUE | TRUE | 1
SA.Adrian | mike.sm | 2025-04-20 | 2025-11-01 | 0 | 0.25 | TRUE | TRUE | 1
SA.Adrian | mike.sf | 2025-11-02 | 2025-11-30 | 0.25 | 0.5 | TRUE | TRUE | 1
SA.Robert | foxtrot.sm | 2025-01-01 | 2025-04-01 | 0 | 0.25 | TRUE | TRUE | 1
SA.Robert | foxtrot.sf | 2025-04-02 | 2025-05-02 | 0.25 | 0.5 | TRUE | TRUE | 1
SA.Robert | hotel.sm | 2025-01-01 | 2025-09-01 | 0 | 0.25 | TRUE | TRUE | 1
SA.Robert | hotel.sf | 2025-09-02 | 2025-10-17 | 0 | 0.25 | TRUE | TRUE | 1
SA.Robert | india.sm | 2025-01-01 | 2025-10-01 | 0 | 0.25 | TRUE | TRUE | 1
SA.Robert | india.sf | 2025-10-02 | 2025-11-01 | 0.5 | 0.75 | TRUE | TRUE | 1
SA.Robert | juliet.se | 2025-02-10 | 2025-02-27 | 0.5 | 0.75 | TRUE | TRUE | 1
SA.Robert | juliet.sm | 2025-02-28 | 2025-06-30 | 0 | 0.25 | TRUE | TRUE | 1
SA.Robert | juliet.sf | 2025-07-01 | 2025-08-15 | 0 | 0.25 | TRUE | TRUE | 1
SA.Robert | november.se | 2025-05-26 | 2025-06-14 | 0.5 | 0.75 | TRUE | TRUE | 1
SA.Robert | november.sm | 2025-06-15 | 2025-12-30 | 0 | 0.25 | TRUE | TRUE | 1
SA.Robert | november.sf | 2025-12-31 | 2026-01-31 | 0 | 0.25 | TRUE | TRUE | 1
SA.Robert | oscar.se | 2025-06-25 | 2025-07-09 | 0.75 | 1 | TRUE | TRUE | 1
SA.Robert | oscar.sm | 2025-07-10 | 2025-12-30 | 0 | 0.25 | TRUE | TRUE | 1
SA.Robert | oscar.sf | 2025-12-31 | 2026-01-31 | 0.25 | 0.5 | TRUE | TRUE | 1
SA.Kevin | alpha2.se | 2025-01-27 | 2025-02-01 | 2.25 | 2.5 | TRUE | TRUE | 1
SA.Kevin | alpha2.sm | 2025-02-02 | 2025-03-19 | 0.5 | 0.75 | TRUE | TRUE | 1
SA.Kevin | alpha2.sf | 2025-03-20 | 2025-04-01 | 0.75 | 1 | TRUE | TRUE | 1
SA.Kevin | beta2.se | 2025-01-05 | 2025-01-15 | 3.75 | 4 | TRUE | TRUE | 1
SA.Kevin | beta2.sm | 2025-01-16 | 2025-07-15 | 0.25 | 0.5 | TRUE | TRUE | 1
SA.Kevin | beta2.sf | 2025-07-16 | 2025-08-04 | 2.75 | 3 | TRUE | TRUE | 1
SA.Kevin | gamma2.sm | 2025-01-01 | 2025-01-21 | 1 | 1.25 | TRUE | TRUE | 1
SA.Kevin | gamma2.sf | 2025-01-22 | 2025-02-03 | 0.5 | 0.75 | TRUE | TRUE | 1
SA.Kevin | quebec2.se | 2025-06-01 | 2025-06-26 | 2 | 2.25 | TRUE | TRUE | 1
SA.Kevin | quebec2.sm | 2025-06-27 | 2026-11-09 | 0 | 0.25 | TRUE | TRUE | 1
SA.Kevin | quebec2.sf | 2026-11-10 | 2027-01-04 | 0.5 | 0.75 | TRUE | TRUE | 1
SA.Kevin | uniform2.se | 2025-05-01 | 2025-05-16 | 5.25 | 5.5 | TRUE | TRUE | 1
SA.Kevin | uniform2.sm | 2025-05-17 | 2026-02-11 | 0.25 | 0.5 | TRUE | TRUE | 1
SA.Kevin | uniform2.sf | 2026-02-12 | 2026-03-02 | 1.5 | 1.75 | TRUE | TRUE | 1
SA.Kevin | xray2.se | 2025-07-15 | 2025-08-09 | 1 | 1.25 | TRUE | TRUE | 1
SA.Kevin | xray2.sm | 2025-08-10 | 2026-01-07 | 0.25 | 0.5 | TRUE | TRUE | 1
SA.Kevin | xray2.sf | 2026-01-08 | 2026-02-01 | 1 | 1.25 | TRUE | TRUE | 1
SA.Justin | india2.sm | 2025-01-01 | 2025-03-17 | 0 | 0.25 | TRUE | TRUE | 1
SA.Justin | india2.sf | 2025-03-18 | 2025-03-25 | 1.5 | 1.75 | TRUE | TRUE | 1
SA.Justin | juliet2.sm | 2025-01-01 | 2025-03-22 | 0.25 | 0.5 | TRUE | TRUE | 1
SA.Justin | juliet2.sf | 2025-03-23 | 2025-04-01 | 2 | 2.25 | TRUE | TRUE | 1
SA.Justin | lima2.sm | 2025-01-01 | 2025-02-25 | 0.25 | 0.5 | TRUE | TRUE | 1
SA.Justin | lima2.sf | 2025-02-26 | 2025-03-03 | 2.5 | 2.75 | TRUE | TRUE | 1
SA.Martha | kilo2.sm | 2025-01-01 | 2025-02-25 | 0.25 | 0.5 | TRUE | TRUE | 1
SA.Martha | kilo2.sf | 2025-02-26 | 2025-03-03 | 2.5 | 2.75 | TRUE | TRUE | 1
SA.Martha | november2.sm | 2025-01-01 | 2025-03-27 | 0.25 | 0.5 | TRUE | TRUE | 1
SA.Martha | november2.sf | 2025-03-28 | 2025-04-07 | 2 | 2.25 | TRUE | TRUE | 1
SA.Martha | oscar2.sm | 2025-01-01 | 2025-06-20 | 0 | 0.25 | TRUE | TRUE | 1
SA.Martha | oscar2.sf | 2025-06-21 | 2025-06-30 | 1.5 | 1.75 | TRUE | TRUE | 1
SA.Martha | papa2.sm | 2025-01-01 | 2025-06-20 | 0.25 | 0.5 | TRUE | TRUE | 1
SA.Martha | papa2.sf | 2025-06-21 | 2025-06-30 | 2.5 | 2.75 | TRUE | TRUE | 1
SA.Martha | zulu2.se | 2025-06-15 | 2025-07-15 | 2.25 | 2.5 | TRUE | TRUE | 1
SA.Martha | zulu2.sm | 2025-07-16 | 2025-11-23 | 0 | 0.25 | TRUE | TRUE | 1
SA.Martha | zulu2.sf | 2025-11-24 | 2025-12-01 | 1.5 | 1.75 | TRUE | TRUE | 1
SA.Melanie | delta2.sm | 2025-01-01 | 2025-06-20 | 0 | 0.25 | TRUE | TRUE | 1
SA.Melanie | delta2.sf | 2025-06-21 | 2025-07-01 | 1.25 | 1.5 | TRUE | TRUE | 1
SA.Melanie | echo2.sm | 2025-01-01 | 2025-01-21 | 0.5 | 0.75 | TRUE | TRUE | 1
SA.Melanie | echo2.sf | 2025-01-22 | 2025-03-10 | 0 | 0.25 | TRUE | TRUE | 1
SA.Melanie | foxtrot2.sm | 2025-01-01 | 2025-03-22 | 0.75 | 1 | TRUE | TRUE | 1
SA.Melanie | foxtrot2.sf | 2025-03-23 | 2025-04-01 | 4.25 | 4.5 | TRUE | TRUE | 1
SA.Melanie | hotel2.sm | 2025-01-01 | 2025-02-15 | 0.25 | 0.5 | TRUE | TRUE | 1
SA.Melanie | hotel2.sf | 2025-02-16 | 2025-02-25 | 0.5 | 0.75 | TRUE | TRUE | 1
SA.Melanie | mike2.se | 2025-01-10 | 2025-01-25 | 3.5 | 3.75 | TRUE | TRUE | 1
SA.Melanie | mike2.sm | 2025-01-26 | 2025-05-16 | 0.25 | 0.5 | TRUE | TRUE | 1
SA.Melanie | mike2.sf | 2025-05-17 | 2025-06-01 | 1 | 1.25 | TRUE | TRUE | 1
Note on G1: Valid expert?
Note on H1: Valid task?
Note on I1: Are date OK?

## ubday
Expert | Start | End | Lower | Upper | TRUE | TRUE
DEV.Adam | 2025-01-01 | 2025-01-10 | 0 | 1 | TRUE | TRUE
DEV.Andrew | 2025-01-01 | 2025-01-10 | 0 | 1 | 1 | 1
DEV.Anna | 2025-01-01 | 2025-01-10 | 0 | 1 | 1 | 1
DEV.Ava | 2025-01-01 | 2025-01-10 | 0 | 1 | 1 | 1
DEV.Carl | 2025-01-01 | 2025-01-10 | 0 | 1 | 1 | 1
DEV.Charles | 2025-01-01 | 2025-01-10 | 0 | 1 | 1 | 1
DEV.Dorothy | 2025-01-01 | 2025-01-10 | 0 | 1 | 1 | 1
DEV.Edward | 2025-01-01 | 2025-01-10 | 0 | 1 | 1 | 1
DEV.Eric | 2025-01-01 | 2025-01-10 | 0 | 1 | 1 | 1
DEV.Frances | 2025-01-01 | 2025-01-10 | 0 | 1 | 1 | 1
DEV.Francis | 2025-01-01 | 2025-01-10 | 0 | 1 | 1 | 1
DEV.Fred | 2025-01-01 | 2025-01-10 | 0 | 1 | 1 | 1
DEV.Hugo | 2025-01-01 | 2025-01-10 | 0 | 1 | 1 | 1
DEV.Jacob | 2025-01-01 | 2025-01-10 | 0 | 1 | 1 | 1
DEV.Lars | 2025-01-01 | 2025-01-10 | 0 | 1 | 1 | 1
DEV.Lennart | 2025-01-01 | 2025-01-10 | 0 | 1 | 1 | 1
DEV.Martin | 2025-01-01 | 2025-01-10 | 0 | 1 | 1 | 1
DEV.Max | 2025-01-01 | 2025-01-10 | 0 | 1 | 1 | 1
DEV.Michael | 2025-01-01 | 2025-01-10 | 0 | 1 | 1 | 1
DEV.Molly | 2025-01-01 | 2025-01-10 | 0 | 1 | 1 | 1
DEV.Paul | 2025-01-01 | 2025-01-10 | 0 | 1 | 1 | 1
DEV.Sabina | 2025-01-01 | 2025-01-10 | 0 | 1 | 1 | 1
DEV.Stefan | 2025-01-01 | 2025-01-10 | 0 | 1 | 1 | 1
DEV.Tom | 2025-01-01 | 2025-01-10 | 0 | 1 | 1 | 1
DEV.Uma | 2025-01-01 | 2025-01-10 | 0 | 1 | 1 | 1
Note on F1: Valid expert?
Note on G1: Are date OK?

## ebday
Expert | Start | End | Lower | Upper

## period
Name | Start | End | TRUE
Jan.25 | 2024-12-11 | 2025-01-15 | TRUE
Feb.25 | 2025-01-16 | 2025-02-13 | TRUE
Mar.25 | 2025-02-14 | 2025-03-16 | TRUE
Apr.25 | 2025-03-17 | 2025-04-14 | TRUE
May.25 | 2025-04-15 | 2025-05-18 | TRUE
Jun.25 | 2025-05-19 | 2025-06-18 | TRUE
Jul.25 | 2025-06-19 | 2025-07-17 | TRUE
Aug.25 | 2025-07-18 | 2025-08-17 | TRUE
Sep.25 | 2025-08-18 | 2025-09-15 | TRUE
Oct.25 | 2025-09-16 | 2025-10-15 | TRUE
Nov.25 | 2025-10-16 | 2025-11-12 | TRUE
Dec.25 | 2025-11-13 | 2025-12-11 | TRUE
Note on D1: Are dates OK?

## pbsum
Expert | Period | Lower | Upper | #VALUE! | #VALUE!
Note on E1: Valid expert?
Note on F1: Valid period?

## holiday
Date | TRUE
2025-01-01 | TRUE
2025-04-20 | TRUE
2025-05-01 | TRUE
Note on B1: Are dates OK?

## misc
Today | Hours per day | Solver | With ubday | Last day
2024-12-31 | 8 | highs | Yes | 2027-01-04

## imgh
Hours per day | Width | Height | Dpi | Start | End | Bar:color | Bar:hatch | Bar:alpha | Is Start OK? | Is End OK?
| 8 | 4 | 150 | 2025-01-01 | 2027-01-04 | #2ca02c | / | 0.3 | TRUE | TRUE

## imgt
Tasks per day | Width | Height | Dpi | Start | End | Bar:color | Bar:hatch | Bar:alpha | Is Start OK? | Is End OK?
| 8 | 4 | 150 | 2025-01-01 | 2027-01-04 | #d62728 | \ | 0.3 | TRUE | TRUE

## imgs
Hours per day stacked | Width | Height | Dpi | Start | End | Bar:alpha | Is Start OK? | Is End OK?
| 8 | 4 | 150 | 2025-01-01 | 2027-01-04 | 0.6 | TRUE | TRUE

## imgg
Task's Gantt Chart | Width | Height | Dpi | Barh:color | Barh:height | Barh:alpha
| 8 | 4 | 150 | #ff7f0e | 0.9 | 0.6

## imgw
Invoicing Periods Workload | Width | Height | Dpi | Bar:color | Bar:ecolor | Bar:capsize
| 8 | 4 | 150 | #7BC8F6 | #EE0000 | 4

## imgb
Task with bounds | Width | Height | Dpi | Fill:color | Fill:hatch | Fill:alpha | Plot:format | Plot:markeredgewidth | Step:linewidth
| 8 | 4 | 150 | #90EE90 | / | 0.2 | o | 0.5 | 0.5

## imge
Experts per day stacked | Width | Height | Dpi | Bar:alpha
| 8 | 4 | 150 | 0.6