## expert
Name | Comment
Radosław | Project Manager role

## task
Name | Start | End | Work
p2.e | 2024-11-21 | 2024-12-04 | 10
p2.m | 2024-12-05 | 2025-04-02 | 170
p2.f | 2025-04-03 | 2025-04-30 | 60
p3.e | 2024-12-01 | 2024-12-13 | 4
p3.m | 2024-12-14 | 2025-05-30 | 112
p3.f | 2025-05-31 | 2025-06-27 | 24
p4.e | 2024-12-16 | 2025-01-03 | 15
p4.m | 2025-01-04 | 2025-06-20 | 240
p4.f | 2025-06-21 | 2025-07-18 | 40

## assign
Expert | Task
Radosław | p2.e
Radosław | p2.m
Radosław | p2.f
Radosław | p3.e
Radosław | p3.m
Radosław | p3.f
Radosław | p4.e
Radosław | p4.m
Radosław | p4.f

## xbday
Expert | Task | Start | End | Lower | Upper
Radosław | p2.e | 2024-11-21 | 2024-12-04 | 1 | 1
Radosław | p2.m | 2024-12-05 | 2025-04-02 | 1 | 3
Radosław | p2.f | 2025-04-03 | 2025-04-30 | 0 | 3
Radosław | p3.e | 2024-12-01 | 2024-12-07 | 0 | 1
Radosław | p3.e | 2024-12-08 | 2024-12-14 | 0 | 2
Radosław | p3.f | 2025-06-02 | 2025-06-06 | 2 | 2
Radosław | p3.f | 2025-06-09 | 2025-06-27 | 0 | 1
Radosław | p3.m | 2024-12-14 | 2025-05-30 | 0 | 1
Radosław | p4.e | 2024-12-16 | 2025-01-03 | 0 | 2
Radosław | p4.m | 2025-01-04 | 2025-03-04 | 3 | 3
Radosław | p4.m | 2025-03-05 | 2025-05-01 | 2 | 2
Radosław | p4.m | 2025-05-02 | 2025-06-20 | 0 | 1
Radosław | p4.f | 2025-06-21 | 2025-07-18 | 0 | 2

## ubday
Expert | Start | End | Lower | Upper

## ebday
Expert | Start | End | Lower | Upper

## period
Name | Start | End
25.Jan | 2024-12-11 | 2025-01-15
25.Feb | 2025-01-16 | 2025-02-13
25.Mar | 2025-02-14 | 2025-03-16
25.Apr | 2025-03-17 | 2025-04-14
25.May | 2025-04-15 | 2025-05-18

## pbsum
Expert | Period | Lower | Upper
Radosław | 25.Jan | 0 | 200

## holiday
Date
2024-12-25

## misc
Today | Hours per day | Solver | With ubday | Last day
2024-11-20 | 8 | scip | No | 2025-07-18

## imgh
Hours per day | Width | Height | Dpi | Start | End | Bar:color | Bar:hatch | Bar:alpha | Is Start OK? | Is End OK?
| 8 | 4 | 150 | 2024-11-21 | 2024-12-11 | #2ca02c | / | 0.3 | TRUE | TRUE
Formulas:
End = [Start]+20

## imgt
Tasks per day | Width | Height | Dpi | Start | End | Bar:color | Bar:hatch | Bar:alpha | Is Start OK? | Is End OK?
| 8 | 4 | 150 | 2024-11-21 | 2024-12-11 | #d62728 | \ | 0.3 | TRUE | TRUE
Formulas:
End = [Start]+20

## imgs
Hours per day stacked | Width | Height | Dpi | Start | End | Bar:alpha | Is Start OK? | Is End OK?
| 8 | 4 | 150 | 2024-11-21 | 2024-12-11 | 0.6 | TRUE | TRUE
Formulas:
End = [Start]+20

## imgg
Task's Gantt Chart | Width | Height | Dpi | Barh:color | Barh:height | Barh:alpha
| 8 | 4 | 150 | #ff7f0e | 0.9 | 0.6

## imgw
Invoicing Periods Workload | Width | Height | Dpi | Bar:color | Bar:ecolor | Bar:capsize
| 8 | 4 | 150 | #7BC8F6 | #EE0000 | 4

## imgb
Task with bounds | Width | Height | Dpi | Fill:color | Fill:hatch | Fill:alpha | Plot:format | Plot:markeredgewidth | Step:linewidth
| 8 | 4 | 150 | #90EE90 | / | 0.2 | o | 0.5 | 0.5

## imge
Experts per day stacked | Width | Height | Dpi | Bar:alpha
| 8 | 4 | 150 | 0.6