## expert
Name | Comment | TRUE
PM.Angel | the 1st unit | TRUE
Note on C1: Has Expert any task?

## task
Name | Start | End | Work | TRUE | TRUE
charlie.pm | 2025-01-01 | 2025-06-05 | 80 | TRUE | TRUE
charlie.pf | 2025-06-06 | 2025-07-06 | 10 | TRUE | TRUE
delta.pm | 2025-01-01 | 2025-02-25 | 25 | TRUE | TRUE
delta.pf | 2025-02-26 | 2025-04-12 | 5 | TRUE | TRUE
juliet.pe | 2025-02-10 | 2025-02-27 | 10 | TRUE | TRUE
juliet.pm | 2025-02-28 | 2025-06-30 | 50 | TRUE | TRUE
juliet.pf | 2025-07-01 | 2025-08-15 | 5 | TRUE | TRUE
mike.pe | 2025-04-10 | 2025-04-20 | 10 | TRUE | TRUE
mike.pm | 2025-04-21 | 2025-09-25 | 50 | TRUE | TRUE
mike.pf | 2025-09-26 | 2025-10-30 | 5 | TRUE | TRUE
november.pe | 2025-05-26 | 2025-06-14 | 10 | TRUE | TRUE
november.pm | 2025-06-15 | 2025-12-30 | 55 | TRUE | TRUE
november.pf | 2025-12-31 | 2026-01-31 | 5 | TRUE | TRUE
Note on E1: Is task assign to an Expert?
Note on F1: Should task be included?

## assign
Expert | Task | TRUE | TRUE
PM.Angel | charlie.pm | 1 | 1
PM.Angel | charlie.pf | 1 | 1
PM.Angel | delta.pm | 1 | 1
PM.Angel | delta.pf | 1 | 1
PM.Angel | juliet.pe | 1 | 1
PM.Angel | juliet.pm | 1 | 1
PM.Angel | juliet.pf | 1 | 1
PM.Angel | mike.pe | 1 | 1
PM.Angel | mike.pm | 1 | 1
PM.Angel | mike.pf | 1 | 1
PM.Angel | november.pe | 1 | 1
PM.Angel | november.pm | 1 | 1
PM.Angel | november.pf | 1 | 1
Note on C1: Valid expert?
Note on D1: Valid task?

## xbday
Expert | Task | Start | End | Lower | Upper | TRUE | TRUE
PM.Angel | charlie.pf | 2025-06-06 | 2025-07-06 | 0.25 | 0.5 | TRUE | TRUE
PM.Angel | charlie.pm | 2025-01-01 | 2025-06-05 | 0.5 | 0.75 | TRUE | TRUE
PM.Angel | delta.pf | 2025-02-26 | 2025-04-12 | 0 | 0.25 | TRUE | TRUE
PM.Angel | delta.pm | 2025-01-01 | 2025-02-25 | 0.5 | 0.75 | TRUE | TRUE
PM.Angel | juliet.pe | 2025-02-10 | 2025-02-27 | 0.5 | 0.75 | TRUE | TRUE
PM.Angel | juliet.pf | 2025-07-01 | 2025-08-15 | 0 | 0.25 | TRUE | TRUE
PM.Angel | juliet.pm | 2025-02-28 | 2025-06-30 | 0.5 | 0.75 | TRUE | TRUE
PM.Angel | mike.pe | 2025-04-10 | 2025-04-20 | 1.25 | 1.5 | TRUE | TRUE
PM.Angel | mike.pf | 2025-09-26 | 2025-10-30 | 0 | 0.25 | TRUE | TRUE
PM.Angel | mike.pm | 2025-04-21 | 2025-09-25 | 0.25 | 0.5 | TRUE | TRUE
PM.Angel | november.pe | 2025-05-26 | 2025-06-14 | 0.5 | 0.75 | TRUE | TRUE
PM.Angel | november.pf | 2025-12-31 | 2026-01-31 | 0 | 0.25 | TRUE | TRUE
PM.Angel | november.pm | 2025-06-15 | 2025-12-30 | 0.25 | 0.5 | TRUE | TRUE
Note on G1: Valid expert?
Note on H1: Valid task?

## ubday
Expert | Start | End | Lower | Upper

## ebday
Expert | Start | End | Lower | Upper | TRUE
PM.Angel | 2025-01-01 | 2026-01-01 | 0 | 6 | TRUE
Note on F1: Valid expert?

## period
Name | Start | End | TRUE
Jan.25 | 2024-12-11 | 2025-01-15 | TRUE
Feb.25 | 2025-01-16 | 2025-02-13 | TRUE
Mar.25 | 2025-02-14 | 2025-03-16 | TRUE
Apr.25 | 2025-03-17 | 2025-04-14 | TRUE
May.25 | 2025-04-15 | 2025-05-18 | TRUE
Jun.25 | 2025-05-19 | 2025-06-18 | TRUE
Jul.25 | 2025-06-19 | 2025-07-17 | TRUE
Aug.25 | 2025-07-18 | 2025-08-17 | TRUE
Sep.25 | 2025-08-18 | 2025-09-15 | TRUE
Oct.25 | 2025-09-16 | 2025-10-15 | TRUE
Nov.25 | 2025-10-16 | 2025-11-12 | TRUE
Dec.25 | 2025-11-13 | 2025-12-11 | TRUE

## pbsum
Expert | Period | Lower | Upper | TRUE | TRUE
PM.Angel | Jan.25 | 0 | 180 | TRUE | TRUE
PM.Angel | Feb.25 | 0 | 180 | TRUE | TRUE
PM.Angel | Mar.25 | 0 | 180 | TRUE | TRUE
PM.Angel | Apr.25 | 0 | 180 | TRUE | TRUE
PM.Angel | May.25 | 0 | 180 | TRUE | TRUE
PM.Angel | Jun.25 | 0 | 180 | TRUE | TRUE
PM.Angel | Jul.25 | 0 | 180 | TRUE | TRUE
PM.Angel | Aug.25 | 0 | 180 | TRUE | TRUE
PM.Angel | Sep.25 | 0 | 180 | TRUE | TRUE
PM.Angel | Oct.25 | 0 | 180 | TRUE | TRUE
PM.Angel | Nov.25 | 0 | 180 | TRUE | TRUE
PM.Angel | Dec.25 | 0 | 180 | TRUE | TRUE
Note on E1: Valid expert?
Note on F1: Valid period?

## holiday
Date | TRUE
2025-01-01 | TRUE
2025-04-20 | TRUE
2025-05-01 | TRUE
Note on B1: Are dates OK?

## misc
Today | Hours per day | Solver | With ubday | Last day
2024-12-30 | 8 | gcg | No | 2026-01-31

## imgh
Hours per day | Width | Height | Dpi | Start | End | Bar:color | Bar:hatch | Bar:alpha | Is Start OK? | Is End OK?
| 8 | 4 | 150 | 2025-01-01 | 2025-01-21 | #2ca02c | / | 0.3 | TRUE | TRUE
Formulas:
End = [Start]+20

## imgt
Tasks per day | Width | Height | Dpi | Start | End | Bar:color | Bar:hatch | Bar:alpha | Is Start OK? | Is End OK?
| 8 | 4 | 150 | 2025-01-01 | 2025-01-21 | #d62728 | \ | 0.3 | TRUE | TRUE
Formulas:
End = [Start]+20

## imgs
Hours per day stacked | Width | Height | Dpi | Start | End | Bar:alpha | Is Start OK? | Is End OK?
| 8 | 4 | 150 | 2025-01-01 | 2025-01-21 | 0.6 | TRUE | TRUE
Formulas:
End = [Start]+20

## imgg
Task's Gantt Chart | Width | Height | Dpi | Barh:color | Barh:height | Barh:alpha
| 8 | 4 | 150 | #ff7f0e | 0.9 | 0.6

## imgw
Invoicing Periods Workload | Width | Height | Dpi | Bar:color | Bar:ecolor | Bar:capsize
| 8 | 4 | 150 | #7BC8F6 | #EE0000 | 4

## imgb
Task with bounds | Width | Height | Dpi | Fill:color | Fill:hatch | Fill:alpha | Plot:format | Plot:markeredgewidth | Step:linewidth
| 8 | 4 | 150 | #90EE90 | / | 0.2 | o | 0.5 | 0.5

## imge
Experts per day stacked | Width | Height | Dpi | Bar:alpha
| 8 | 4 | 150 | 0.6