## expert
Name | Comment | TRUE
PM.Lisa | the 1st unit | 1
Note on C1: Has Expert any task?

## task
Name | Start | End | Work | Days | Workdays | Avg[h/day] | Lower | Upper | TRUE | TRUE | TRUE
echo.pm | 2025-01-01 | 2025-03-15 | 20 | 74 | 52 | 0.38462 | 0.25 | 0.5 | 1 | 1 | 1
echo.pf | 2025-04-02 | 2025-05-17 | 5 | 46 | 32 | 0.15625 | 0 | 0.25 | 1 | 1 | 1
foxtrot.pm | 2025-01-01 | 2025-04-01 | 20 | 91 | 64 | 0.3125 | 0.25 | 0.5 | 1 | 1 | 1
foxtrot.pf | 2025-04-02 | 2025-05-02 | 5 | 31 | 22 | 0.22727 | 0 | 0.25 | 1 | 1 | 1
golf.pm | 2025-01-01 | 2025-05-12 | 40 | 132 | 92 | 0.43478 | 0.25 | 0.5 | 1 | 1 | 1
golf.pf | 2025-05-13 | 2025-06-27 | 10 | 46 | 34 | 0.29412 | 0.25 | 0.5 | 1 | 1 | 1
hotel.pm | 2025-01-01 | 2025-09-01 | 80 | 244 | 172 | 0.46512 | 0.25 | 0.5 | 1 | 1 | 1
hotel.pf | 2025-09-02 | 2025-10-17 | 10 | 46 | 34 | 0.29412 | 0.25 | 0.5 | 1 | 1 | 1
kilo.pe | 2025-03-01 | 2025-03-24 | 25 | 24 | 16 | 1.5625 | 1.5 | 1.75 | 1 | 1 | 1
kilo.pm | 2025-03-25 | 2025-08-01 | 15 | 130 | 93 | 0.16129 | 0 | 0.25 | 1 | 1 | 1
kilo.pf | 2025-08-02 | 2025-09-16 | 20 | 46 | 32 | 0.625 | 0.5 | 0.75 | 1 | 1 | 1
lima.pe | 2025-03-21 | 2025-04-19 | 25 | 30 | 21 | 1.1905 | 1 | 1.25 | 1 | 1 | 1
lima.pm | 2025-04-20 | 2025-11-01 | 100 | 196 | 139 | 0.71942 | 0.5 | 0.75 | 1 | 1 | 1
lima.pf | 2025-11-02 | 2025-11-30 | 20 | 29 | 20 | 1 | 1 | 1.25 | 1 | 1 | 1
zulu2.pe | 2025-06-15 | 2025-07-15 | 50 | 31 | 22 | 2.2727 | 2.25 | 2.5 | 1 | 1 | 1
zulu2.pm | 2025-07-16 | 2025-11-23 | 90 | 131 | 93 | 0.96774 | 0.75 | 1 | 1 | 1 | 1
zulu2.pf | 2025-11-24 | 2025-12-01 | 20 | 8 | 6 | 3.3333 | 3.25 | 3.5 | 1 | 1 | 1
Note on J1: Is task assign to an Expert?
Note on K1: Should task be included?
Note on L1: Are date OK?

## assign
Expert | Task | TRUE | TRUE
PM.Lisa | echo.pf | 1 | 1
PM.Lisa | echo.pm | 1 | 1
PM.Lisa | foxtrot.pf | 1 | 1
PM.Lisa | foxtrot.pm | 1 | 1
PM.Lisa | golf.pf | 1 | 1
PM.Lisa | golf.pm | 1 | 1
PM.Lisa | hotel.pf | 1 | 1
PM.Lisa | hotel.pm | 1 | 1
PM.Lisa | kilo.pe | 1 | 1
PM.Lisa | kilo.pf | 1 | 1
PM.Lisa | kilo.pm | 1 | 1
PM.Lisa | lima.pe | 1 | 1
PM.Lisa | lima.pf | 1 | 1
PM.Lisa | lima.pm | 1 | 1
PM.Lisa | zulu2.pe | 1 | 1
PM.Lisa | zulu2.pf | 1 | 1
PM.Lisa | zulu2.pm | 1 | 1
Note on C1: Valid expert?
Note on D1: Valid task?

## xbday
Expert | Task | Start | End | Lower | Upper | TRUE | TRUE | TRUE
PM.Lisa | echo.pm | 2025-01-01 | 2025-03-15 | 0.25 | 0.5 | TRUE | TRUE | TRUE
PM.Lisa | echo.pf | 2025-04-02 | 2025-05-17 | 0 | 0.25 | TRUE | TRUE | TRUE
PM.Lisa | foxtrot.pm | 2025-01-01 | 2025-04-01 | 0.25 | 0.5 | TRUE | TRUE | TRUE
PM.Lisa | foxtrot.pf | 2025-04-02 | 2025-05-02 | 0 | 0.25 | TRUE | TRUE | TRUE
PM.Lisa | golf.pm | 2025-01-01 | 2025-05-12 | 0.25 | 0.5 | TRUE | TRUE | TRUE
PM.Lisa | golf.pf | 2025-05-13 | 2025-06-27 | 0.25 | 0.5 | TRUE | TRUE | TRUE
PM.Lisa | hotel.pm | 2025-01-01 | 2025-09-01 | 0.25 | 0.5 | TRUE | TRUE | TRUE
PM.Lisa | hotel.pf | 2025-09-02 | 2025-10-17 | 0.25 | 0.5 | TRUE | TRUE | TRUE
PM.Lisa | kilo.pe | 2025-03-01 | 2025-03-24 | 1.5 | 1.75 | TRUE | TRUE | TRUE
PM.Lisa | kilo.pm | 2025-03-25 | 2025-08-01 | 0 | 0.25 | TRUE | TRUE | TRUE
PM.Lisa | kilo.pf | 2025-08-02 | 2025-09-16 | 0.5 | 0.75 | TRUE | TRUE | TRUE
PM.Lisa | lima.pe | 2025-03-21 | 2025-04-19 | 1 | 1.25 | TRUE | TRUE | TRUE
PM.Lisa | lima.pm | 2025-04-20 | 2025-11-01 | 0.5 | 0.75 | TRUE | TRUE | TRUE
PM.Lisa | lima.pf | 2025-11-02 | 2025-11-30 | 1 | 1.25 | TRUE | TRUE | TRUE
PM.Lisa | zulu2.pe | 2025-06-15 | 2025-07-15 | 2.25 | 2.5 | TRUE | TRUE | TRUE
PM.Lisa | zulu2.pm | 2025-07-16 | 2025-11-23 | 0.75 | 1 | TRUE | TRUE | TRUE
PM.Lisa | zulu2.pf | 2025-11-24 | 2025-12-01 | 3.25 | 3.5 | TRUE | TRUE | TRUE
Note on G1: Valid expert?
Note on H1: Valid task?
Note on I1: Are date OK?

## ubday
Expert | Start | End | Lower | Upper

## ebday
Expert | Start | End | Lower | Upper

## period
Name | Start | End | TRUE
Jan.25 | 2024-12-11 | 2025-01-15 | TRUE
Feb.25 | 2025-01-16 | 2025-02-13 | TRUE
Mar.25 | 2025-02-14 | 2025-03-16 | TRUE
Apr.25 | 2025-03-17 | 2025-04-14 | TRUE
May.25 | 2025-04-15 | 2025-05-18 | TRUE
Jun.25 | 2025-05-19 | 2025-06-18 | TRUE
Jul.25 | 2025-06-19 | 2025-07-17 | TRUE
Aug.25 | 2025-07-18 | 2025-08-17 | TRUE
Sep.25 | 2025-08-18 | 2025-09-15 | TRUE
Oct.25 | 2025-09-16 | 2025-10-15 | TRUE
Nov.25 | 2025-10-16 | 2025-11-12 | TRUE
Dec.25 | 2025-11-13 | 2025-12-11 | TRUE
Note on D1: Are dates OK?

## pbsum
Expert | Period | Lower | Upper | TRUE | TRUE
PM.Lisa | Jan.25 | 0 | 180 | TRUE | TRUE
PM.Lisa | Feb.25 | 0 | 180 | TRUE | TRUE
PM.Lisa | Mar.25 | 0 | 180 | TRUE | TRUE
PM.Lisa | Apr.25 | 0 | 180 | TRUE | TRUE
PM.Lisa | May.25 | 0 | 180 | TRUE | TRUE
PM.Lisa | Jun.25 | 0 | 180 | TRUE | TRUE
PM.Lisa | Jul.25 | 0 | 180 | TRUE | TRUE
PM.Lisa | Aug.25 | 0 | 180 | TRUE | TRUE
PM.Lisa | Sep.25 | 0 | 180 | TRUE | TRUE
PM.Lisa | Oct.25 | 0 | 180 | TRUE | TRUE
PM.Lisa | Nov.25 | 0 | 180 | TRUE | TRUE
PM.Lisa | Dec.25 | 0 | 180 | TRUE | TRUE
Note on E1: Valid expert?
Note on F1: Valid period?

## holiday
Date | TRUE
2025-01-01 | TRUE
2025-04-20 | TRUE
2025-05-01 | TRUE
Note on B1: Are dates OK?

## misc
Today | Hours per day | Solver | With ubday | Last day
2024-12-30 | 8 | highs | No | 2025-12-11

## imgh
Hours per day | Width | Height | Dpi | Start | End | Bar:color | Bar:hatch | Bar:alpha | Is Start OK? | Is End OK?
| 8 | 4 | 150 | 2024-12-31 | 2025-12-11 | #2ca02c | / | 0.3 | TRUE | TRUE

## imgt
Tasks per day | Width | Height | Dpi | Start | End | Bar:color | Bar:hatch | Bar:alpha | Is Start OK? | Is End OK?
| 8 | 4 | 150 | 2024-12-31 | 2025-12-11 | #d62728 | \ | 0.3 | TRUE | TRUE

## imgs
Hours per day stacked | Width | Height | Dpi | Start | End | Bar:alpha | Is Start OK? | Is End OK?
| 8 | 4 | 150 | 2024-12-31 | 2025-12-11 | 0.6 | TRUE | TRUE

## imgg
Task's Gantt Chart | Width | Height | Dpi | Barh:color | Barh:height | Barh:alpha
| 8 | 4 | 150 | #ff7f0e | 0.9 | 0.6

## imgw
Invoicing Periods Workload | Width | Height | Dpi | Bar:color | Bar:ecolor | Bar:capsize
| 8 | 4 | 150 | #7BC8F6 | #EE0000 | 4

## imgb
Task with bounds | Width | Height | Dpi | Fill:color | Fill:hatch | Fill:alpha | Plot:format | Plot:markeredgewidth | Step:linewidth
| 8 | 4 | 150 | #90EE90 | / | 0.2 | o | 0.5 | 0.5

## imge
Experts per day stacked | Width | Height | Dpi | Bar:alpha
| 8 | 4 | 150 | 0.6