## expert
Name | Comment | TRUE
PM.Fabian | the 2nd unit | 1
Note on C1: Has Expert any task?

## task
Name | Start | End | Work | Days | Workdays | Avg[h/day] | Lower | Upper | TRUE | TRUE | TRUE
india2.pm | 2025-01-01 | 2025-03-17 | 40 | 76 | 53 | 0.75472 | 0.75 | 1 | 1 | 1 | 1
india2.pf | 2025-03-18 | 2025-03-25 | 10 | 8 | 6 | 1.6667 | 1.5 | 1.75 | 1 | 1 | 1
kilo2.pm | 2025-01-01 | 2025-02-25 | 30 | 56 | 39 | 0.76923 | 0.75 | 1 | 1 | 1 | 1
kilo2.pf | 2025-02-26 | 2025-03-03 | 15 | 6 | 4 | 3.75 | 3.75 | 4 | 1 | 1 | 1
november2.pm | 2025-01-01 | 2025-03-27 | 60 | 86 | 61 | 0.98361 | 0.75 | 1 | 1 | 1 | 1
november2.pf | 2025-03-28 | 2025-04-07 | 20 | 11 | 7 | 2.8571 | 2.75 | 3 | 1 | 1 | 1
romeo2.pm | 2025-01-01 | 2025-05-21 | 30 | 141 | 99 | 0.30303 | 0.25 | 0.5 | 1 | 1 | 1
romeo2.pf | 2025-05-22 | 2025-06-02 | 15 | 12 | 8 | 1.875 | 1.75 | 2 | 1 | 1 | 1
victor2.pe | 2025-03-15 | 2025-04-09 | 60 | 26 | 18 | 3.3333 | 3.25 | 3.5 | 1 | 1 | 1
victor2.pm | 2025-04-10 | 2025-08-18 | 90 | 131 | 92 | 0.97826 | 0.75 | 1 | 1 | 1 | 1
victor2.pf | 2025-08-19 | 2025-09-01 | 20 | 14 | 10 | 2 | 2 | 2.25 | 1 | 1 | 1
Note on J1: Is task assign to an Expert?
Note on K1: Should task be included?
Note on L1: Are date OK?

## assign
Expert | Task | TRUE | TRUE
PM.Fabian | india2.pf | 1 | 1
PM.Fabian | india2.pm | 1 | 1
PM.Fabian | kilo2.pf | 1 | 1
PM.Fabian | kilo2.pm | 1 | 1
PM.Fabian | november2.pf | 1 | 1
PM.Fabian | november2.pm | 1 | 1
PM.Fabian | romeo2.pf | 1 | 1
PM.Fabian | romeo2.pm | 1 | 1
PM.Fabian | victor2.pe | 1 | 1
PM.Fabian | victor2.pf | 1 | 1
PM.Fabian | victor2.pm | 1 | 1
Note on C1: Valid expert?
Note on D1: Valid task?

## xbday
Expert | Task | Start | End | Lower | Upper | TRUE | TRUE | TRUE
PM.Fabian | india2.pm | 2025-01-01 | 2025-03-17 | 0.75 | 1 | TRUE | TRUE | TRUE
PM.Fabian | india2.pf | 2025-03-18 | 2025-03-25 | 1.5 | 1.75 | TRUE | TRUE | TRUE
PM.Fabian | kilo2.pm | 2025-01-01 | 2025-02-25 | 0.75 | 1 | TRUE | TRUE | TRUE
PM.Fabian | kilo2.pf | 2025-02-26 | 2025-03-03 | 3.75 | 4 | TRUE | TRUE | TRUE
PM.Fabian | november2.pm | 2025-01-01 | 2025-03-27 | 0.75 | 1 | TRUE | TRUE | TRUE
PM.Fabian | november2.pf | 2025-03-28 | 2025-04-07 | 2.75 | 3 | TRUE | TRUE | TRUE
PM.Fabian | romeo2.pm | 2025-01-01 | 2025-05-21 | 0.25 | 0.5 | TRUE | TRUE | TRUE
PM.Fabian | romeo2.pf | 2025-05-22 | 2025-06-02 | 1.75 | 2 | TRUE | TRUE | TRUE
PM.Fabian | victor2.pe | 2025-03-15 | 2025-04-09 | 3.25 | 3.5 | TRUE | TRUE | TRUE
PM.Fabian | victor2.pm | 2025-04-10 | 2025-08-18 | 0.75 | 1 | TRUE | TRUE | TRUE
PM.Fabian | victor2.pf | 2025-08-19 | 2025-09-01 | 2 | 2.25 | TRUE | TRUE | TRUE
Note on G1: Valid expert?
Note on H1: Valid task?
Note on I1: Are date OK?

## ubday
Expert | Start | End | Lower | Upper

## ebday
Expert | Start | End | Lower | Upper

## period
Name | Start | End | TRUE
Jan.25 | 2024-12-11 | 2025-01-15 | TRUE
Feb.25 | 2025-01-16 | 2025-02-13 | TRUE
Mar.25 | 2025-02-14 | 2025-03-16 | TRUE
Apr.25 | 2025-03-17 | 2025-04-14 | TRUE
May.25 | 2025-04-15 | 2025-05-18 | TRUE
Jun.25 | 2025-05-19 | 2025-06-18 | TRUE
Jul.25 | 2025-06-19 | 2025-07-17 | TRUE
Aug.25 | 2025-07-18 | 2025-08-17 | TRUE
Sep.25 | 2025-08-18 | 2025-09-15 | TRUE
Oct.25 | 2025-09-16 | 2025-10-15 | TRUE
Nov.25 | 2025-10-16 | 2025-11-12 | TRUE
Dec.25 | 2025-11-13 | 2025-12-11 | TRUE
Note on D1: Are dates OK?

## pbsum
Expert | Period | Lower | Upper | TRUE | TRUE
PM.Fabian | Jan.25 | 0 | 180 | TRUE | TRUE
PM.Fabian | Feb.25 | 0 | 180 | TRUE | TRUE
PM.Fabian | Mar.25 | 0 | 180 | TRUE | TRUE
PM.Fabian | Apr.25 | 0 | 180 | TRUE | TRUE
PM.Fabian | May.25 | 0 | 180 | TRUE | TRUE
PM.Fabian | Jun.25 | 0 | 180 | TRUE | TRUE
PM.Fabian | Jul.25 | 0 | 180 | TRUE | TRUE
PM.Fabian | Aug.25 | 0 | 180 | TRUE | TRUE
PM.Fabian | Sep.25 | 0 | 180 | TRUE | TRUE
PM.Fabian | Oct.25 | 0 | 180 | TRUE | TRUE
PM.Fabian | Nov.25 | 0 | 180 | TRUE | TRUE
PM.Fabian | Dec.25 | 0 | 180 | TRUE | TRUE
Note on E1: Valid expert?
Note on F1: Valid period?

## holiday
Date | TRUE
2025-01-01 | TRUE
2025-04-20 | TRUE
2025-05-01 | TRUE
Note on B1: Are dates OK?

## misc
Today | Hours per day | Solver | With ubday | Last day
2024-12-30 | 8 | highs | No | 2025-12-11

## imgh
Hours per day | Width | Height | Dpi | Start | End | Bar:color | Bar:hatch | Bar:alpha | Is Start OK? | Is End OK?
| 8 | 4 | 150 | 2024-12-31 | 2025-12-11 | #2ca02c | / | 0.3 | TRUE | TRUE

## imgt
Tasks per day | Width | Height | Dpi | Start | End | Bar:color | Bar:hatch | Bar:alpha | Is Start OK? | Is End OK?
| 8 | 4 | 150 | 2024-12-31 | 2025-12-11 | #d62728 | \ | 0.3 | TRUE | TRUE

## imgs
Hours per day stacked | Width | Height | Dpi | Start | End | Bar:alpha | Is Start OK? | Is End OK?
| 8 | 4 | 150 | 2024-12-31 | 2025-12-11 | 0.6 | TRUE | TRUE

## imgg
Task's Gantt Chart | Width | Height | Dpi | Barh:color | Barh:height | Barh:alpha
| 8 | 4 | 150 | #ff7f0e | 0.9 | 0.6

## imgw
Invoicing Periods Workload | Width | Height | Dpi | Bar:color | Bar:ecolor | Bar:capsize
| 8 | 4 | 150 | #7BC8F6 | #EE0000 | 4

## imgb
Task with bounds | Width | Height | Dpi | Fill:color | Fill:hatch | Fill:alpha | Plot:format | Plot:markeredgewidth | Step:linewidth
| 8 | 4 | 150 | #90EE90 | / | 0.2 | o | 0.5 | 0.5

## imge
Experts per day stacked | Width | Height | Dpi | Bar:alpha
| 8 | 4 | 150 | 0.6