## expert
Name | Comment | TRUE
SA.Robert | the 1st unit | 1
Note on C1: Has Expert any task?

## task
Name | Start | End | Work | Days | Workdays | Avg[h/day] | Lower | Upper | TRUE | TRUE | TRUE
foxtrot.sm | 2025-01-01 | 2025-04-01 | 8 | 91 | 64 | 0.125 | 0 | 0.25 | 1 | TRUE | TRUE
foxtrot.sf | 2025-04-02 | 2025-05-02 | 8 | 31 | 22 | 0.36364 | 0.25 | 0.5 | TRUE | TRUE | TRUE
hotel.sm | 2025-01-01 | 2025-09-01 | 15 | 244 | 172 | 0.087209 | 0 | 0.25 | TRUE | TRUE | TRUE
hotel.sf | 2025-09-02 | 2025-10-17 | 5 | 46 | 34 | 0.14706 | 0 | 0.25 | TRUE | TRUE | TRUE
india.sm | 2025-01-01 | 2025-10-01 | 30 | 274 | 194 | 0.15464 | 0 | 0.25 | TRUE | TRUE | TRUE
india.sf | 2025-10-02 | 2025-11-01 | 12 | 31 | 22 | 0.54545 | 0.5 | 0.75 | TRUE | TRUE | TRUE
juliet.se | 2025-02-10 | 2025-02-27 | 10 | 18 | 14 | 0.71429 | 0.5 | 0.75 | TRUE | TRUE | TRUE
juliet.sm | 2025-02-28 | 2025-06-30 | 10 | 123 | 86 | 0.11628 | 0 | 0.25 | TRUE | TRUE | TRUE
juliet.sf | 2025-07-01 | 2025-08-15 | 5 | 46 | 34 | 0.14706 | 0 | 0.25 | TRUE | TRUE | TRUE
november.se | 2025-05-26 | 2025-06-14 | 10 | 20 | 15 | 0.66667 | 0.5 | 0.75 | TRUE | TRUE | TRUE
november.sm | 2025-06-15 | 2025-12-30 | 10 | 199 | 142 | 0.070423 | 0 | 0.25 | TRUE | TRUE | TRUE
november.sf | 2025-12-31 | 2026-01-31 | 5 | 32 | 23 | 0.21739 | 0 | 0.25 | TRUE | TRUE | TRUE
oscar.se | 2025-06-25 | 2025-07-09 | 10 | 15 | 11 | 0.90909 | 0.75 | 1 | TRUE | TRUE | TRUE
oscar.sm | 2025-07-10 | 2025-12-30 | 10 | 174 | 124 | 0.080645 | 0 | 0.25 | TRUE | TRUE | TRUE
oscar.sf | 2025-12-31 | 2026-01-31 | 8 | 32 | 23 | 0.34783 | 0.25 | 0.5 | TRUE | TRUE | TRUE
Note on J1: Is task assign to an Expert?
Note on K1: Should task be included?
Note on L1: Are date OK?

## assign
Expert | Task | TRUE | TRUE
SA.Robert | foxtrot.sf | 1 | 1
SA.Robert | foxtrot.sm | 1 | 1
SA.Robert | hotel.sf | 1 | 1
SA.Robert | hotel.sm | 1 | 1
SA.Robert | india.sf | 1 | 1
SA.Robert | india.sm | 1 | 1
SA.Robert | juliet.se | 1 | 1
SA.Robert | juliet.sf | 1 | 1
SA.Robert | juliet.sm | 1 | 1
SA.Robert | november.se | 1 | 1
SA.Robert | november.sf | 1 | 1
SA.Robert | november.sm | 1 | 1
SA.Robert | oscar.se | 1 | 1
SA.Robert | oscar.sf | 1 | 1
SA.Robert | oscar.sm | 1 | 1
Note on C1: Valid expert?
Note on D1: Valid task?

## xbday
Expert | Task | Start | End | Lower | Upper | TRUE | TRUE | TRUE
SA.Robert | foxtrot.sm | 2025-01-01 | 2025-04-01 | 0 | 0.25 | TRUE | TRUE | TRUE
SA.Robert | foxtrot.sf | 2025-04-02 | 2025-05-02 | 0.25 | 0.5 | TRUE | TRUE | TRUE
SA.Robert | hotel.sm | 2025-01-01 | 2025-09-01 | 0 | 0.25 | TRUE | TRUE | TRUE
SA.Robert | hotel.sf | 2025-09-02 | 2025-10-17 | 0 | 0.25 | TRUE | TRUE | TRUE
SA.Robert | india.sm | 2025-01-01 | 2025-10-01 | 0 | 0.25 | TRUE | TRUE | TRUE
SA.Robert | india.sf | 2025-10-02 | 2025-11-01 | 0.5 | 0.75 | TRUE | TRUE | TRUE
SA.Robert | juliet.se | 2025-02-10 | 2025-02-27 | 0.5 | 0.75 | TRUE | TRUE | TRUE
SA.Robert | juliet.sm | 2025-02-28 | 2025-06-30 | 0 | 0.25 | TRUE | TRUE | TRUE
SA.Robert | juliet.sf | 2025-07-01 | 2025-08-15 | 0 | 0.25 | TRUE | TRUE | TRUE
SA.Robert | november.se | 2025-05-26 | 2025-06-14 | 0.5 | 0.75 | TRUE | TRUE | TRUE
SA.Robert | november.sm | 2025-06-15 | 2025-12-30 | 0 | 0.25 | TRUE | TRUE | TRUE
SA.Robert | november.sf | 2025-12-31 | 2026-01-31 | 0 | 0.25 | TRUE | TRUE | TRUE
SA.Robert | oscar.se | 2025-06-25 | 2025-07-09 | 0.75 | 1 | TRUE | TRUE | TRUE
SA.Robert | oscar.sm | 2025-07-10 | 2025-12-30 | 0 | 0.25 | TRUE | TRUE | TRUE
SA.Robert | oscar.sf | 2025-12-31 | 2026-01-31 | 0.25 | 0.5 | TRUE | TRUE | TRUE
Note on G1: Valid expert?
Note on H1: Valid task?
Note on I1: Are date OK?

## ubday
Expert | Start | End | Lower | Upper

## ebday
Expert | Start | End | Lower | Upper

## period
Name | Start | End | TRUE
Jan.25 | 2024-12-11 | 2025-01-15 | TRUE
Feb.25 | 2025-01-16 | 2025-02-13 | TRUE
Mar.25 | 2025-02-14 | 2025-03-16 | TRUE
Apr.25 | 2025-03-17 | 2025-04-14 | TRUE
May.25 | 2025-04-15 | 2025-05-18 | TRUE
Jun.25 | 2025-05-19 | 2025-06-18 | TRUE
Jul.25 | 2025-06-19 | 2025-07-17 | TRUE
Aug.25 | 2025-07-18 | 2025-08-17 | TRUE
Sep.25 | 2025-08-18 | 2025-09-15 | TRUE
Oct.25 | 2025-09-16 | 2025-10-15 | TRUE
Nov.25 | 2025-10-16 | 2025-11-12 | TRUE
Dec.25 | 2025-11-13 | 2025-12-11 | TRUE
Note on D1: Are dates OK?

## pbsum
Expert | Period | Lower | Upper | TRUE | TRUE
SA.Robert | Jan.25 | 0 | 180 | TRUE | TRUE
SA.Robert | Feb.25 | 0 | 180 | TRUE | TRUE
SA.Robert | Mar.25 | 0 | 180 | TRUE | TRUE
SA.Robert | Apr.25 | 0 | 180 | TRUE | TRUE
SA.Robert | May.25 | 0 | 180 | TRUE | TRUE
SA.Robert | Jun.25 | 0 | 180 | TRUE | TRUE
SA.Robert | Jul.25 | 0 | 180 | TRUE | TRUE
SA.Robert | Aug.25 | 0 | 180 | TRUE | TRUE
SA.Robert | Sep.25 | 0 | 180 | TRUE | TRUE
SA.Robert | Oct.25 | 0 | 180 | TRUE | TRUE
SA.Robert | Nov.25 | 0 | 180 | TRUE | TRUE
SA.Robert | Dec.25 | 0 | 180 | TRUE | TRUE
Note on E1: Valid expert?
Note on F1: Valid period?

## holiday
Date | TRUE
2025-01-01 | TRUE
2025-04-20 | TRUE
2025-05-01 | TRUE
Note on B1: Are dates OK?

## misc
Today | Hours per day | Solver | With ubday | Last day
2024-12-30 | 8 | highs | No | 2026-01-31

## imgh
Hours per day | Width | Height | Dpi | Start | End | Bar:color | Bar:hatch | Bar:alpha | Is Start OK? | Is End OK?
| 8 | 4 | 150 | 2024-12-31 | 2026-01-31 | #2ca02c | / | 0.3 | TRUE | TRUE

## imgt
Tasks per day | Width | Height | Dpi | Start | End | Bar:color | Bar:hatch | Bar:alpha | Is Start OK? | Is End OK?
| 8 | 4 | 150 | 2024-12-31 | 2026-01-31 | #d62728 | \ | 0.3 | TRUE | TRUE

## imgs
Hours per day stacked | Width | Height | Dpi | Start | End | Bar:alpha | Is Start OK? | Is End OK?
| 8 | 4 | 150 | 2024-12-31 | 2026-01-31 | 0.6 | TRUE | TRUE

## imgg
Task's Gantt Chart | Width | Height | Dpi | Barh:color | Barh:height | Barh:alpha
| 8 | 4 | 150 | #ff7f0e | 0.9 | 0.6

## imgw
Invoicing Periods Workload | Width | Height | Dpi | Bar:color | Bar:ecolor | Bar:capsize
| 8 | 4 | 150 | #7BC8F6 | #EE0000 | 4

## imgb
Task with bounds | Width | Height | Dpi | Fill:color | Fill:hatch | Fill:alpha | Plot:format | Plot:markeredgewidth | Step:linewidth
| 8 | 4 | 150 | #90EE90 | / | 0.2 | o | 0.5 | 0.5

## imge
Experts per day stacked | Width | Height | Dpi | Bar:alpha
| 8 | 4 | 150 | 0.6