## experts
Name | Comment | TRUE
SA.Peter | the 2nd unit | 1
Note on C1: Has Expert any task?

## tasks
Name | Start | End | Work | Days | Workdays | Avg[h/day] | Lower | Upper | TRUE | TRUE | TRUE
golf2.sm | 2025-01-01 | 2025-03-22 | 20 | 81 | 57 | 0.35088 | 0.25 | 0.5 | 1 | TRUE | 1
golf2.sf | 2025-03-23 | 2025-03-31 | 10 | 9 | 6 | 1.6667 | 1.5 | 1.75 | 1 | 1 | 1
tango2.se | 2025-02-01 | 2025-02-16 | 60 | 16 | 10 | 6 | 6 | 6.25 | 1 | 1 | 1
tango2.sm | 2025-02-17 | 2025-09-15 | 60 | 211 | 150 | 0.4 | 0.25 | 0.5 | 1 | 1 | 1
tango2.sf | 2025-09-16 | 2025-10-01 | 20 | 16 | 12 | 1.6667 | 1.5 | 1.75 | 1 | 1 | 1
victor2.se | 2025-02-15 | 2025-03-02 | 20 | 16 | 10 | 2 | 2 | 2.25 | 1 | 1 | 1
victor2.sm | 2025-03-03 | 2025-08-20 | 20 | 171 | 122 | 0.16393 | 0 | 0.25 | 1 | 1 | 1
victor2.sf | 2025-08-21 | 2025-09-01 | 10 | 12 | 8 | 1.25 | 1.25 | 1.5 | 1 | 1 | 1
Note on J1: Is task assign to an Expert?
Note on K1: Should task be included?
Note on L1: Are date OK?

## links
Expert | Task | TRUE | TRUE
SA.Peter | golf2.sf | 1 | 1
SA.Peter | golf2.sm | 1 | 1
SA.Peter | tango2.se | 1 | 1
SA.Peter | tango2.sf | 1 | 1
SA.Peter | tango2.sm | 1 | 1
SA.Peter | victor2.se | 1 | 1
SA.Peter | victor2.sf | 1 | 1
SA.Peter | victor2.sm | 1 | 1
Note on C1: Valid expert?
Note on D1: Valid task?

## xbday
Expert | Task | Start | End | Lower | Upper | TRUE | TRUE | TRUE
SA.Peter | golf2.sm | 2025-01-01 | 2025-03-22 | 0.25 | 0.5 | TRUE | TRUE | TRUE
SA.Peter | golf2.sf | 2025-03-23 | 2025-03-31 | 1.5 | 1.75 | TRUE | TRUE | TRUE
SA.Peter | tango2.se | 2025-02-01 | 2025-02-16 | 6 | 6.25 | TRUE | TRUE | TRUE
SA.Peter | tango2.sm | 2025-02-17 | 2025-09-15 | 0.25 | 0.5 | TRUE | TRUE | TRUE
SA.Peter | tango2.sf | 2025-09-16 | 2025-10-01 | 1.5 | 1.75 | TRUE | TRUE | TRUE
SA.Peter | victor2.se | 2025-02-15 | 2025-03-02 | 2 | 2.25 | TRUE | TRUE | TRUE
SA.Peter | victor2.sm | 2025-03-03 | 2025-08-20 | 0 | 0.25 | TRUE | TRUE | TRUE
SA.Peter | victor2.sf | 2025-08-21 | 2025-09-01 | 1.25 | 1.5 | TRUE | TRUE | TRUE
Note on G1: Valid expert?
Note on H1: Valid task?
Note on I1: Are date OK?

## xbsum
Expert | Task | Start | End | Lower | Upper

## ubday
Expert | Start | End | Lower | Upper

## ubsum
Expert | Task | Start | End | Lower | Upper

## expert bounds
Expert | Start | End | Lower | Upper

## invoicing periods
Name | Start | End | TRUE
Jan.25 | 2024-12-11 | 2025-01-15 | TRUE
Feb.25 | 2025-01-16 | 2025-02-13 | TRUE
Mar.25 | 2025-02-14 | 2025-03-16 | TRUE
Apr.25 | 2025-03-17 | 2025-04-14 | TRUE
May.25 | 2025-04-15 | 2025-05-18 | TRUE
Jun.25 | 2025-05-19 | 2025-06-18 | TRUE
Jul.25 | 2025-06-19 | 2025-07-17 | TRUE
Aug.25 | 2025-07-18 | 2025-08-17 | TRUE
Sep.25 | 2025-08-18 | 2025-09-15 | TRUE
Oct.25 | 2025-09-16 | 2025-10-15 | TRUE
Nov.25 | 2025-10-16 | 2025-11-12 | TRUE
Dec.25 | 2025-11-13 | 2025-12-11 | TRUE
Note on D1: Are dates OK?

## invoicing periods bounds
Expert | Period | Lower | Upper | TRUE | TRUE
SA.Peter | Jan.25 | 0 | 180 | TRUE | TRUE
SA.Peter | Feb.25 | 0 | 180 | TRUE | TRUE
SA.Peter | Mar.25 | 0 | 180 | TRUE | TRUE
SA.Peter | Apr.25 | 0 | 180 | TRUE | TRUE
SA.Peter | May.25 | 0 | 180 | TRUE | TRUE
SA.Peter | Jun.25 | 0 | 180 | TRUE | TRUE
SA.Peter | Jul.25 | 0 | 180 | TRUE | TRUE
SA.Peter | Aug.25 | 0 | 180 | TRUE | TRUE
SA.Peter | Sep.25 | 0 | 180 | TRUE | TRUE
SA.Peter | Oct.25 | 0 | 180 | TRUE | TRUE
SA.Peter | Nov.25 | 0 | 180 | TRUE | TRUE
SA.Peter | Dec.25 | 0 | 180 | TRUE | TRUE
Note on E1: Valid expert?
Note on F1: Valid period?

## public holidays
Date | TRUE
2025-01-01 | TRUE
2025-04-20 | TRUE
2025-05-01 | TRUE
Note on B1: Are dates OK?

## misc
Today | Hours per day | Solver | Last day
2024-12-30 | 8 | highs | 2025-12-11

## himg
Hours per day | Width | Height | Dpi | Start | End | Bar:color | Bar:hatch | Bar:alpha | Is Start OK? | Is End OK?
| 8 | 4 | 150 | 2024-12-31 | 2025-12-11 | #2ca02c | / | 0.3 | TRUE | TRUE

## timg
Tasks per day | Width | Height | Dpi | Start | End | Bar:color | Bar:hatch | Bar:alpha | Is Start OK? | Is End OK?
| 8 | 4 | 150 | 2024-12-31 | 2025-12-11 | #d62728 | \ | 0.3 | TRUE | TRUE

## simg
Hours per day stacked | Width | Height | Dpi | Start | End | Bar:alpha | Is Start OK? | Is End OK?
| 8 | 4 | 150 | 2024-12-31 | 2025-12-11 | 0.6 | TRUE | TRUE

## gimg
Task's Gantt Chart | Width | Height | Dpi | Barh:color | Barh:height | Barh:alpha
| 8 | 4 | 150 | #ff7f0e | 0.9 | 0.6

## wimg
Invoicing Periods Workload | Width | Height | Dpi | Bar:color | Bar:ecolor | Bar:capsize
| 8 | 4 | 150 | #7BC8F6 | #EE0000 | 4

## bimg
Task with bounds | Width | Height | Dpi | Fill:color | Fill:hatch | Fill:alpha | Plot:format | Plot:markeredgewidth | Step:linewidth
| 8 | 4 | 150 | #90EE90 | / | 0.2 | o | 0.5 | 0.5