## experts
Name | Comment | TRUE
SA.Martha | the 2nd unit | 1
Note on C1: Has Expert any task?

## tasks
Name | Start | End | Work | Days | Workdays | Avg[h/day] | Lower | Upper | TRUE | TRUE | TRUE
kilo2.sm | 2025-01-01 | 2025-02-25 | 15 | 56 | 39 | 0.38462 | 0.25 | 0.5 | 1 | TRUE | 1
kilo2.sf | 2025-02-26 | 2025-03-03 | 10 | 6 | 4 | 2.5 | 2.5 | 2.75 | 1 | 1 | 1
november2.sm | 2025-01-01 | 2025-03-27 | 30 | 86 | 61 | 0.4918 | 0.25 | 0.5 | 1 | 1 | 1
november2.sf | 2025-03-28 | 2025-04-07 | 15 | 11 | 7 | 2.1429 | 2 | 2.25 | 1 | 1 | 1
oscar2.sm | 2025-01-01 | 2025-06-20 | 30 | 171 | 121 | 0.24793 | 0 | 0.25 | 1 | 1 | 1
oscar2.sf | 2025-06-21 | 2025-06-30 | 10 | 10 | 6 | 1.6667 | 1.5 | 1.75 | 1 | 1 | 1
papa2.sm | 2025-01-01 | 2025-06-20 | 40 | 171 | 121 | 0.33058 | 0.25 | 0.5 | 1 | 1 | 1
papa2.sf | 2025-06-21 | 2025-06-30 | 15 | 10 | 6 | 2.5 | 2.5 | 2.75 | 1 | 1 | 1
zulu2.se | 2025-06-15 | 2025-07-15 | 50 | 31 | 22 | 2.2727 | 2.25 | 2.5 | 1 | 1 | 1
zulu2.sm | 2025-07-16 | 2025-11-23 | 20 | 131 | 93 | 0.21505 | 0 | 0.25 | 1 | 1 | 1
zulu2.sf | 2025-11-24 | 2025-12-01 | 10 | 8 | 6 | 1.6667 | 1.5 | 1.75 | 1 | 1 | 1
Note on J1: Is task assign to an Expert?
Note on K1: Should task be included?
Note on L1: Are date OK?

## links
Expert | Task | TRUE | TRUE
SA.Martha | kilo2.sf | 1 | 1
SA.Martha | kilo2.sm | 1 | 1
SA.Martha | november2.sf | 1 | 1
SA.Martha | november2.sm | 1 | 1
SA.Martha | oscar2.sf | 1 | 1
SA.Martha | oscar2.sm | 1 | 1
SA.Martha | papa2.sf | 1 | 1
SA.Martha | papa2.sm | 1 | 1
SA.Martha | zulu2.se | 1 | 1
SA.Martha | zulu2.sf | 1 | 1
SA.Martha | zulu2.sm | 1 | 1
Note on C1: Valid expert?
Note on D1: Valid task?

## xbday
Expert | Task | Start | End | Lower | Upper | TRUE | TRUE | TRUE
SA.Martha | kilo2.sm | 2025-01-01 | 2025-02-25 | 0.25 | 0.5 | TRUE | TRUE | TRUE
SA.Martha | kilo2.sf | 2025-02-26 | 2025-03-03 | 2.5 | 2.75 | TRUE | TRUE | TRUE
SA.Martha | november2.sm | 2025-01-01 | 2025-03-27 | 0.25 | 0.5 | TRUE | TRUE | TRUE
SA.Martha | november2.sf | 2025-03-28 | 2025-04-07 | 2 | 2.25 | TRUE | TRUE | TRUE
SA.Martha | oscar2.sm | 2025-01-01 | 2025-06-20 | 0 | 0.25 | TRUE | TRUE | TRUE
SA.Martha | oscar2.sf | 2025-06-21 | 2025-06-30 | 1.5 | 1.75 | TRUE | TRUE | TRUE
SA.Martha | papa2.sm | 2025-01-01 | 2025-06-20 | 0.25 | 0.5 | TRUE | TRUE | TRUE
SA.Martha | papa2.sf | 2025-06-21 | 2025-06-30 | 2.5 | 2.75 | TRUE | TRUE | TRUE
SA.Martha | zulu2.se | 2025-06-15 | 2025-07-15 | 2.25 | 2.5 | TRUE | TRUE | TRUE
SA.Martha | zulu2.sm | 2025-07-16 | 2025-11-23 | 0 | 0.25 | TRUE | TRUE | TRUE
SA.Martha | zulu2.sf | 2025-11-24 | 2025-12-01 | 1.5 | 1.75 | TRUE | TRUE | TRUE
Note on G1: Valid expert?
Note on H1: Valid task?
Note on I1: Are date OK?

## xbsum
Expert | Task | Start | End | Lower | Upper

## ubday
Expert | Start | End | Lower | Upper

## ubsum
Expert | Task | Start | End | Lower | Upper

## expert bounds
Expert | Start | End | Lower | Upper

## invoicing periods
Name | Start | End | TRUE
Jan.25 | 2024-12-11 | 2025-01-15 | TRUE
Feb.25 | 2025-01-16 | 2025-02-13 | TRUE
Mar.25 | 2025-02-14 | 2025-03-16 | TRUE
Apr.25 | 2025-03-17 | 2025-04-14 | TRUE
May.25 | 2025-04-15 | 2025-05-18 | TRUE
Jun.25 | 2025-05-19 | 2025-06-18 | TRUE
Jul.25 | 2025-06-19 | 2025-07-17 | TRUE
Aug.25 | 2025-07-18 | 2025-08-17 | TRUE
Sep.25 | 2025-08-18 | 2025-09-15 | TRUE
Oct.25 | 2025-09-16 | 2025-10-15 | TRUE
Nov.25 | 2025-10-16 | 2025-11-12 | TRUE
Dec.25 | 2025-11-13 | 2025-12-11 | TRUE
Note on D1: Are dates OK?

## invoicing periods bounds
Expert | Period | Lower | Upper | TRUE | TRUE
SA.Martha | Jan.25 | 0 | 180 | TRUE | TRUE
SA.Martha | Feb.25 | 0 | 180 | TRUE | TRUE
SA.Martha | Mar.25 | 0 | 180 | TRUE | TRUE
SA.Martha | Apr.25 | 0 | 180 | TRUE | TRUE
SA.Martha | May.25 | 0 | 180 | TRUE | TRUE
SA.Martha | Jun.25 | 0 | 180 | TRUE | TRUE
SA.Martha | Jul.25 | 0 | 180 | TRUE | TRUE
SA.Martha | Aug.25 | 0 | 180 | TRUE | TRUE
SA.Martha | Sep.25 | 0 | 180 | TRUE | TRUE
SA.Martha | Oct.25 | 0 | 180 | TRUE | TRUE
SA.Martha | Nov.25 | 0 | 180 | TRUE | TRUE
SA.Martha | Dec.25 | 0 | 180 | TRUE | TRUE
Note on E1: Valid expert?
Note on F1: Valid period?

## public holidays
Date | TRUE
2025-01-01 | TRUE
2025-04-20 | TRUE
2025-05-01 | TRUE
Note on B1: Are dates OK?

## misc
Today | Hours per day | Solver | Last day
2024-12-30 | 8 | highs | 2025-12-11

## himg
Hours per day | Width | Height | Dpi | Start | End | Bar:color | Bar:hatch | Bar:alpha | Is Start OK? | Is End OK?
| 8 | 4 | 150 | 2024-12-31 | 2025-12-11 | #2ca02c | / | 0.3 | TRUE | TRUE

## timg
Tasks per day | Width | Height | Dpi | Start | End | Bar:color | Bar:hatch | Bar:alpha | Is Start OK? | Is End OK?
| 8 | 4 | 150 | 2024-12-31 | 2025-12-11 | #d62728 | \ | 0.3 | TRUE | TRUE

## simg
Hours per day stacked | Width | Height | Dpi | Start | End | Bar:alpha | Is Start OK? | Is End OK?
| 8 | 4 | 150 | 2024-12-31 | 2025-12-11 | 0.6 | TRUE | TRUE

## gimg
Task's Gantt Chart | Width | Height | Dpi | Barh:color | Barh:height | Barh:alpha
| 8 | 4 | 150 | #ff7f0e | 0.9 | 0.6

## wimg
Invoicing Periods Workload | Width | Height | Dpi | Bar:color | Bar:ecolor | Bar:capsize
| 8 | 4 | 150 | #7BC8F6 | #EE0000 | 4

## bimg
Task with bounds | Width | Height | Dpi | Fill:color | Fill:hatch | Fill:alpha | Plot:format | Plot:markeredgewidth | Step:linewidth
| 8 | 4 | 150 | #90EE90 | / | 0.2 | o | 0.5 | 0.5