## expert
Name | Comment | TRUE
PM.Lisa | the 1st unit | TRUE
Note on C1: Has Expert any task?

## task
Name | Start | End | Work | TRUE | TRUE | TRUE
echo.pm | 2025-01-01 | 2025-03-15 | 20 | TRUE | TRUE | TRUE
echo.pf | 2025-04-02 | 2025-05-17 | 5 | TRUE | TRUE | TRUE
foxtrot.pm | 2025-01-01 | 2025-04-01 | 20 | TRUE | TRUE | TRUE
foxtrot.pf | 2025-04-02 | 2025-05-02 | 5 | TRUE | TRUE | TRUE
golf.pm | 2025-01-01 | 2025-05-12 | 40 | TRUE | TRUE | TRUE
golf.pf | 2025-05-13 | 2025-06-27 | 10 | TRUE | TRUE | TRUE
hotel.pm | 2025-01-01 | 2025-09-01 | 80 | TRUE | TRUE | TRUE
hotel.pf | 2025-09-02 | 2025-10-17 | 10 | TRUE | TRUE | TRUE
kilo.pe | 2025-03-01 | 2025-03-24 | 10 | TRUE | TRUE | TRUE
kilo.pm | 2025-03-25 | 2025-08-01 | 50 | TRUE | TRUE | TRUE
kilo.pf | 2025-08-02 | 2025-09-16 | 5 | TRUE | TRUE | TRUE
lima.pe | 2025-03-21 | 2025-04-19 | 25 | TRUE | TRUE | TRUE
lima.pm | 2025-04-20 | 2025-11-01 | 100 | TRUE | TRUE | TRUE
lima.pf | 2025-11-02 | 2025-11-30 | 20 | TRUE | TRUE | TRUE
whisky2.pe | 2025-02-15 | 2025-03-02 | 0 | TRUE | TRUE | TRUE | 80
whisky2.pm | 2025-03-03 | 2025-08-20 | 0 | TRUE | TRUE | TRUE | 200
whisky2.pf | 2025-08-21 | 2025-09-01 | 0 | TRUE | TRUE | TRUE | 20
xray2.pe | 2025-02-15 | 2025-03-02 | 0 | TRUE | TRUE | TRUE | 25
xray2.pm | 2025-03-03 | 2025-08-20 | 0 | TRUE | TRUE | TRUE | 120
xray2.pf | 2025-08-21 | 2025-09-01 | 0 | TRUE | TRUE | TRUE | 10
zulu2.pe | 2025-02-15 | 2025-03-02 | 0 | TRUE | TRUE | TRUE | 50
zulu2.pm | 2025-03-03 | 2025-08-20 | 0 | TRUE | TRUE | TRUE | 90
zulu2.pf | 2025-08-21 | 2025-09-01 | 0 | TRUE | TRUE | TRUE | 20
Note on E1: Is task assign to an Expert?
Note on F1: Should task be included?
Note on G1: Are date OK?

## assign
Expert | Task | TRUE | TRUE
PM.Lisa | echo.pf | TRUE | TRUE
PM.Lisa | echo.pm | TRUE | 1
PM.Lisa | foxtrot.pf | TRUE | 1
PM.Lisa | foxtrot.pm | TRUE | 1
PM.Lisa | golf.pf | TRUE | 1
PM.Lisa | golf.pm | TRUE | 1
PM.Lisa | hotel.pf | TRUE | 1
PM.Lisa | hotel.pm | TRUE | 1
PM.Lisa | kilo.pe | TRUE | 1
PM.Lisa | kilo.pf | TRUE | 1
PM.Lisa | kilo.pm | TRUE | 1
PM.Lisa | lima.pe | TRUE | 1
PM.Lisa | lima.pf | TRUE | 1
PM.Lisa | lima.pm | TRUE | 1
PM.Lisa | whisky2.pe | TRUE | 1
PM.Lisa | whisky2.pf | TRUE | 1
PM.Lisa | whisky2.pm | TRUE | 1
PM.Lisa | xray2.pe | TRUE | 1
PM.Lisa | xray2.pf | TRUE | 1
PM.Lisa | xray2.pm | TRUE | 1
PM.Lisa | zulu2.pe | TRUE | 1
PM.Lisa | zulu2.pf | TRUE | 1
PM.Lisa | zulu2.pm | TRUE | 1
Note on C1: Valid expert?
Note on D1: Valid task?

## xbday
Expert | Task | Start | End | Lower | Upper
PM.Lisa | echo.pf | 2025-04-02 | 2025-05-17 | 0 | 0.25
PM.Lisa | echo.pm | 2025-01-01 | 2025-03-15 | 0.25 | 0.5
PM.Lisa | foxtrot.pf | 2025-04-02 | 2025-05-02 | 0 | 0.25
PM.Lisa | foxtrot.pm | 2025-01-01 | 2025-04-01 | 0.25 | 0.5
PM.Lisa | golf.pf | 2025-05-13 | 2025-06-27 | 0.25 | 0.5
PM.Lisa | golf.pm | 2025-01-01 | 2025-05-12 | 0.25 | 0.5
PM.Lisa | hotel.pf | 2025-09-02 | 2025-10-17 | 0.25 | 0.5
PM.Lisa | hotel.pm | 2025-01-01 | 2025-09-01 | 0.25 | 0.5
PM.Lisa | kilo.pe | 2025-03-01 | 2025-03-24 | 0.5 | 0.75
PM.Lisa | kilo.pf | 2025-08-02 | 2025-09-16 | 0 | 0.25
PM.Lisa | kilo.pm | 2025-03-25 | 2025-08-01 | 0.5 | 0.75
PM.Lisa | lima.pe | 2025-03-21 | 2025-04-19 | 1 | 1.25
PM.Lisa | lima.pf | 2025-11-02 | 2025-11-30 | 1 | 1
PM.Lisa | lima.pm | 2025-04-20 | 2025-11-01 | 0.5 | 0.75
PM.Lisa | whisky2.pe | 2025-02-15 | 2025-03-02 | 0 | 8
PM.Lisa | whisky2.pf | 2025-08-21 | 2025-09-01 | 0 | 8
PM.Lisa | whisky2.pm | 2025-03-03 | 2025-08-20 | 0 | 8
PM.Lisa | xray2.pe | 2025-02-15 | 2025-03-02 | 0 | 8
PM.Lisa | xray2.pf | 2025-08-21 | 2025-09-01 | 0 | 8
PM.Lisa | xray2.pm | 2025-03-03 | 2025-08-20 | 0 | 8
PM.Lisa | zulu2.pe | 2025-02-15 | 2025-03-02 | 0 | 8
PM.Lisa | zulu2.pf | 2025-08-21 | 2025-09-01 | 0 | 8
PM.Lisa | zulu2.pm | 2025-03-03 | 2025-08-20 | 0 | 8

## ubday
Expert | Start | End | Lower | Upper

## ebday
Expert | Start | End | Lower | Upper

## period
Name | Start | End | TRUE
Jan.25 | 2024-12-11 | 2025-01-15 | TRUE
Feb.25 | 2025-01-16 | 2025-02-13 | TRUE
Mar.25 | 2025-02-14 | 2025-03-16 | TRUE
Apr.25 | 2025-03-17 | 2025-04-14 | TRUE
May.25 | 2025-04-15 | 2025-05-18 | TRUE
Jun.25 | 2025-05-19 | 2025-06-18 | TRUE
Jul.25 | 2025-06-19 | 2025-07-17 | TRUE
Aug.25 | 2025-07-18 | 2025-08-17 | TRUE
Sep.25 | 2025-08-18 | 2025-09-15 | TRUE
Oct.25 | 2025-09-16 | 2025-10-15 | TRUE
Nov.25 | 2025-10-16 | 2025-11-12 | TRUE
Dec.25 | 2025-11-13 | 2025-12-11 | TRUE
Note on D1: Are dates OK?

## pbsum
Expert | Period | Lower | Upper | TRUE | TRUE
PM.Lisa | Jan.25 | 0 | 180 | TRUE | TRUE
PM.Lisa | Feb.25 | 0 | 180 | TRUE | TRUE
PM.Lisa | Mar.25 | 0 | 180 | TRUE | TRUE
PM.Lisa | Apr.25 | 0 | 180 | TRUE | TRUE
PM.Lisa | May.25 | 0 | 180 | TRUE | TRUE
PM.Lisa | Jun.25 | 0 | 180 | TRUE | TRUE
PM.Lisa | Jul.25 | 0 | 180 | TRUE | TRUE
PM.Lisa | Aug.25 | 0 | 180 | TRUE | TRUE
PM.Lisa | Sep.25 | 0 | 180 | TRUE | TRUE
PM.Lisa | Oct.25 | 0 | 180 | TRUE | TRUE
PM.Lisa | Nov.25 | 0 | 180 | TRUE | TRUE
PM.Lisa | Dec.25 | 0 | 180 | TRUE | TRUE
Note on E1: Valid expert?
Note on F1: Valid period?

## holiday
Date | TRUE
2025-01-01 | TRUE
2025-04-20 | TRUE
2025-05-01 | TRUE
Note on B1: Are dates OK?

## misc
Today | Hours per day | Solver | Last day
2024-12-30 | 8 | highs | 2025-12-11

## himg
Hours per day | Width | Height | Dpi | Start | End | Bar:color | Bar:hatch | Bar:alpha | Is Start OK? | Is End OK?
| 8 | 4 | 150 | 2024-12-31 | 2025-12-11 | #2ca02c | / | 0.3 | TRUE | TRUE

## timg
Tasks per day | Width | Height | Dpi | Start | End | Bar:color | Bar:hatch | Bar:alpha | Is Start OK? | Is End OK?
| 8 | 4 | 150 | 2024-12-31 | 2025-12-11 | #d62728 | \ | 0.3 | TRUE | TRUE

## simg
Hours per day stacked | Width | Height | Dpi | Start | End | Bar:alpha | Is Start OK? | Is End OK?
| 8 | 4 | 150 | 2024-12-31 | 2025-12-11 | 0.6 | TRUE | TRUE

## gimg
Task's Gantt Chart | Width | Height | Dpi | Barh:color | Barh:height | Barh:alpha
| 8 | 4 | 150 | #ff7f0e | 0.9 | 0.6

## wimg
Invoicing Periods Workload | Width | Height | Dpi | Bar:color | Bar:ecolor | Bar:capsize
| 8 | 4 | 150 | #7BC8F6 | #EE0000 | 4

## bimg
Task with bounds | Width | Height | Dpi | Fill:color | Fill:hatch | Fill:alpha | Plot:format | Plot:markeredgewidth | Step:linewidth
| 8 | 4 | 150 | #90EE90 | / | 0.2 | o | 0.5 | 0.5

## eimg
Experts per day stacked | Width | Height | Dpi | Bar:alpha
| 8 | 4 | 150 | 0.6