## expert
Name | Comment | TRUE
Alojzy | Main tasks p2.* | TRUE
Bartłomiej | Main tasks p3.* | TRUE
Franciszek | No main task | TRUE
Paweł | Main tasks p4.* | TRUE
Wojciech | Main tasks p5.* | TRUE
Note on C1: Has Expert any task?

## task
Name | Start | End | Work | TRUE | TRUE | TRUE
p2.m | 2024-12-05 | 2025-04-02 | 664 | TRUE | TRUE | TRUE
p2.f | 2025-04-03 | 2025-04-30 | 128 | TRUE | TRUE | TRUE
p2.pf | 2025-05-01 | 2025-05-13 | 64 | TRUE | TRUE | TRUE
p3.m | 2024-12-14 | 2025-05-30 | 636 | TRUE | TRUE | TRUE
p3.f | 2025-05-31 | 2025-06-27 | 96 | TRUE | TRUE | TRUE
p3.pf | 2025-06-28 | 2025-07-11 | 64 | TRUE | TRUE | TRUE
p4.m | 2025-01-04 | 2025-06-20 | 1130 | TRUE | TRUE | TRUE
p4.f | 2025-06-21 | 2025-07-18 | 160 | TRUE | TRUE | TRUE
p4.pf | 2025-07-19 | 2025-08-03 | 64 | TRUE | TRUE | TRUE
p5.m | 2025-01-14 | 2025-05-12 | 680 | TRUE | TRUE | TRUE
p5.f | 2025-05-13 | 2025-06-09 | 128 | TRUE | TRUE | TRUE
p5.pf | 2025-06-10 | 2025-06-23 | 64 | TRUE | TRUE | TRUE
p6.m | 2025-02-15 | 2025-08-01 | 1130 | TRUE | TRUE | TRUE
p6.f | 2025-08-02 | 2025-08-29 | 160 | TRUE | TRUE | TRUE
p6.pf | 2025-08-30 | 2025-09-12 | 64 | TRUE | TRUE | TRUE
Q1 | 2025-08-30 | 2025-09-12 | 1 | TRUE | TRUE | TRUE
Note on E1: Is task assign to an Expert?
Note on F1: Should task be included?
Note on G1: Are date OK?

## assign
Expert | Task | TRUE | TRUE
Alojzy | p2.m | TRUE | TRUE
Alojzy | p2.f | TRUE | TRUE
Alojzy | p2.pf | TRUE | TRUE
Bartłomiej | p3.m | TRUE | TRUE
Bartłomiej | p3.f | TRUE | TRUE
Bartłomiej | p3.pf | TRUE | TRUE
Paweł | p4.m | TRUE | TRUE
Paweł | p4.f | TRUE | TRUE
Paweł | p4.pf | TRUE | TRUE
Wojciech | p5.m | TRUE | TRUE
Wojciech | p5.f | TRUE | TRUE
Wojciech | p5.pf | TRUE | TRUE
Alojzy | p4.m | TRUE | TRUE
Bartłomiej | p4.m | TRUE | TRUE
Franciszek | p4.m | TRUE | TRUE
Wojciech | p4.m | TRUE | TRUE
Franciszek | p6.m | TRUE | TRUE
Franciszek | p6.f | TRUE | TRUE
Franciszek | p6.pf | TRUE | TRUE
Alojzy | p6.m | TRUE | TRUE
Bartłomiej | p6.m | TRUE | TRUE
Paweł | p6.m | TRUE | TRUE
Wojciech | p6.m | TRUE | TRUE
Franciszek | Q1 | TRUE | TRUE
Note on C1: Valid expert?
Note on D1: Valid task?

## xbday
Expert | Task | Start | End | Lower | Upper | TRUE | TRUE | TRUE
Alojzy | p2.m | 2024-12-05 | 2025-04-02 | 7 | 8 | TRUE | TRUE | TRUE
Alojzy | p2.f | 2025-04-03 | 2025-04-30 | 6 | 7 | TRUE | TRUE | TRUE
Alojzy | p2.pf | 2025-05-01 | 2025-05-13 | 7 | 8 | TRUE | TRUE | TRUE
Bartłomiej | p3.m | 2024-12-14 | 2025-05-30 | 4 | 8 | TRUE | TRUE | TRUE
Bartłomiej | p3.f | 2025-05-31 | 2025-06-27 | 4 | 5 | TRUE | TRUE | TRUE
Bartłomiej | p3.pf | 2025-06-28 | 2025-07-11 | 6 | 7 | TRUE | TRUE | TRUE
Paweł | p4.m | 2025-01-04 | 2025-06-20 | 8 | 8 | TRUE | TRUE | TRUE
Paweł | p4.f | 2025-06-21 | 2025-07-18 | 0 | 8 | TRUE | TRUE | TRUE
Paweł | p4.pf | 2025-07-19 | 2025-08-03 | 6 | 7 | TRUE | TRUE | TRUE
Wojciech | p5.m | 2025-01-14 | 2025-05-12 | 8 | 8 | TRUE | TRUE | TRUE
Wojciech | p5.f | 2025-05-13 | 2025-06-09 | 6 | 7 | TRUE | TRUE | TRUE
Wojciech | p5.pf | 2025-06-10 | 2025-06-23 | 6 | 7 | TRUE | TRUE | TRUE
Alojzy | p4.m | 2025-01-04 | 2025-06-20 | 0 | 8 | TRUE | TRUE | TRUE
Bartłomiej | p4.m | 2025-01-04 | 2025-06-20 | 0 | 8 | TRUE | TRUE | TRUE
Franciszek | p4.m | 2025-01-04 | 2025-06-20 | 0 | 8 | TRUE | TRUE | TRUE
Wojciech | p4.m | 2025-01-04 | 2025-06-20 | 0 | 8 | TRUE | TRUE | TRUE
Franciszek | p6.m | 2025-02-15 | 2025-08-01 | 8 | 8 | TRUE | TRUE | TRUE
Franciszek | p6.f | 2025-08-02 | 2025-08-29 | 8 | 8 | TRUE | TRUE | TRUE
Franciszek | p6.pf | 2025-08-30 | 2025-09-12 | 6 | 7 | TRUE | TRUE | TRUE
Alojzy | p6.m | 2025-02-15 | 2025-08-01 | 0 | 8 | TRUE | TRUE | TRUE
Bartłomiej | p6.m | 2025-02-15 | 2025-08-01 | 0 | 8 | TRUE | TRUE | TRUE
Paweł | p6.m | 2025-02-15 | 2025-08-01 | 0 | 8 | TRUE | TRUE | TRUE
Wojciech | p6.m | 2025-02-15 | 2025-08-01 | 0 | 8 | TRUE | TRUE | TRUE
Note on G1: Valid expert?
Note on H1: Valid task?
Note on I1: Are date OK?

## ubday
Expert | Start | End | Lower | Upper

## ebday
Expert | Start | End | Lower | Upper

## period
Name | Start | End | TRUE
25.Jan | 2024-12-11 | 2025-01-15 | TRUE
25.Feb | 2025-01-16 | 2025-02-13 | TRUE
25.Mar | 2025-02-14 | 2025-03-16 | TRUE
25.Apr | 2025-03-17 | 2025-04-14 | TRUE
25.May | 2025-04-15 | 2025-05-18 | TRUE
Note on D1: Are dates OK?

## pbsum
Expert | Period | Lower | Upper | TRUE | TRUE
Alojzy | 25.Jan | 0 | 200 | TRUE | TRUE
Alojzy | 25.Feb | 0 | 200 | TRUE | TRUE
Alojzy | 25.Mar | 0 | 200 | TRUE | TRUE
Alojzy | 25.Apr | 0 | 200 | TRUE | TRUE
Alojzy | 25.May | 0 | 200 | TRUE | TRUE
Bartłomiej | 25.Jan | 0 | 200 | TRUE | TRUE
Bartłomiej | 25.Feb | 0 | 200 | TRUE | TRUE
Bartłomiej | 25.Mar | 0 | 200 | TRUE | TRUE
Bartłomiej | 25.Apr | 0 | 200 | TRUE | TRUE
Bartłomiej | 25.May | 0 | 200 | TRUE | TRUE
Franciszek | 25.Jan | 0 | 200 | TRUE | TRUE
Franciszek | 25.Feb | 0 | 200 | TRUE | TRUE
Franciszek | 25.Mar | 0 | 200 | TRUE | TRUE
Franciszek | 25.Apr | 0 | 200 | TRUE | TRUE
Franciszek | 25.May | 0 | 200 | TRUE | TRUE
Paweł | 25.Jan | 0 | 200 | TRUE | TRUE
Paweł | 25.Feb | 0 | 200 | TRUE | TRUE
Paweł | 25.Mar | 0 | 200 | TRUE | TRUE
Paweł | 25.Apr | 0 | 200 | TRUE | TRUE
Paweł | 25.May | 0 | 200 | TRUE | TRUE
Wojciech | 25.Jan | 0 | 200 | TRUE | TRUE
Wojciech | 25.Feb | 0 | 200 | TRUE | TRUE
Wojciech | 25.Mar | 0 | 200 | TRUE | TRUE
Wojciech | 25.Apr | 0 | 200 | TRUE | TRUE
Wojciech | 25.May | 0 | 200 | TRUE | TRUE
Note on E1: Valid expert?
Note on F1: Valid period?

## holiday
Date | TRUE
2024-12-25 | TRUE
Note on B1: Are dates OK?

## misc
Today | Hours per day | Solver | Last day
2024-12-05 | 8 | scip | 2025-09-12

## himg
Hours per day | Width | Height | Dpi | Start | End | Bar:color | Bar:hatch | Bar:alpha | Is Start OK? | Is End OK?
| 8 | 4 | 150 | 2024-12-06 | 2025-01-25 | #2ca02c | / | 0.3 | TRUE | TRUE
Formulas:
End = [Start]+50

## timg
Tasks per day | Width | Height | Dpi | Start | End | Bar:color | Bar:hatch | Bar:alpha | Is Start OK? | Is End OK?
| 8 | 4 | 150 | 2024-12-06 | 2025-01-25 | #d62728 | \ | 0.3 | TRUE | TRUE
Formulas:
End = [Start]+50

## simg
Hours per day stacked | Width | Height | Dpi | Start | End | Bar:alpha | Is Start OK? | Is End OK?
| 8 | 4 | 150 | 2024-12-06 | 2025-01-25 | 0.6 | TRUE | TRUE
Formulas:
End = [Start]+50

## gimg
Task's Gantt Chart | Width | Height | Dpi | Barh:color | Barh:height | Barh:alpha
| 8 | 4 | 150 | #ff7f0e | 0.9 | 0.6

## wimg
Invoicing Periods Workload | Width | Height | Dpi | Bar:color | Bar:ecolor | Bar:capsize
| 8 | 4 | 150 | #7BC8F6 | #EE0000 | 4

## bimg
Task with bounds | Width | Height | Dpi | Fill:color | Fill:hatch | Fill:alpha | Plot:format | Plot:markeredgewidth | Step:linewidth
| 8 | 4 | 150 | #90EE90 | / | 0.2 | o | 0.5 | 0.5

## eimg
Experts per day stacked | Width | Height | Dpi | Bar:alpha
| 8 | 4 | 150 | 0.6