## expert
Name | Comment | TRUE
Żaneta | the unit alpha | TRUE
Ździsław | the unit alpha | TRUE
Zbigniew | the unit alpha | TRUE
Note on C1: Has Expert any task?

## task
Name | Start | End | Work | TRUE | TRUE
aaa | 2024-12-30 | 2025-01-10 | 72 | TRUE | TRUE
bbb | 2024-12-31 | 2025-01-13 | 72 | TRUE | TRUE
ccc | 2025-01-01 | 2025-01-14 | 72 | TRUE | TRUE
Note on E1: Is task assign to an Expert?
Note on F1: Should task be included?

## assign
Expert | Task | TRUE | TRUE
Żaneta | aaa | TRUE | TRUE
Ździsław | bbb | TRUE | TRUE
Zbigniew | ccc | TRUE | TRUE
Note on C1: Valid expert?
Note on D1: Valid task?

## xbday
Expert | Task | Start | End | Lower | Upper | #VALUE! | #VALUE!
Note on G1: Valid expert?
Note on H1: Valid task?

## ubday
Expert | Start | End | Lower | Upper

## ebday
Expert | Start | End | Lower | Upper

## period
Name | Start | End | TRUE
Jan.25 | 2024-12-11 | 2025-01-15 | TRUE
Feb.25 | 2025-01-16 | 2025-02-13 | TRUE

## pbsum
Expert | Period | Lower | Upper | TRUE | TRUE
Żaneta | Jan.25 | 0 | 180 | TRUE | TRUE
Żaneta | Feb.25 | 0 | 180 | TRUE | TRUE
Ździsław | Jan.25 | 0 | 180 | TRUE | TRUE
Ździsław | Feb.25 | 0 | 180 | TRUE | TRUE
Zbigniew | Jan.25 | 0 | 180 | TRUE | TRUE
Zbigniew | Feb.25 | 0 | 180 | TRUE | TRUE
Note on E1: Does Expert exist?
Note on F1: Valid period?

## holiday
Date | TRUE
2025-01-01 | TRUE
2025-01-04 | TRUE | It is Saturday
Note on B1: Are dates OK?

## misc
Today | Hours per day | Solver | Last day
2024-12-29 | 8 | gcg | 2025-02-13

## himg
Hours per day | Width | Height | Dpi | Start | End | Bar:color | Bar:hatch | Bar:alpha | Is Start OK? | Is End OK?
| 8 | 4 | 150 | 2024-12-30 | 2025-01-14 | #2ca02c | / | 0.3 | TRUE | TRUE

## timg
Tasks per day | Width | Height | Dpi | Start | End | Bar:color | Bar:hatch | Bar:alpha | Is Start OK? | Is End OK?
| 8 | 4 | 150 | 2024-12-30 | 2025-01-14 | #d62728 | \ | 0.3 | TRUE | TRUE

## simg
Hours per day stacked | Width | Height | Dpi | Start | End | Bar:alpha | Is Start OK? | Is End OK?
| 8 | 4 | 150 | 2024-12-30 | 2025-01-14 | 0.6 | TRUE | TRUE

## gimg
Task's Gantt Chart | Width | Height | Dpi | Barh:color | Barh:height | Barh:alpha
| 8 | 4 | 150 | #ff7f0e | 0.9 | 0.6

## wimg
Invoicing Periods Workload | Width | Height | Dpi | Bar:color | Bar:ecolor | Bar:capsize
| 8 | 4 | 150 | #7BC8F6 | #EE0000 | 4

## bimg
Task with bounds | Width | Height | Dpi | Fill:color | Fill:hatch | Fill:alpha | Plot:format | Plot:markeredgewidth | Step:linewidth
| 8 | 4 | 150 | #90EE90 | / | 0.2 | o | 0.5 | 0.5

## eimg
Experts per day stacked | Width | Height | Dpi | Bar:alpha
| 8 | 4 | 150 | 0.6