## expert
Name | Comment | TRUE
SA.Peter | the 2nd unit | 1
SA.Adrian | the 1st unit | 1
SA.Robert | the 1st unit | 1
SA.Kevin | the 2nd unit | 1
SA.Justin | the 2nd unit | 1
SA.Martha | the 2nd unit | 1
SA.Melanie | the 2nd unit | 1
Note on C1: Has Expert any task?

## task
Name | Start | End | Work | Days | Workdays | Avg[h/day] | Lower | Upper | TRUE | TRUE | TRUE
golf2.sm | 2025-01-01 | 2025-03-22 | 20 | 81 | 57 | 0.35088 | 0.25 | 0.5 | 1 | TRUE | TRUE
golf2.sf | 2025-03-23 | 2025-03-31 | 10 | 9 | 6 | 1.6667 | 1.5 | 1.75 | TRUE | TRUE | TRUE
tango2.se | 2025-02-01 | 2025-02-16 | 60 | 16 | 10 | 6 | 6 | 6.25 | TRUE | TRUE | TRUE
tango2.sm | 2025-02-17 | 2025-09-15 | 60 | 211 | 150 | 0.4 | 0.25 | 0.5 | TRUE | TRUE | TRUE
tango2.sf | 2025-09-16 | 2025-10-01 | 20 | 16 | 12 | 1.6667 | 1.5 | 1.75 | TRUE | TRUE | TRUE
victor2.se | 2025-02-15 | 2025-03-02 | 20 | 16 | 10 | 2 | 2 | 2.25 | TRUE | TRUE | TRUE
victor2.sm | 2025-03-03 | 2025-08-20 | 20 | 171 | 122 | 0.16393 | 0 | 0.25 | TRUE | TRUE | TRUE
victor2.sf | 2025-08-21 | 2025-09-01 | 10 | 12 | 8 | 1.25 | 1.25 | 1.5 | TRUE | TRUE | TRUE
alpha.sm | 2025-01-01 | 2025-04-01 | 10 | 91 | 64 | 0.15625 | 0 | 0.25 | TRUE | TRUE | TRUE
alpha.sf | 2025-04-02 | 2025-05-02 | 5 | 31 | 22 | 0.22727 | 0 | 0.25 | TRUE | TRUE | TRUE
beta.sm | 2025-01-01 | 2025-06-20 | 10 | 171 | 121 | 0.082645 | 0 | 0.25 | TRUE | TRUE | TRUE
beta.sf | 2025-06-21 | 2025-08-05 | 5 | 46 | 32 | 0.15625 | 0 | 0.25 | TRUE | TRUE | TRUE
charlie.sm | 2025-01-01 | 2025-06-05 | 15 | 156 | 110 | 0.13636 | 0 | 0.25 | TRUE | TRUE | TRUE
charlie.sf | 2025-06-06 | 2025-07-06 | 5 | 31 | 21 | 0.2381 | 0 | 0.25 | TRUE | TRUE | TRUE
delta.sm | 2025-01-01 | 2025-02-25 | 5 | 56 | 39 | 0.12821 | 0 | 0.25 | TRUE | TRUE | TRUE
delta.sf | 2025-02-26 | 2025-04-12 | 5 | 46 | 33 | 0.15152 | 0 | 0.25 | TRUE | TRUE | TRUE
echo.sm | 2025-01-01 | 2025-03-15 | 5 | 74 | 52 | 0.096154 | 0 | 0.25 | TRUE | TRUE | TRUE
echo.sf | 2025-04-02 | 2025-05-17 | 8 | 46 | 32 | 0.25 | 0.25 | 0.5 | TRUE | TRUE | TRUE
golf.sm | 2025-01-01 | 2025-05-12 | 10 | 132 | 92 | 0.1087 | 0 | 0.25 | TRUE | TRUE | TRUE
golf.sf | 2025-05-13 | 2025-06-27 | 8 | 46 | 34 | 0.23529 | 0 | 0.25 | TRUE | TRUE | TRUE
kilo.se | 2025-03-01 | 2025-03-24 | 15 | 24 | 16 | 0.9375 | 0.75 | 1 | TRUE | TRUE | TRUE
kilo.sm | 2025-03-25 | 2025-08-01 | 10 | 130 | 93 | 0.10753 | 0 | 0.25 | TRUE | TRUE | TRUE
kilo.sf | 2025-08-02 | 2025-09-16 | 5 | 46 | 32 | 0.15625 | 0 | 0.25 | TRUE | TRUE | TRUE
lima.se | 2025-03-21 | 2025-04-19 | 36 | 30 | 21 | 1.7143 | 1.5 | 1.75 | TRUE | TRUE | TRUE
lima.sm | 2025-04-20 | 2025-11-01 | 10 | 196 | 139 | 0.071942 | 0 | 0.25 | TRUE | TRUE | TRUE
lima.sf | 2025-11-02 | 2025-11-30 | 5 | 29 | 20 | 0.25 | 0.25 | 0.5 | TRUE | TRUE | TRUE
mike.se | 2025-03-21 | 2025-04-19 | 15 | 30 | 21 | 0.71429 | 0.5 | 0.75 | TRUE | TRUE | TRUE
mike.sm | 2025-04-20 | 2025-11-01 | 10 | 196 | 139 | 0.071942 | 0 | 0.25 | TRUE | TRUE | TRUE
mike.sf | 2025-11-02 | 2025-11-30 | 5 | 29 | 20 | 0.25 | 0.25 | 0.5 | TRUE | TRUE | TRUE
foxtrot.sm | 2025-01-01 | 2025-04-01 | 8 | 91 | 64 | 0.125 | 0 | 0.25 | TRUE | TRUE | TRUE
foxtrot.sf | 2025-04-02 | 2025-05-02 | 8 | 31 | 22 | 0.36364 | 0.25 | 0.5 | TRUE | TRUE | TRUE
hotel.sm | 2025-01-01 | 2025-09-01 | 15 | 244 | 172 | 0.087209 | 0 | 0.25 | TRUE | TRUE | TRUE
hotel.sf | 2025-09-02 | 2025-10-17 | 5 | 46 | 34 | 0.14706 | 0 | 0.25 | TRUE | TRUE | TRUE
india.sm | 2025-01-01 | 2025-10-01 | 30 | 274 | 194 | 0.15464 | 0 | 0.25 | TRUE | TRUE | TRUE
india.sf | 2025-10-02 | 2025-11-01 | 12 | 31 | 22 | 0.54545 | 0.5 | 0.75 | TRUE | TRUE | TRUE
juliet.se | 2025-02-10 | 2025-02-27 | 10 | 18 | 14 | 0.71429 | 0.5 | 0.75 | TRUE | TRUE | TRUE
juliet.sm | 2025-02-28 | 2025-06-30 | 10 | 123 | 86 | 0.11628 | 0 | 0.25 | TRUE | TRUE | TRUE
juliet.sf | 2025-07-01 | 2025-08-15 | 5 | 46 | 34 | 0.14706 | 0 | 0.25 | TRUE | TRUE | TRUE
november.se | 2025-05-26 | 2025-06-14 | 10 | 20 | 15 | 0.66667 | 0.5 | 0.75 | TRUE | TRUE | TRUE
november.sm | 2025-06-15 | 2025-12-30 | 10 | 199 | 142 | 0.070423 | 0 | 0.25 | TRUE | TRUE | TRUE
november.sf | 2025-12-31 | 2026-01-31 | 5 | 32 | 23 | 0.21739 | 0 | 0.25 | TRUE | TRUE | TRUE
oscar.se | 2025-06-25 | 2025-07-09 | 10 | 15 | 11 | 0.90909 | 0.75 | 1 | TRUE | TRUE | TRUE
oscar.sm | 2025-07-10 | 2025-12-30 | 10 | 174 | 124 | 0.080645 | 0 | 0.25 | TRUE | TRUE | TRUE
oscar.sf | 2025-12-31 | 2026-01-31 | 8 | 32 | 23 | 0.34783 | 0.25 | 0.5 | TRUE | TRUE | TRUE
alpha2.se | 2025-01-27 | 2025-02-01 | 12 | 6 | 5 | 2.4 | 2.25 | 2.5 | TRUE | TRUE | TRUE
alpha2.sm | 2025-02-02 | 2025-03-19 | 24 | 46 | 33 | 0.72727 | 0.5 | 0.75 | TRUE | TRUE | TRUE
alpha2.sf | 2025-03-20 | 2025-04-01 | 8 | 13 | 9 | 0.88889 | 0.75 | 1 | TRUE | TRUE | TRUE
beta2.se | 2025-01-05 | 2025-01-15 | 30 | 11 | 8 | 3.75 | 3.75 | 4 | TRUE | TRUE | TRUE
beta2.sm | 2025-01-16 | 2025-07-15 | 60 | 181 | 128 | 0.46875 | 0.25 | 0.5 | TRUE | TRUE | TRUE
beta2.sf | 2025-07-16 | 2025-08-04 | 40 | 20 | 14 | 2.8571 | 2.75 | 3 | TRUE | TRUE | TRUE
gamma2.sm | 2025-01-01 | 2025-01-21 | 15 | 21 | 14 | 1.0714 | 1 | 1.25 | TRUE | TRUE | TRUE
gamma2.sf | 2025-01-22 | 2025-02-03 | 5 | 13 | 9 | 0.55556 | 0.5 | 0.75 | TRUE | TRUE | TRUE
quebec2.se | 2025-06-01 | 2025-06-26 | 40 | 26 | 19 | 2.1053 | 2 | 2.25 | TRUE | TRUE | TRUE
quebec2.sm | 2025-06-27 | 2026-11-09 | 20 | 501 | 357 | 0.056022 | 0 | 0.25 | TRUE | TRUE | TRUE
quebec2.sf | 2026-11-10 | 2027-01-04 | 20 | 56 | 40 | 0.5 | 0.5 | 0.75 | TRUE | TRUE | TRUE
uniform2.se | 2025-05-01 | 2025-05-16 | 60 | 16 | 11 | 5.4545 | 5.25 | 5.5 | TRUE | TRUE | TRUE
uniform2.sm | 2025-05-17 | 2026-02-11 | 50 | 271 | 193 | 0.25907 | 0.25 | 0.5 | TRUE | TRUE | TRUE
uniform2.sf | 2026-02-12 | 2026-03-02 | 20 | 19 | 13 | 1.5385 | 1.5 | 1.75 | TRUE | TRUE | TRUE
xray2.se | 2025-07-15 | 2025-08-09 | 20 | 26 | 19 | 1.0526 | 1 | 1.25 | TRUE | TRUE | TRUE
xray2.sm | 2025-08-10 | 2026-01-07 | 30 | 151 | 108 | 0.27778 | 0.25 | 0.5 | TRUE | TRUE | TRUE
xray2.sf | 2026-01-08 | 2026-02-01 | 20 | 25 | 17 | 1.1765 | 1 | 1.25 | TRUE | TRUE | TRUE
india2.sm | 2025-01-01 | 2025-03-17 | 10 | 76 | 53 | 0.18868 | 0 | 0.25 | TRUE | TRUE | TRUE
india2.sf | 2025-03-18 | 2025-03-25 | 10 | 8 | 6 | 1.6667 | 1.5 | 1.75 | TRUE | TRUE | TRUE
juliet2.sm | 2025-01-01 | 2025-03-22 | 20 | 81 | 57 | 0.35088 | 0.25 | 0.5 | TRUE | TRUE | TRUE
juliet2.sf | 2025-03-23 | 2025-04-01 | 15 | 10 | 7 | 2.1429 | 2 | 2.25 | TRUE | TRUE | TRUE
lima2.sm | 2025-01-01 | 2025-02-25 | 10 | 56 | 39 | 0.25641 | 0.25 | 0.5 | TRUE | TRUE | TRUE
lima2.sf | 2025-02-26 | 2025-03-03 | 10 | 6 | 4 | 2.5 | 2.5 | 2.75 | TRUE | TRUE | TRUE
kilo2.sm | 2025-01-01 | 2025-02-25 | 15 | 56 | 39 | 0.38462 | 0.25 | 0.5 | TRUE | TRUE | TRUE
kilo2.sf | 2025-02-26 | 2025-03-03 | 10 | 6 | 4 | 2.5 | 2.5 | 2.75 | TRUE | TRUE | TRUE
november2.sm | 2025-01-01 | 2025-03-27 | 30 | 86 | 61 | 0.4918 | 0.25 | 0.5 | TRUE | TRUE | TRUE
november2.sf | 2025-03-28 | 2025-04-07 | 15 | 11 | 7 | 2.1429 | 2 | 2.25 | TRUE | TRUE | TRUE
oscar2.sm | 2025-01-01 | 2025-06-20 | 30 | 171 | 121 | 0.24793 | 0 | 0.25 | TRUE | TRUE | TRUE
oscar2.sf | 2025-06-21 | 2025-06-30 | 10 | 10 | 6 | 1.6667 | 1.5 | 1.75 | TRUE | TRUE | TRUE
papa2.sm | 2025-01-01 | 2025-06-20 | 40 | 171 | 121 | 0.33058 | 0.25 | 0.5 | TRUE | TRUE | TRUE
papa2.sf | 2025-06-21 | 2025-06-30 | 15 | 10 | 6 | 2.5 | 2.5 | 2.75 | TRUE | TRUE | TRUE
zulu2.se | 2025-06-15 | 2025-07-15 | 50 | 31 | 22 | 2.2727 | 2.25 | 2.5 | TRUE | TRUE | TRUE
zulu2.sm | 2025-07-16 | 2025-11-23 | 20 | 131 | 93 | 0.21505 | 0 | 0.25 | TRUE | TRUE | TRUE
zulu2.sf | 2025-11-24 | 2025-12-01 | 10 | 8 | 6 | 1.6667 | 1.5 | 1.75 | TRUE | TRUE | TRUE
delta2.sm | 2025-01-01 | 2025-06-20 | 20 | 171 | 121 | 0.16529 | 0 | 0.25 | TRUE | TRUE | TRUE
delta2.sf | 2025-06-21 | 2025-07-01 | 10 | 11 | 7 | 1.4286 | 1.25 | 1.5 | TRUE | TRUE | TRUE
echo2.sm | 2025-01-01 | 2025-01-21 | 10 | 21 | 14 | 0.71429 | 0.5 | 0.75 | TRUE | TRUE | TRUE
echo2.sf | 2025-01-22 | 2025-03-10 | 5 | 48 | 34 | 0.14706 | 0 | 0.25 | TRUE | TRUE | TRUE
foxtrot2.sm | 2025-01-01 | 2025-03-22 | 50 | 81 | 57 | 0.87719 | 0.75 | 1 | TRUE | TRUE | TRUE
foxtrot2.sf | 2025-03-23 | 2025-04-01 | 30 | 10 | 7 | 4.2857 | 4.25 | 4.5 | TRUE | TRUE | TRUE
hotel2.sm | 2025-01-01 | 2025-02-15 | 10 | 46 | 32 | 0.3125 | 0.25 | 0.5 | TRUE | TRUE | TRUE
hotel2.sf | 2025-02-16 | 2025-02-25 | 5 | 10 | 7 | 0.71429 | 0.5 | 0.75 | TRUE | TRUE | TRUE
mike2.se | 2025-01-10 | 2025-01-25 | 40 | 16 | 11 | 3.6364 | 3.5 | 3.75 | TRUE | TRUE | TRUE
mike2.sm | 2025-01-26 | 2025-05-16 | 20 | 111 | 79 | 0.25316 | 0.25 | 0.5 | TRUE | TRUE | TRUE
mike2.sf | 2025-05-17 | 2025-06-01 | 10 | 16 | 10 | 1 | 1 | 1.25 | TRUE | TRUE | TRUE
Note on J1: Is task assign to an Expert?
Note on K1: Should task be included?
Note on L1: Are date OK?

## assign
Expert | Task | TRUE | TRUE
SA.Peter | golf2.sf | 1 | 1
SA.Peter | golf2.sm | 1 | 1
SA.Peter | tango2.se | 1 | 1
SA.Peter | tango2.sf | 1 | 1
SA.Peter | tango2.sm | 1 | 1
SA.Peter | victor2.se | 1 | 1
SA.Peter | victor2.sf | 1 | 1
SA.Peter | victor2.sm | 1 | 1
SA.Adrian | alpha.sf | 1 | 1
SA.Adrian | alpha.sm | 1 | 1
SA.Adrian | beta.sf | 1 | 1
SA.Adrian | beta.sm | 1 | 1
SA.Adrian | charlie.sf | 1 | 1
SA.Adrian | charlie.sm | 1 | 1
SA.Adrian | delta.sf | 1 | 1
SA.Adrian | delta.sm | 1 | 1
SA.Adrian | echo.sf | 1 | 1
SA.Adrian | echo.sm | 1 | 1
SA.Adrian | golf.sf | 1 | 1
SA.Adrian | golf.sm | 1 | 1
SA.Adrian | kilo.se | 1 | 1
SA.Adrian | kilo.sf | 1 | 1
SA.Adrian | kilo.sm | 1 | 1
SA.Adrian | lima.se | 1 | 1
SA.Adrian | lima.sf | 1 | 1
SA.Adrian | lima.sm | 1 | 1
SA.Adrian | mike.se | 1 | 1
SA.Adrian | mike.sf | 1 | 1
SA.Adrian | mike.sm | 1 | 1
SA.Robert | foxtrot.sf | 1 | 1
SA.Robert | foxtrot.sm | 1 | 1
SA.Robert | hotel.sf | 1 | 1
SA.Robert | hotel.sm | 1 | 1
SA.Robert | india.sf | 1 | 1
SA.Robert | india.sm | 1 | 1
SA.Robert | juliet.se | 1 | 1
SA.Robert | juliet.sf | 1 | 1
SA.Robert | juliet.sm | 1 | 1
SA.Robert | november.se | 1 | 1
SA.Robert | november.sf | 1 | 1
SA.Robert | november.sm | 1 | 1
SA.Robert | oscar.se | 1 | 1
SA.Robert | oscar.sf | 1 | 1
SA.Robert | oscar.sm | 1 | 1
SA.Kevin | alpha2.se | 1 | 1
SA.Kevin | alpha2.sf | 1 | 1
SA.Kevin | alpha2.sm | 1 | 1
SA.Kevin | beta2.se | 1 | 1
SA.Kevin | beta2.sf | 1 | 1
SA.Kevin | beta2.sm | 1 | 1
SA.Kevin | gamma2.sf | 1 | 1
SA.Kevin | gamma2.sm | 1 | 1
SA.Kevin | quebec2.se | 1 | 1
SA.Kevin | quebec2.sf | 1 | 1
SA.Kevin | quebec2.sm | 1 | 1
SA.Kevin | uniform2.se | 1 | 1
SA.Kevin | uniform2.sf | 1 | 1
SA.Kevin | uniform2.sm | 1 | 1
SA.Kevin | xray2.se | 1 | 1
SA.Kevin | xray2.sf | 1 | 1
SA.Kevin | xray2.sm | 1 | 1
SA.Justin | india2.sf | 1 | 1
SA.Justin | india2.sm | 1 | 1
SA.Justin | juliet2.sf | 1 | 1
SA.Justin | juliet2.sm | 1 | 1
SA.Justin | lima2.sf | 1 | 1
SA.Justin | lima2.sm | 1 | 1
SA.Martha | kilo2.sf | 1 | 1
SA.Martha | kilo2.sm | 1 | 1
SA.Martha | november2.sf | 1 | 1
SA.Martha | november2.sm | 1 | 1
SA.Martha | oscar2.sf | 1 | 1
SA.Martha | oscar2.sm | 1 | 1
SA.Martha | papa2.sf | 1 | 1
SA.Martha | papa2.sm | 1 | 1
SA.Martha | zulu2.se | 1 | 1
SA.Martha | zulu2.sf | 1 | 1
SA.Martha | zulu2.sm | 1 | 1
SA.Melanie | delta2.sf | 1 | 1
SA.Melanie | delta2.sm | 1 | 1
SA.Melanie | echo2.sf | 1 | 1
SA.Melanie | echo2.sm | 1 | 1
SA.Melanie | foxtrot2.sf | 1 | 1
SA.Melanie | foxtrot2.sm | 1 | 1
SA.Melanie | hotel2.sf | 1 | 1
SA.Melanie | hotel2.sm | 1 | 1
SA.Melanie | mike2.se | 1 | 1
SA.Melanie | mike2.sf | 1 | 1
SA.Melanie | mike2.sm | 1 | 1
Note on C1: Valid expert?
Note on D1: Valid task?

## xbday
Expert | Task | Start | End | Lower | Upper | TRUE | TRUE | TRUE
SA.Peter | golf2.sm | 2025-01-01 | 2025-03-22 | 0.25 | 0.5 | TRUE | TRUE | TRUE
SA.Peter | golf2.sf | 2025-03-23 | 2025-03-31 | 1.5 | 1.75 | TRUE | TRUE | TRUE
SA.Peter | tango2.se | 2025-02-01 | 2025-02-16 | 6 | 6.25 | TRUE | TRUE | TRUE
SA.Peter | tango2.sm | 2025-02-17 | 2025-09-15 | 0.25 | 0.5 | TRUE | TRUE | TRUE
SA.Peter | tango2.sf | 2025-09-16 | 2025-10-01 | 1.5 | 1.75 | TRUE | TRUE | TRUE
SA.Peter | victor2.se | 2025-02-15 | 2025-03-02 | 2 | 2.25 | TRUE | TRUE | TRUE
SA.Peter | victor2.sm | 2025-03-03 | 2025-08-20 | 0 | 0.25 | TRUE | TRUE | TRUE
SA.Peter | victor2.sf | 2025-08-21 | 2025-09-01 | 1.25 | 1.5 | TRUE | TRUE | TRUE
SA.Adrian | alpha.sm | 2025-01-01 | 2025-04-01 | 0 | 0.25 | TRUE | TRUE | TRUE
SA.Adrian | alpha.sf | 2025-04-02 | 2025-05-02 | 0 | 0.25 | TRUE | TRUE | TRUE
SA.Adrian | beta.sm | 2025-01-01 | 2025-06-20 | 0 | 0.25 | TRUE | TRUE | TRUE
SA.Adrian | beta.sf | 2025-06-21 | 2025-08-05 | 0 | 0.25 | TRUE | TRUE | TRUE
SA.Adrian | charlie.sm | 2025-01-01 | 2025-06-05 | 0 | 0.25 | TRUE | TRUE | TRUE
SA.Adrian | charlie.sf | 2025-06-06 | 2025-07-06 | 0 | 0.25 | TRUE | TRUE | TRUE
SA.Adrian | delta.sm | 2025-01-01 | 2025-02-25 | 0 | 0.25 | TRUE | TRUE | TRUE
SA.Adrian | delta.sf | 2025-02-26 | 2025-04-12 | 0 | 0.25 | TRUE | TRUE | TRUE
SA.Adrian | echo.sm | 2025-01-01 | 2025-03-15 | 0 | 0.25 | TRUE | TRUE | TRUE
SA.Adrian | echo.sf | 2025-04-02 | 2025-05-17 | 0.25 | 0.5 | TRUE | TRUE | TRUE
SA.Adrian | golf.sm | 2025-01-01 | 2025-05-12 | 0 | 0.25 | TRUE | TRUE | TRUE
SA.Adrian | golf.sf | 2025-05-13 | 2025-06-27 | 0 | 0.25 | TRUE | TRUE | TRUE
SA.Adrian | kilo.se | 2025-03-01 | 2025-03-24 | 0.75 | 1 | TRUE | TRUE | TRUE
SA.Adrian | kilo.sm | 2025-03-25 | 2025-08-01 | 0 | 0.25 | TRUE | TRUE | TRUE
SA.Adrian | kilo.sf | 2025-08-02 | 2025-09-16 | 0 | 0.25 | TRUE | TRUE | TRUE
SA.Adrian | lima.se | 2025-03-21 | 2025-04-19 | 1.5 | 1.75 | TRUE | TRUE | TRUE
SA.Adrian | lima.sm | 2025-04-20 | 2025-11-01 | 0 | 0.25 | TRUE | TRUE | TRUE
SA.Adrian | lima.sf | 2025-11-02 | 2025-11-30 | 0.25 | 0.5 | TRUE | TRUE | TRUE
SA.Adrian | mike.se | 2025-03-21 | 2025-04-19 | 0.5 | 0.75 | TRUE | TRUE | TRUE
SA.Adrian | mike.sm | 2025-04-20 | 2025-11-01 | 0 | 0.25 | TRUE | TRUE | TRUE
SA.Adrian | mike.sf | 2025-11-02 | 2025-11-30 | 0.25 | 0.5 | TRUE | TRUE | TRUE
SA.Robert | foxtrot.sm | 2025-01-01 | 2025-04-01 | 0 | 0.25 | TRUE | TRUE | TRUE
SA.Robert | foxtrot.sf | 2025-04-02 | 2025-05-02 | 0.25 | 0.5 | TRUE | TRUE | TRUE
SA.Robert | hotel.sm | 2025-01-01 | 2025-09-01 | 0 | 0.25 | TRUE | TRUE | TRUE
SA.Robert | hotel.sf | 2025-09-02 | 2025-10-17 | 0 | 0.25 | TRUE | TRUE | TRUE
SA.Robert | india.sm | 2025-01-01 | 2025-10-01 | 0 | 0.25 | TRUE | TRUE | TRUE
SA.Robert | india.sf | 2025-10-02 | 2025-11-01 | 0.5 | 0.75 | TRUE | TRUE | TRUE
SA.Robert | juliet.se | 2025-02-10 | 2025-02-27 | 0.5 | 0.75 | TRUE | TRUE | TRUE
SA.Robert | juliet.sm | 2025-02-28 | 2025-06-30 | 0 | 0.25 | TRUE | TRUE | TRUE
SA.Robert | juliet.sf | 2025-07-01 | 2025-08-15 | 0 | 0.25 | TRUE | TRUE | TRUE
SA.Robert | november.se | 2025-05-26 | 2025-06-14 | 0.5 | 0.75 | TRUE | TRUE | TRUE
SA.Robert | november.sm | 2025-06-15 | 2025-12-30 | 0 | 0.25 | TRUE | TRUE | TRUE
SA.Robert | november.sf | 2025-12-31 | 2026-01-31 | 0 | 0.25 | TRUE | TRUE | TRUE
SA.Robert | oscar.se | 2025-06-25 | 2025-07-09 | 0.75 | 1 | TRUE | TRUE | TRUE
SA.Robert | oscar.sm | 2025-07-10 | 2025-12-30 | 0 | 0.25 | TRUE | TRUE | TRUE
SA.Robert | oscar.sf | 2025-12-31 | 2026-01-31 | 0.25 | 0.5 | TRUE | TRUE | TRUE
SA.Kevin | alpha2.se | 2025-01-27 | 2025-02-01 | 2.25 | 2.5 | TRUE | TRUE | TRUE
SA.Kevin | alpha2.sm | 2025-02-02 | 2025-03-19 | 0.5 | 0.75 | TRUE | TRUE | TRUE
SA.Kevin | alpha2.sf | 2025-03-20 | 2025-04-01 | 0.75 | 1 | TRUE | TRUE | TRUE
SA.Kevin | beta2.se | 2025-01-05 | 2025-01-15 | 3.75 | 4 | TRUE | TRUE | TRUE
SA.Kevin | beta2.sm | 2025-01-16 | 2025-07-15 | 0.25 | 0.5 | TRUE | TRUE | TRUE
SA.Kevin | beta2.sf | 2025-07-16 | 2025-08-04 | 2.75 | 3 | TRUE | TRUE | TRUE
SA.Kevin | gamma2.sm | 2025-01-01 | 2025-01-21 | 1 | 1.25 | TRUE | TRUE | TRUE
SA.Kevin | gamma2.sf | 2025-01-22 | 2025-02-03 | 0.5 | 0.75 | TRUE | TRUE | TRUE
SA.Kevin | quebec2.se | 2025-06-01 | 2025-06-26 | 2 | 2.25 | TRUE | TRUE | TRUE
SA.Kevin | quebec2.sm | 2025-06-27 | 2026-11-09 | 0 | 0.25 | TRUE | TRUE | TRUE
SA.Kevin | quebec2.sf | 2026-11-10 | 2027-01-04 | 0.5 | 0.75 | TRUE | TRUE | TRUE
SA.Kevin | uniform2.se | 2025-05-01 | 2025-05-16 | 5.25 | 5.5 | TRUE | TRUE | TRUE
SA.Kevin | uniform2.sm | 2025-05-17 | 2026-02-11 | 0.25 | 0.5 | TRUE | TRUE | TRUE
SA.Kevin | uniform2.sf | 2026-02-12 | 2026-03-02 | 1.5 | 1.75 | TRUE | TRUE | TRUE
SA.Kevin | xray2.se | 2025-07-15 | 2025-08-09 | 1 | 1.25 | TRUE | TRUE | TRUE
SA.Kevin | xray2.sm | 2025-08-10 | 2026-01-07 | 0.25 | 0.5 | TRUE | TRUE | TRUE
SA.Kevin | xray2.sf | 2026-01-08 | 2026-02-01 | 1 | 1.25 | TRUE | TRUE | TRUE
SA.Justin | india2.sm | 2025-01-01 | 2025-03-17 | 0 | 0.25 | TRUE | TRUE | TRUE
SA.Justin | india2.sf | 2025-03-18 | 2025-03-25 | 1.5 | 1.75 | TRUE | TRUE | TRUE
SA.Justin | juliet2.sm | 2025-01-01 | 2025-03-22 | 0.25 | 0.5 | TRUE | TRUE | TRUE
SA.Justin | juliet2.sf | 2025-03-23 | 2025-04-01 | 2 | 2.25 | TRUE | TRUE | TRUE
SA.Justin | lima2.sm | 2025-01-01 | 2025-02-25 | 0.25 | 0.5 | TRUE | TRUE | TRUE
SA.Justin | lima2.sf | 2025-02-26 | 2025-03-03 | 2.5 | 2.75 | TRUE | TRUE | TRUE
SA.Martha | kilo2.sm | 2025-01-01 | 2025-02-25 | 0.25 | 0.5 | TRUE | TRUE | TRUE
SA.Martha | kilo2.sf | 2025-02-26 | 2025-03-03 | 2.5 | 2.75 | TRUE | TRUE | TRUE
SA.Martha | november2.sm | 2025-01-01 | 2025-03-27 | 0.25 | 0.5 | TRUE | TRUE | TRUE
SA.Martha | november2.sf | 2025-03-28 | 2025-04-07 | 2 | 2.25 | TRUE | TRUE | TRUE
SA.Martha | oscar2.sm | 2025-01-01 | 2025-06-20 | 0 | 0.25 | TRUE | TRUE | TRUE
SA.Martha | oscar2.sf | 2025-06-21 | 2025-06-30 | 1.5 | 1.75 | TRUE | TRUE | TRUE
SA.Martha | papa2.sm | 2025-01-01 | 2025-06-20 | 0.25 | 0.5 | TRUE | TRUE | TRUE
SA.Martha | papa2.sf | 2025-06-21 | 2025-06-30 | 2.5 | 2.75 | TRUE | TRUE | TRUE
SA.Martha | zulu2.se | 2025-06-15 | 2025-07-15 | 2.25 | 2.5 | TRUE | TRUE | TRUE
SA.Martha | zulu2.sm | 2025-07-16 | 2025-11-23 | 0 | 0.25 | TRUE | TRUE | TRUE
SA.Martha | zulu2.sf | 2025-11-24 | 2025-12-01 | 1.5 | 1.75 | TRUE | TRUE | TRUE
SA.Melanie | delta2.sm | 2025-01-01 | 2025-06-20 | 0 | 0.25 | TRUE | TRUE | TRUE
SA.Melanie | delta2.sf | 2025-06-21 | 2025-07-01 | 1.25 | 1.5 | TRUE | TRUE | TRUE
SA.Melanie | echo2.sm | 2025-01-01 | 2025-01-21 | 0.5 | 0.75 | TRUE | TRUE | TRUE
SA.Melanie | echo2.sf | 2025-01-22 | 2025-03-10 | 0 | 0.25 | TRUE | TRUE | TRUE
SA.Melanie | foxtrot2.sm | 2025-01-01 | 2025-03-22 | 0.75 | 1 | TRUE | TRUE | TRUE
SA.Melanie | foxtrot2.sf | 2025-03-23 | 2025-04-01 | 4.25 | 4.5 | TRUE | TRUE | TRUE
SA.Melanie | hotel2.sm | 2025-01-01 | 2025-02-15 | 0.25 | 0.5 | TRUE | TRUE | TRUE
SA.Melanie | hotel2.sf | 2025-02-16 | 2025-02-25 | 0.5 | 0.75 | TRUE | TRUE | TRUE
SA.Melanie | mike2.se | 2025-01-10 | 2025-01-25 | 3.5 | 3.75 | TRUE | TRUE | TRUE
SA.Melanie | mike2.sm | 2025-01-26 | 2025-05-16 | 0.25 | 0.5 | TRUE | TRUE | TRUE
SA.Melanie | mike2.sf | 2025-05-17 | 2025-06-01 | 1 | 1.25 | TRUE | TRUE | TRUE
Note on G1: Valid expert?
Note on H1: Valid task?
Note on I1: Are date OK?

## ubday
Expert | Start | End | Lower | Upper

## ebday
Expert | Start | End | Lower | Upper

## period
Name | Start | End | TRUE
Jan.25 | 2024-12-11 | 2025-01-15 | TRUE
Feb.25 | 2025-01-16 | 2025-02-13 | TRUE
Mar.25 | 2025-02-14 | 2025-03-16 | TRUE
Apr.25 | 2025-03-17 | 2025-04-14 | TRUE
May.25 | 2025-04-15 | 2025-05-18 | TRUE
Jun.25 | 2025-05-19 | 2025-06-18 | TRUE
Jul.25 | 2025-06-19 | 2025-07-17 | TRUE
Aug.25 | 2025-07-18 | 2025-08-17 | TRUE
Sep.25 | 2025-08-18 | 2025-09-15 | TRUE
Oct.25 | 2025-09-16 | 2025-10-15 | TRUE
Nov.25 | 2025-10-16 | 2025-11-12 | TRUE
Dec.25 | 2025-11-13 | 2025-12-11 | TRUE
Note on D1: Are dates OK?

## pbsum
Expert | Period | Lower | Upper | TRUE | TRUE
SA.Peter | Jan.25 | 0 | 180 | TRUE | TRUE
SA.Peter | Feb.25 | 0 | 180 | TRUE | TRUE
SA.Peter | Mar.25 | 0 | 180 | TRUE | TRUE
SA.Peter | Apr.25 | 0 | 180 | TRUE | TRUE
SA.Peter | May.25 | 0 | 180 | TRUE | TRUE
SA.Peter | Jun.25 | 0 | 180 | TRUE | TRUE
SA.Peter | Jul.25 | 0 | 180 | TRUE | TRUE
SA.Peter | Aug.25 | 0 | 180 | TRUE | TRUE
SA.Peter | Sep.25 | 0 | 180 | TRUE | TRUE
SA.Peter | Oct.25 | 0 | 180 | TRUE | TRUE
SA.Peter | Nov.25 | 0 | 180 | TRUE | TRUE
SA.Peter | Dec.25 | 0 | 180 | TRUE | TRUE
SA.Adrian | Jan.25 | 0 | 180 | TRUE | TRUE
SA.Adrian | Feb.25 | 0 | 180 | TRUE | TRUE
SA.Adrian | Mar.25 | 0 | 180 | TRUE | TRUE
SA.Adrian | Apr.25 | 0 | 180 | TRUE | TRUE
SA.Adrian | May.25 | 0 | 180 | TRUE | TRUE
SA.Adrian | Jun.25 | 0 | 180 | TRUE | TRUE
SA.Adrian | Jul.25 | 0 | 180 | TRUE | TRUE
SA.Adrian | Aug.25 | 0 | 180 | TRUE | TRUE
SA.Adrian | Sep.25 | 0 | 180 | TRUE | TRUE
SA.Adrian | Oct.25 | 0 | 180 | TRUE | TRUE
SA.Adrian | Nov.25 | 0 | 180 | TRUE | TRUE
SA.Adrian | Dec.25 | 0 | 180 | TRUE | TRUE
SA.Robert | Jan.25 | 0 | 180 | TRUE | TRUE
SA.Robert | Feb.25 | 0 | 180 | TRUE | TRUE
SA.Robert | Mar.25 | 0 | 180 | TRUE | TRUE
SA.Robert | Apr.25 | 0 | 180 | TRUE | TRUE
SA.Robert | May.25 | 0 | 180 | TRUE | TRUE
SA.Robert | Jun.25 | 0 | 180 | TRUE | TRUE
SA.Robert | Jul.25 | 0 | 180 | TRUE | TRUE
SA.Robert | Aug.25 | 0 | 180 | TRUE | TRUE
SA.Robert | Sep.25 | 0 | 180 | TRUE | TRUE
SA.Robert | Oct.25 | 0 | 180 | TRUE | TRUE
SA.Robert | Nov.25 | 0 | 180 | TRUE | TRUE
SA.Robert | Dec.25 | 0 | 180 | TRUE | TRUE
SA.Kevin | Jan.25 | 0 | 180 | TRUE | TRUE
SA.Kevin | Feb.25 | 0 | 180 | TRUE | TRUE
SA.Kevin | Mar.25 | 0 | 180 | TRUE | TRUE
SA.Kevin | Apr.25 | 0 | 180 | TRUE | TRUE
SA.Kevin | May.25 | 0 | 180 | TRUE | TRUE
SA.Kevin | Jun.25 | 0 | 180 | TRUE | TRUE
SA.Kevin | Jul.25 | 0 | 180 | TRUE | TRUE
SA.Kevin | Aug.25 | 0 | 180 | TRUE | TRUE
SA.Kevin | Sep.25 | 0 | 180 | TRUE | TRUE
SA.Kevin | Oct.25 | 0 | 180 | TRUE | TRUE
SA.Kevin | Nov.25 | 0 | 180 | TRUE | TRUE
SA.Kevin | Dec.25 | 0 | 180 | TRUE | TRUE
SA.Justin | Jan.25 | 0 | 180 | TRUE | TRUE
SA.Justin | Feb.25 | 0 | 180 | TRUE | TRUE
SA.Justin | Mar.25 | 0 | 180 | TRUE | TRUE
SA.Justin | Apr.25 | 0 | 180 | TRUE | TRUE
SA.Justin | May.25 | 0 | 180 | TRUE | TRUE
SA.Justin | Jun.25 | 0 | 180 | TRUE | TRUE
SA.Justin | Jul.25 | 0 | 180 | TRUE | TRUE
SA.Justin | Aug.25 | 0 | 180 | TRUE | TRUE
SA.Justin | Sep.25 | 0 | 180 | TRUE | TRUE
SA.Justin | Oct.25 | 0 | 180 | TRUE | TRUE
SA.Justin | Nov.25 | 0 | 180 | TRUE | TRUE
SA.Justin | Dec.25 | 0 | 180 | TRUE | TRUE
SA.Martha | Jan.25 | 0 | 180 | TRUE | TRUE
SA.Martha | Feb.25 | 0 | 180 | TRUE | TRUE
SA.Martha | Mar.25 | 0 | 180 | TRUE | TRUE
SA.Martha | Apr.25 | 0 | 180 | TRUE | TRUE
SA.Martha | May.25 | 0 | 180 | TRUE | TRUE
SA.Martha | Jun.25 | 0 | 180 | TRUE | TRUE
SA.Martha | Jul.25 | 0 | 180 | TRUE | TRUE
SA.Martha | Aug.25 | 0 | 180 | TRUE | TRUE
SA.Martha | Sep.25 | 0 | 180 | TRUE | TRUE
SA.Martha | Oct.25 | 0 | 180 | TRUE | TRUE
SA.Martha | Nov.25 | 0 | 180 | TRUE | TRUE
SA.Martha | Dec.25 | 0 | 180 | TRUE | TRUE
SA.Melanie | Jan.25 | 0 | 180 | TRUE | TRUE
SA.Melanie | Feb.25 | 0 | 180 | TRUE | TRUE
SA.Melanie | Mar.25 | 0 | 180 | TRUE | TRUE
SA.Melanie | Apr.25 | 0 | 180 | TRUE | TRUE
SA.Melanie | May.25 | 0 | 180 | TRUE | TRUE
SA.Melanie | Jun.25 | 0 | 180 | TRUE | TRUE
SA.Melanie | Jul.25 | 0 | 180 | TRUE | TRUE
SA.Melanie | Aug.25 | 0 | 180 | TRUE | TRUE
SA.Melanie | Sep.25 | 0 | 180 | TRUE | TRUE
SA.Melanie | Oct.25 | 0 | 180 | TRUE | TRUE
SA.Melanie | Nov.25 | 0 | 180 | TRUE | TRUE
SA.Melanie | Dec.25 | 0 | 180 | TRUE | TRUE
Note on E1: Valid expert?
Note on F1: Valid period?

## holiday
Date | TRUE
2025-01-01 | TRUE
2025-04-20 | TRUE
2025-05-01 | TRUE
Note on B1: Are dates OK?

## misc
Today | Hours per day | Solver | Last day
2024-12-30 | 8 | highs | 2027-01-04

## himg
Hours per day | Width | Height | Dpi | Start | End | Bar:color | Bar:hatch | Bar:alpha | Is Start OK? | Is End OK?
| 8 | 4 | 150 | 2024-12-31 | 2027-01-04 | #2ca02c | / | 0.3 | TRUE | TRUE

## timg
Tasks per day | Width | Height | Dpi | Start | End | Bar:color | Bar:hatch | Bar:alpha | Is Start OK? | Is End OK?
| 8 | 4 | 150 | 2024-12-31 | 2027-01-04 | #d62728 | \ | 0.3 | TRUE | TRUE

## simg
Hours per day stacked | Width | Height | Dpi | Start | End | Bar:alpha | Is Start OK? | Is End OK?
| 8 | 4 | 150 | 2024-12-31 | 2027-01-04 | 0.6 | TRUE | TRUE

## gimg
Task's Gantt Chart | Width | Height | Dpi | Barh:color | Barh:height | Barh:alpha
| 8 | 4 | 150 | #ff7f0e | 0.9 | 0.6

## wimg
Invoicing Periods Workload | Width | Height | Dpi | Bar:color | Bar:ecolor | Bar:capsize
| 8 | 4 | 150 | #7BC8F6 | #EE0000 | 4

## bimg
Task with bounds | Width | Height | Dpi | Fill:color | Fill:hatch | Fill:alpha | Plot:format | Plot:markeredgewidth | Step:linewidth
| 8 | 4 | 150 | #90EE90 | / | 0.2 | o | 0.5 | 0.5

## eimg
Experts per day stacked | Width | Height | Dpi | Bar:alpha
| 8 | 4 | 150 | 0.6