## experts
Name | Comment | TRUE
PM.Daniel | the 2nd unit | TRUE
Note on C1: Has Expert any task?

## tasks
Name | Start | End | Work | Days | Workdays | Avg[h/day] | Lower | Upper | TRUE | TRUE | TRUE
alpha.pm | 2025-01-01 | 2025-04-01 | 45 | 91 | 64 | 0.70312 | 0.5 | 0.75 | TRUE | TRUE | TRUE
alpha.pf | 2025-04-02 | 2025-05-02 | 5 | 31 | 22 | 0.22727 | 0 | 0.25 | TRUE | TRUE | TRUE
beta.pm | 2025-01-01 | 2025-06-20 | 65 | 171 | 121 | 0.53719 | 0.5 | 0.75 | TRUE | TRUE | TRUE
beta.pf | 2025-06-21 | 2025-08-05 | 5 | 46 | 32 | 0.15625 | 0 | 0.25 | TRUE | TRUE | TRUE
india.pm | 2025-01-01 | 2025-10-01 | 130 | 274 | 194 | 0.6701 | 0.5 | 0.75 | TRUE | TRUE | TRUE
india.pf | 2025-10-02 | 2025-11-01 | 25 | 31 | 22 | 1.1364 | 1 | 1.25 | TRUE | TRUE | TRUE
oscar.pe | 2025-06-25 | 2025-07-09 | 15 | 15 | 11 | 1.3636 | 1.25 | 1.5 | TRUE | TRUE | TRUE
oscar.pm | 2025-07-10 | 2025-12-30 | 70 | 174 | 124 | 0.56452 | 0.5 | 0.75 | TRUE | TRUE | TRUE
oscar.pf | 2025-12-31 | 2026-01-31 | 10 | 32 | 23 | 0.43478 | 0.25 | 0.5 | TRUE | TRUE | TRUE
lima2.pm | 2025-01-01 | 2025-02-25 | 25 | 56 | 39 | 0.64103 | 0.5 | 0.75 | TRUE | TRUE | TRUE
lima2.pf | 2025-02-26 | 2025-03-03 | 15 | 6 | 4 | 3.75 | 3.75 | 4 | TRUE | TRUE | TRUE
mike2.pe | 2025-01-10 | 2025-01-15 | 20 | 6 | 4 | 5 | 5 | 5.25 | TRUE | TRUE | TRUE
mike2.pm | 2025-01-16 | 2025-05-16 | 80 | 121 | 86 | 0.93023 | 0.75 | 1 | TRUE | TRUE | TRUE
mike2.pf | 2025-05-17 | 2025-06-01 | 20 | 16 | 10 | 2 | 2 | 2.25 | TRUE | TRUE | TRUE
whisky2.pe | 2025-06-25 | 2025-07-10 | 60 | 16 | 12 | 5 | 5 | 5.25 | TRUE | TRUE | TRUE
whisky2.pm | 2025-07-11 | 2026-04-07 | 200 | 271 | 193 | 1.0363 | 1 | 1.25 | TRUE | TRUE | TRUE
whisky2.pf | 2026-04-08 | 2026-04-30 | 20 | 23 | 17 | 1.1765 | 1 | 1.25 | TRUE | TRUE | TRUE
Note on J1: Is task assign to an Expert?
Note on K1: Should task be included?
Note on L1: Are date OK?

## links
Expert | Task | TRUE | TRUE
PM.Daniel | alpha.pf | TRUE | TRUE
PM.Daniel | alpha.pm | TRUE | TRUE
PM.Daniel | beta.pf | TRUE | TRUE
PM.Daniel | beta.pm | TRUE | TRUE
PM.Daniel | india.pf | TRUE | TRUE
PM.Daniel | india.pm | TRUE | TRUE
PM.Daniel | lima2.pf | TRUE | TRUE
PM.Daniel | lima2.pm | TRUE | TRUE
PM.Daniel | mike2.pe | TRUE | TRUE
PM.Daniel | mike2.pf | TRUE | TRUE
PM.Daniel | mike2.pm | TRUE | TRUE
PM.Daniel | oscar.pe | TRUE | TRUE
PM.Daniel | oscar.pf | TRUE | TRUE
PM.Daniel | oscar.pm | TRUE | TRUE
PM.Daniel | whisky2.pe | TRUE | TRUE
PM.Daniel | whisky2.pm | TRUE | TRUE
PM.Daniel | whisky2.pf | TRUE | TRUE
Note on C1: Valid expert?
Note on D1: Valid task?

## xbday
Expert | Task | Start | End | Lower | Upper | TRUE | TRUE | TRUE
PM.Daniel | alpha.pm | 2025-01-01 | 2025-04-01 | 0.5 | 0.75 | TRUE | TRUE | TRUE
PM.Daniel | alpha.pf | 2025-04-02 | 2025-05-02 | 0 | 0.25 | TRUE | TRUE | TRUE
PM.Daniel | beta.pm | 2025-01-01 | 2025-06-20 | 0.5 | 0.75 | TRUE | TRUE | TRUE
PM.Daniel | beta.pf | 2025-06-21 | 2025-08-05 | 0 | 0.25 | TRUE | TRUE | TRUE
PM.Daniel | india.pm | 2025-01-01 | 2025-10-01 | 0.5 | 0.75 | TRUE | TRUE | TRUE
PM.Daniel | india.pf | 2025-10-02 | 2025-11-01 | 1 | 1.25 | TRUE | TRUE | TRUE
PM.Daniel | oscar.pe | 2025-06-25 | 2025-07-09 | 1.25 | 1.5 | TRUE | TRUE | TRUE
PM.Daniel | oscar.pm | 2025-07-10 | 2025-12-30 | 0.5 | 0.75 | TRUE | TRUE | TRUE
PM.Daniel | oscar.pf | 2025-12-31 | 2026-01-31 | 0.25 | 0.5 | TRUE | TRUE | TRUE
PM.Daniel | lima2.pm | 2025-01-01 | 2025-02-25 | 0.5 | 0.75 | TRUE | TRUE | TRUE
PM.Daniel | lima2.pf | 2025-02-26 | 2025-03-03 | 3.75 | 4 | TRUE | TRUE | TRUE
PM.Daniel | mike2.pe | 2025-01-10 | 2025-01-15 | 5 | 5.25 | TRUE | TRUE | TRUE
PM.Daniel | mike2.pm | 2025-01-16 | 2025-05-16 | 0.75 | 1 | TRUE | TRUE | TRUE
PM.Daniel | mike2.pf | 2025-05-17 | 2025-06-01 | 2 | 2.25 | TRUE | TRUE | TRUE
PM.Daniel | whisky2.pe | 2025-06-25 | 2025-07-10 | 5 | 5.25 | TRUE | TRUE | TRUE
PM.Daniel | whisky2.pm | 2025-07-11 | 2026-04-07 | 1 | 1.25 | TRUE | TRUE | TRUE
PM.Daniel | whisky2.pf | 2026-04-08 | 2026-04-30 | 1 | 1.25 | TRUE | TRUE | TRUE
Note on G1: Valid expert?
Note on H1: Valid task?
Note on I1: Are date OK?

## xbsum
Expert | Task | Start | End | Lower | Upper

## ubday
Expert | Start | End | Lower | Upper

## ubsum
Expert | Task | Start | End | Lower | Upper

## expert bounds
Expert | Start | End | Lower | Upper

## invoicing periods
Name | Start | End | TRUE
Jan.25 | 2024-12-11 | 2025-01-15 | TRUE
Feb.25 | 2025-01-16 | 2025-02-13 | TRUE
Mar.25 | 2025-02-14 | 2025-03-16 | TRUE
Apr.25 | 2025-03-17 | 2025-04-14 | TRUE
May.25 | 2025-04-15 | 2025-05-18 | TRUE
Jun.25 | 2025-05-19 | 2025-06-18 | TRUE
Jul.25 | 2025-06-19 | 2025-07-17 | TRUE
Aug.25 | 2025-07-18 | 2025-08-17 | TRUE
Sep.25 | 2025-08-18 | 2025-09-15 | TRUE
Oct.25 | 2025-09-16 | 2025-10-15 | TRUE
Nov.25 | 2025-10-16 | 2025-11-12 | TRUE
Dec.25 | 2025-11-13 | 2025-12-11 | TRUE
Note on D1: Are dates OK?

## invoicing periods bounds
Expert | Period | Lower | Upper | TRUE | TRUE
PM.Daniel | Jan.25 | 0 | 180 | TRUE | TRUE
PM.Daniel | Feb.25 | 0 | 180 | TRUE | TRUE
PM.Daniel | Mar.25 | 0 | 180 | TRUE | TRUE
PM.Daniel | Apr.25 | 0 | 180 | TRUE | TRUE
PM.Daniel | May.25 | 0 | 180 | TRUE | TRUE
PM.Daniel | Jun.25 | 0 | 180 | TRUE | TRUE
PM.Daniel | Jul.25 | 0 | 180 | TRUE | TRUE
PM.Daniel | Aug.25 | 0 | 180 | TRUE | TRUE
PM.Daniel | Sep.25 | 0 | 180 | TRUE | TRUE
PM.Daniel | Oct.25 | 0 | 180 | TRUE | TRUE
PM.Daniel | Nov.25 | 0 | 180 | TRUE | TRUE
PM.Daniel | Dec.25 | 0 | 180 | TRUE | TRUE
Note on E1: Valid expert?
Note on F1: Valid period?

## public holidays
Date | TRUE
2025-01-01 | TRUE
2025-04-20 | TRUE
2025-05-01 | TRUE
Note on B1: Are dates OK?

## misc
Today | Hours per day | Solver | Last day
2024-12-30 | 8 | highs | 2026-04-30

## himg
Hours per day | Width | Height | Dpi | Start | End | Bar:color | Bar:hatch | Bar:alpha | Is Start OK? | Is End OK?
| 8 | 4 | 150 | 2024-12-31 | 2026-04-30 | #2ca02c | / | 0.3 | TRUE | TRUE

## timg
Tasks per day | Width | Height | Dpi | Start | End | Bar:color | Bar:hatch | Bar:alpha | Is Start OK? | Is End OK?
| 8 | 4 | 150 | 2024-12-31 | 2026-04-30 | #d62728 | \ | 0.3 | TRUE | TRUE

## simg
Hours per day stacked | Width | Height | Dpi | Start | End | Bar:alpha | Is Start OK? | Is End OK?
| 8 | 4 | 150 | 2024-12-31 | 2026-04-30 | 0.6 | TRUE | TRUE

## gimg
Task's Gantt Chart | Width | Height | Dpi | Barh:color | Barh:height | Barh:alpha
| 8 | 4 | 150 | #ff7f0e | 0.9 | 0.6

## wimg
Invoicing Periods Workload | Width | Height | Dpi | Bar:color | Bar:ecolor | Bar:capsize
| 8 | 4 | 150 | #7BC8F6 | #EE0000 | 4

## bimg
Task with bounds | Width | Height | Dpi | Fill:color | Fill:hatch | Fill:alpha | Plot:format | Plot:markeredgewidth | Step:linewidth
| 8 | 4 | 150 | #90EE90 | / | 0.2 | o | 0.5 | 0.5