## experts
Name | Comment | TRUE
SA.Adrian | the 1st unit | TRUE
Note on C1: Has Expert any task?

## tasks
Name | Start | End | Work | Days | Workdays | Avg[h/day] | Lower | Upper | TRUE | TRUE | TRUE
alpha.sm | 2025-01-01 | 2025-04-01 | 10 | 91 | 64 | 0.15625 | 0 | 0.25 | TRUE | TRUE | TRUE
alpha.sf | 2025-04-02 | 2025-05-02 | 5 | 31 | 22 | 0.22727 | 0 | 0.25 | TRUE | TRUE | TRUE
beta.sm | 2025-01-01 | 2025-06-20 | 10 | 171 | 121 | 0.082645 | 0 | 0.25 | TRUE | TRUE | TRUE
beta.sf | 2025-06-21 | 2025-08-05 | 5 | 46 | 32 | 0.15625 | 0 | 0.25 | TRUE | TRUE | TRUE
charlie.sm | 2025-01-01 | 2025-06-05 | 15 | 156 | 110 | 0.13636 | 0 | 0.25 | TRUE | TRUE | TRUE
charlie.sf | 2025-06-06 | 2025-07-06 | 5 | 31 | 21 | 0.2381 | 0 | 0.25 | TRUE | TRUE | TRUE
delta.sm | 2025-01-01 | 2025-02-25 | 5 | 56 | 39 | 0.12821 | 0 | 0.25 | TRUE | TRUE | TRUE
delta.sf | 2025-02-26 | 2025-04-12 | 5 | 46 | 33 | 0.15152 | 0 | 0.25 | TRUE | TRUE | TRUE
echo.sm | 2025-01-01 | 2025-03-15 | 5 | 74 | 52 | 0.096154 | 0 | 0.25 | TRUE | TRUE | TRUE
echo.sf | 2025-04-02 | 2025-05-17 | 8 | 46 | 32 | 0.25 | 0.25 | 0.5 | TRUE | TRUE | TRUE
golf.sm | 2025-01-01 | 2025-05-12 | 10 | 132 | 92 | 0.1087 | 0 | 0.25 | TRUE | TRUE | TRUE
golf.sf | 2025-05-13 | 2025-06-27 | 8 | 46 | 34 | 0.23529 | 0 | 0.25 | TRUE | TRUE | TRUE
kilo.se | 2025-03-01 | 2025-03-24 | 15 | 24 | 16 | 0.9375 | 0.75 | 1 | TRUE | TRUE | TRUE
kilo.sm | 2025-03-25 | 2025-08-01 | 10 | 130 | 93 | 0.10753 | 0 | 0.25 | TRUE | TRUE | TRUE
kilo.sf | 2025-08-02 | 2025-09-16 | 5 | 46 | 32 | 0.15625 | 0 | 0.25 | TRUE | TRUE | TRUE
lima.se | 2025-03-21 | 2025-04-19 | 36 | 30 | 21 | 1.7143 | 1.5 | 1.75 | TRUE | TRUE | TRUE
lima.sm | 2025-04-20 | 2025-11-01 | 10 | 196 | 139 | 0.071942 | 0 | 0.25 | TRUE | TRUE | TRUE
lima.sf | 2025-11-02 | 2025-11-30 | 5 | 29 | 20 | 0.25 | 0.25 | 0.5 | TRUE | TRUE | TRUE
mike.se | 2025-03-21 | 2025-04-19 | 15 | 30 | 21 | 0.71429 | 0.5 | 0.75 | TRUE | TRUE | TRUE
mike.sm | 2025-04-20 | 2025-11-01 | 10 | 196 | 139 | 0.071942 | 0 | 0.25 | TRUE | TRUE | TRUE
mike.sf | 2025-11-02 | 2025-11-30 | 5 | 29 | 20 | 0.25 | 0.25 | 0.5 | TRUE | TRUE | TRUE
Note on J1: Is task assign to an Expert?
Note on K1: Should task be included?
Note on L1: Are date OK?

## links
Expert | Task | TRUE | TRUE
SA.Adrian | alpha.sf | TRUE | TRUE
SA.Adrian | alpha.sm | TRUE | TRUE
SA.Adrian | beta.sf | TRUE | TRUE
SA.Adrian | beta.sm | TRUE | TRUE
SA.Adrian | charlie.sf | TRUE | TRUE
SA.Adrian | charlie.sm | TRUE | TRUE
SA.Adrian | delta.sf | TRUE | TRUE
SA.Adrian | delta.sm | TRUE | TRUE
SA.Adrian | echo.sf | TRUE | TRUE
SA.Adrian | echo.sm | TRUE | TRUE
SA.Adrian | golf.sf | TRUE | TRUE
SA.Adrian | golf.sm | TRUE | TRUE
SA.Adrian | kilo.se | TRUE | TRUE
SA.Adrian | kilo.sf | TRUE | TRUE
SA.Adrian | kilo.sm | TRUE | TRUE
SA.Adrian | lima.se | TRUE | TRUE
SA.Adrian | lima.sf | TRUE | TRUE
SA.Adrian | lima.sm | TRUE | TRUE
SA.Adrian | mike.se | TRUE | TRUE
SA.Adrian | mike.sf | TRUE | TRUE
SA.Adrian | mike.sm | TRUE | TRUE
Note on C1: Valid expert?
Note on D1: Valid task?

## xbday
Expert | Task | Start | End | Lower | Upper | TRUE | TRUE | TRUE
SA.Adrian | alpha.sm | 2025-01-01 | 2025-04-01 | 0 | 0.25 | TRUE | TRUE | TRUE
SA.Adrian | alpha.sf | 2025-04-02 | 2025-05-02 | 0 | 0.25 | TRUE | TRUE | TRUE
SA.Adrian | beta.sm | 2025-01-01 | 2025-06-20 | 0 | 0.25 | TRUE | TRUE | TRUE
SA.Adrian | beta.sf | 2025-06-21 | 2025-08-05 | 0 | 0.25 | TRUE | TRUE | TRUE
SA.Adrian | charlie.sm | 2025-01-01 | 2025-06-05 | 0 | 0.25 | TRUE | TRUE | TRUE
SA.Adrian | charlie.sf | 2025-06-06 | 2025-07-06 | 0 | 0.25 | TRUE | TRUE | TRUE
SA.Adrian | delta.sm | 2025-01-01 | 2025-02-25 | 0 | 0.25 | TRUE | TRUE | TRUE
SA.Adrian | delta.sf | 2025-02-26 | 2025-04-12 | 0 | 0.25 | TRUE | TRUE | TRUE
SA.Adrian | echo.sm | 2025-01-01 | 2025-03-15 | 0 | 0.25 | TRUE | TRUE | TRUE
SA.Adrian | echo.sf | 2025-04-02 | 2025-05-17 | 0.25 | 0.5 | TRUE | TRUE | TRUE
SA.Adrian | golf.sm | 2025-01-01 | 2025-05-12 | 0 | 0.25 | TRUE | TRUE | TRUE
SA.Adrian | golf.sf | 2025-05-13 | 2025-06-27 | 0 | 0.25 | TRUE | TRUE | TRUE
SA.Adrian | kilo.se | 2025-03-01 | 2025-03-24 | 0.75 | 1 | TRUE | TRUE | TRUE
SA.Adrian | kilo.sm | 2025-03-25 | 2025-08-01 | 0 | 0.25 | TRUE | TRUE | TRUE
SA.Adrian | kilo.sf | 2025-08-02 | 2025-09-16 | 0 | 0.25 | TRUE | TRUE | TRUE
SA.Adrian | lima.se | 2025-03-21 | 2025-04-19 | 1.5 | 1.75 | TRUE | TRUE | TRUE
SA.Adrian | lima.sm | 2025-04-20 | 2025-11-01 | 0 | 0.25 | TRUE | TRUE | TRUE
SA.Adrian | lima.sf | 2025-11-02 | 2025-11-30 | 0.25 | 0.5 | TRUE | TRUE | TRUE
SA.Adrian | mike.se | 2025-03-21 | 2025-04-19 | 0.5 | 0.75 | TRUE | TRUE | TRUE
SA.Adrian | mike.sm | 2025-04-20 | 2025-11-01 | 0 | 0.25 | TRUE | TRUE | TRUE
SA.Adrian | mike.sf | 2025-11-02 | 2025-11-30 | 0.25 | 0.5 | TRUE | TRUE | TRUE
Note on G1: Valid expert?
Note on H1: Valid task?
Note on I1: Are date OK?

## xbsum
Expert | Task | Start | End | Lower | Upper

## ubday
Expert | Start | End | Lower | Upper

## ubsum
Expert | Task | Start | End | Lower | Upper

## expert bounds
Expert | Start | End | Lower | Upper

## invoicing periods
Name | Start | End | TRUE
Jan.25 | 2024-12-11 | 2025-01-15 | TRUE
Feb.25 | 2025-01-16 | 2025-02-13 | TRUE
Mar.25 | 2025-02-14 | 2025-03-16 | TRUE
Apr.25 | 2025-03-17 | 2025-04-14 | TRUE
May.25 | 2025-04-15 | 2025-05-18 | TRUE
Jun.25 | 2025-05-19 | 2025-06-18 | TRUE
Jul.25 | 2025-06-19 | 2025-07-17 | TRUE
Aug.25 | 2025-07-18 | 2025-08-17 | TRUE
Sep.25 | 2025-08-18 | 2025-09-15 | TRUE
Oct.25 | 2025-09-16 | 2025-10-15 | TRUE
Nov.25 | 2025-10-16 | 2025-11-12 | TRUE
Dec.25 | 2025-11-13 | 2025-12-11 | TRUE
Note on D1: Are dates OK?

## invoicing periods bounds
Expert | Period | Lower | Upper | TRUE | TRUE
SA.Adrian | Jan.25 | 0 | 180 | TRUE | TRUE
SA.Adrian | Feb.25 | 0 | 180 | TRUE | TRUE
SA.Adrian | Mar.25 | 0 | 180 | TRUE | TRUE
SA.Adrian | Apr.25 | 0 | 180 | TRUE | TRUE
SA.Adrian | May.25 | 0 | 180 | TRUE | TRUE
SA.Adrian | Jun.25 | 0 | 180 | TRUE | TRUE
SA.Adrian | Jul.25 | 0 | 180 | TRUE | TRUE
SA.Adrian | Aug.25 | 0 | 180 | TRUE | TRUE
SA.Adrian | Sep.25 | 0 | 180 | TRUE | TRUE
SA.Adrian | Oct.25 | 0 | 180 | TRUE | TRUE
SA.Adrian | Nov.25 | 0 | 180 | TRUE | TRUE
SA.Adrian | Dec.25 | 0 | 180 | TRUE | TRUE
Note on E1: Valid expert?
Note on F1: Valid period?

## public holidays
Date | TRUE
2025-01-01 | TRUE
2025-04-20 | TRUE
2025-05-01 | TRUE
Note on B1: Are dates OK?

## misc
Today | Hours per day | Solver | Last day
2024-12-30 | 8 | highs | 2025-12-11

## himg
Hours per day | Width | Height | Dpi | Start | End | Bar:color | Bar:hatch | Bar:alpha | Is Start OK? | Is End OK?
| 8 | 4 | 150 | 2024-12-31 | 2025-12-11 | #2ca02c | / | 0.3 | TRUE | TRUE

## timg
Tasks per day | Width | Height | Dpi | Start | End | Bar:color | Bar:hatch | Bar:alpha | Is Start OK? | Is End OK?
| 8 | 4 | 150 | 2024-12-31 | 2025-12-11 | #d62728 | \ | 0.3 | TRUE | TRUE

## simg
Hours per day stacked | Width | Height | Dpi | Start | End | Bar:alpha | Is Start OK? | Is End OK?
| 8 | 4 | 150 | 2024-12-31 | 2025-12-11 | 0.6 | TRUE | TRUE

## gimg
Task's Gantt Chart | Width | Height | Dpi | Barh:color | Barh:height | Barh:alpha
| 8 | 4 | 150 | #ff7f0e | 0.9 | 0.6

## wimg
Invoicing Periods Workload | Width | Height | Dpi | Bar:color | Bar:ecolor | Bar:capsize
| 8 | 4 | 150 | #7BC8F6 | #EE0000 | 4

## bimg
Task with bounds | Width | Height | Dpi | Fill:color | Fill:hatch | Fill:alpha | Plot:format | Plot:markeredgewidth | Step:linewidth
| 8 | 4 | 150 | #90EE90 | / | 0.2 | o | 0.5 | 0.5