## experts
Name | Comment | TRUE
SA.Kevin | the 2nd unit | TRUE
Note on C1: Has Expert any task?

## tasks
Name | Start | End | Work | Days | Workdays | Avg[h/day] | Lower | Upper | TRUE | #REF! | TRUE
alpha2.se | 2025-01-27 | 2025-02-01 | 12 | 6 | 5 | 2.4 | 2.25 | 2.5 | TRUE | #REF! | TRUE
alpha2.sm | 2025-02-02 | 2025-03-19 | 24 | 46 | 33 | 0.72727 | 0.5 | 0.75 | TRUE | TRUE | TRUE
alpha2.sf | 2025-03-20 | 2025-04-01 | 8 | 13 | 9 | 0.88889 | 0.75 | 1 | TRUE | TRUE | TRUE
beta2.se | 2025-01-05 | 2025-01-15 | 30 | 11 | 8 | 3.75 | 3.75 | 4 | TRUE | TRUE | TRUE
beta2.sm | 2025-01-16 | 2025-07-15 | 60 | 181 | 128 | 0.46875 | 0.25 | 0.5 | TRUE | TRUE | TRUE
beta2.sf | 2025-07-16 | 2025-08-04 | 40 | 20 | 14 | 2.8571 | 2.75 | 3 | TRUE | TRUE | TRUE
gamma2.sm | 2025-01-01 | 2025-01-21 | 15 | 21 | 14 | 1.0714 | 1 | 1.25 | TRUE | TRUE | TRUE
gamma2.sf | 2025-01-22 | 2025-02-03 | 5 | 13 | 9 | 0.55556 | 0.5 | 0.75 | TRUE | TRUE | TRUE
quebec2.se | 2025-06-01 | 2025-06-26 | 40 | 26 | 19 | 2.1053 | 2 | 2.25 | TRUE | TRUE | TRUE
quebec2.sm | 2025-06-27 | 2026-11-09 | 20 | 501 | 357 | 0.056022 | 0 | 0.25 | TRUE | TRUE | TRUE
quebec2.sf | 2026-11-10 | 2027-01-04 | 20 | 56 | 40 | 0.5 | 0.5 | 0.75 | TRUE | TRUE | TRUE
uniform2.se | 2025-05-01 | 2025-05-16 | 60 | 16 | 11 | 5.4545 | 5.25 | 5.5 | TRUE | TRUE | TRUE
uniform2.sm | 2025-05-17 | 2026-02-11 | 50 | 271 | 193 | 0.25907 | 0.25 | 0.5 | TRUE | TRUE | TRUE
uniform2.sf | 2026-02-12 | 2026-03-02 | 20 | 19 | 13 | 1.5385 | 1.5 | 1.75 | TRUE | TRUE | TRUE
xray2.se | 2025-07-15 | 2025-08-09 | 20 | 26 | 19 | 1.0526 | 1 | 1.25 | TRUE | TRUE | TRUE
xray2.sm | 2025-08-10 | 2026-01-07 | 30 | 151 | 108 | 0.27778 | 0.25 | 0.5 | TRUE | TRUE | TRUE
xray2.sf | 2026-01-08 | 2026-02-01 | 20 | 25 | 17 | 1.1765 | 1 | 1.25 | TRUE | TRUE | TRUE
Note on J1: Is task assign to an Expert?
Note on K1: Should task be included?
Note on L1: Are date OK?

## links
Expert | Task | TRUE | TRUE
SA.Kevin | alpha2.se | TRUE | TRUE
SA.Kevin | alpha2.sf | TRUE | TRUE
SA.Kevin | alpha2.sm | TRUE | TRUE
SA.Kevin | beta2.se | TRUE | TRUE
SA.Kevin | beta2.sf | TRUE | TRUE
SA.Kevin | beta2.sm | TRUE | TRUE
SA.Kevin | gamma2.sf | TRUE | TRUE
SA.Kevin | gamma2.sm | TRUE | TRUE
SA.Kevin | quebec2.se | TRUE | TRUE
SA.Kevin | quebec2.sf | TRUE | TRUE
SA.Kevin | quebec2.sm | TRUE | TRUE
SA.Kevin | uniform2.se | TRUE | TRUE
SA.Kevin | uniform2.sf | TRUE | TRUE
SA.Kevin | uniform2.sm | TRUE | TRUE
SA.Kevin | xray2.se | TRUE | TRUE
SA.Kevin | xray2.sf | TRUE | TRUE
SA.Kevin | xray2.sm | TRUE | TRUE
Note on C1: Valid expert?
Note on D1: Valid task?

## xbday
Expert | Task | Start | End | Lower | Upper | TRUE | TRUE | TRUE
SA.Kevin | alpha2.se | 2025-01-27 | 2025-02-01 | 2.25 | 2.5 | TRUE | TRUE | TRUE
SA.Kevin | alpha2.sm | 2025-02-02 | 2025-03-19 | 0.5 | 0.75 | TRUE | TRUE | TRUE
SA.Kevin | alpha2.sf | 2025-03-20 | 2025-04-01 | 0.75 | 1 | TRUE | TRUE | TRUE
SA.Kevin | beta2.se | 2025-01-05 | 2025-01-15 | 3.75 | 4 | TRUE | TRUE | TRUE
SA.Kevin | beta2.sm | 2025-01-16 | 2025-07-15 | 0.25 | 0.5 | TRUE | TRUE | TRUE
SA.Kevin | beta2.sf | 2025-07-16 | 2025-08-04 | 2.75 | 3 | TRUE | TRUE | TRUE
SA.Kevin | gamma2.sm | 2025-01-01 | 2025-01-21 | 1 | 1.25 | TRUE | TRUE | TRUE
SA.Kevin | gamma2.sf | 2025-01-22 | 2025-02-03 | 0.5 | 0.75 | TRUE | TRUE | TRUE
SA.Kevin | quebec2.se | 2025-06-01 | 2025-06-26 | 2 | 2.25 | TRUE | TRUE | TRUE
SA.Kevin | quebec2.sm | 2025-06-27 | 2026-11-09 | 0 | 0.25 | TRUE | TRUE | TRUE
SA.Kevin | quebec2.sf | 2026-11-10 | 2027-01-04 | 0.5 | 0.75 | TRUE | TRUE | TRUE
SA.Kevin | uniform2.se | 2025-05-01 | 2025-05-16 | 5.25 | 5.5 | TRUE | TRUE | TRUE
SA.Kevin | uniform2.sm | 2025-05-17 | 2026-02-11 | 0.25 | 0.5 | TRUE | TRUE | TRUE
SA.Kevin | uniform2.sf | 2026-02-12 | 2026-03-02 | 1.5 | 1.75 | TRUE | TRUE | TRUE
SA.Kevin | xray2.se | 2025-07-15 | 2025-08-09 | 1 | 1.25 | TRUE | TRUE | TRUE
SA.Kevin | xray2.sm | 2025-08-10 | 2026-01-07 | 0.25 | 0.5 | TRUE | TRUE | TRUE
SA.Kevin | xray2.sf | 2026-01-08 | 2026-02-01 | 1 | 1.25 | TRUE | TRUE | TRUE
Note on G1: Valid expert?
Note on H1: Valid task?
Note on I1: Are date OK?

## xbsum
Expert | Task | Start | End | Lower | Upper

## ubday
Expert | Start | End | Lower | Upper

## ubsum
Expert | Task | Start | End | Lower | Upper

## expert bounds
Expert | Start | End | Lower | Upper

## invoicing periods
Name | Start | End | TRUE
Jan.25 | 2024-12-11 | 2025-01-15 | TRUE
Feb.25 | 2025-01-16 | 2025-02-13 | TRUE
Mar.25 | 2025-02-14 | 2025-03-16 | TRUE
Apr.25 | 2025-03-17 | 2025-04-14 | TRUE
May.25 | 2025-04-15 | 2025-05-18 | TRUE
Jun.25 | 2025-05-19 | 2025-06-18 | TRUE
Jul.25 | 2025-06-19 | 2025-07-17 | TRUE
Aug.25 | 2025-07-18 | 2025-08-17 | TRUE
Sep.25 | 2025-08-18 | 2025-09-15 | TRUE
Oct.25 | 2025-09-16 | 2025-10-15 | TRUE
Nov.25 | 2025-10-16 | 2025-11-12 | TRUE
Dec.25 | 2025-11-13 | 2025-12-11 | TRUE
Note on D1: Are dates OK?

## invoicing periods bounds
Expert | Period | Lower | Upper | TRUE | TRUE
SA.Kevin | Jan.25 | 0 | 180 | TRUE | TRUE
SA.Kevin | Feb.25 | 0 | 180 | TRUE | TRUE
SA.Kevin | Mar.25 | 0 | 180 | TRUE | TRUE
SA.Kevin | Apr.25 | 0 | 180 | TRUE | TRUE
SA.Kevin | May.25 | 0 | 180 | TRUE | TRUE
SA.Kevin | Jun.25 | 0 | 180 | TRUE | TRUE
SA.Kevin | Jul.25 | 0 | 180 | TRUE | TRUE
SA.Kevin | Aug.25 | 0 | 180 | TRUE | TRUE
SA.Kevin | Sep.25 | 0 | 180 | TRUE | TRUE
SA.Kevin | Oct.25 | 0 | 180 | TRUE | TRUE
SA.Kevin | Nov.25 | 0 | 180 | TRUE | TRUE
SA.Kevin | Dec.25 | 0 | 180 | TRUE | TRUE
Note on E1: Valid expert?
Note on F1: Valid period?

## public holidays
Date | TRUE
2025-01-01 | TRUE
2025-04-20 | TRUE
2025-05-01 | TRUE
Note on B1: Are dates OK?

## misc
Today | Hours per day | Solver | Last day
2024-12-30 | 8 | highs | 2027-01-04

## himg
Hours per day | Width | Height | Dpi | Start | End | Bar:color | Bar:hatch | Bar:alpha | Is Start OK? | Is End OK?
| 8 | 4 | 150 | 2024-12-31 | 2027-01-04 | #2ca02c | / | 0.3 | TRUE | TRUE

## timg
Tasks per day | Width | Height | Dpi | Start | End | Bar:color | Bar:hatch | Bar:alpha | Is Start OK? | Is End OK?
| 8 | 4 | 150 | 2024-12-31 | 2027-01-04 | #d62728 | \ | 0.3 | TRUE | TRUE

## simg
Hours per day stacked | Width | Height | Dpi | Start | End | Bar:alpha | Is Start OK? | Is End OK?
| 8 | 4 | 150 | 2024-12-31 | 2027-01-04 | 0.6 | TRUE | TRUE

## gimg
Task's Gantt Chart | Width | Height | Dpi | Barh:color | Barh:height | Barh:alpha
| 8 | 4 | 150 | #ff7f0e | 0.9 | 0.6

## wimg
Invoicing Periods Workload | Width | Height | Dpi | Bar:color | Bar:ecolor | Bar:capsize
| 8 | 4 | 150 | #7BC8F6 | #EE0000 | 4

## bimg
Task with bounds | Width | Height | Dpi | Fill:color | Fill:hatch | Fill:alpha | Plot:format | Plot:markeredgewidth | Step:linewidth
| 8 | 4 | 150 | #90EE90 | / | 0.2 | o | 0.5 | 0.5