## expert
Name | Comment | TRUE
PM.Anthony | the 2nd unit | 1
Note on C1: Has Expert any task?

## task
Name | Start | End | Work | Days | Workdays | Avg[h/day] | Lower | Upper | TRUE | TRUE | TRUE
delta2.pm | 2025-01-01 | 2025-06-20 | 30 | 171 | 121 | 0.24793 | 0 | 0.25 | 1 | 1 | 1
delta2.pf | 2025-06-21 | 2025-07-01 | 10 | 11 | 7 | 1.4286 | 1.25 | 1.5 | 1 | 1 | 1
echo2.pm | 2025-01-01 | 2025-01-21 | 20 | 21 | 14 | 1.4286 | 1.25 | 1.5 | 1 | 1 | 1
echo2.pf | 2025-01-22 | 2025-03-10 | 10 | 48 | 34 | 0.29412 | 0.25 | 0.5 | 1 | 1 | 1
foxtrot2.pm | 2025-01-01 | 2025-03-22 | 10 | 81 | 57 | 0.17544 | 0 | 0.25 | 1 | 1 | 1
foxtrot2.pf | 2025-03-23 | 2025-04-01 | 5 | 10 | 7 | 0.71429 | 0.5 | 0.75 | 1 | 1 | 1
gamma2.pm | 2025-01-01 | 2025-01-21 | 15 | 21 | 14 | 1.0714 | 1 | 1.25 | 1 | 1 | 1
gamma2.pf | 2025-01-22 | 2025-02-03 | 10 | 13 | 9 | 1.1111 | 1 | 1.25 | 1 | 1 | 1
golf2.pm | 2025-01-01 | 2025-03-22 | 40 | 81 | 57 | 0.70175 | 0.5 | 0.75 | 1 | 1 | 1
golf2.pf | 2025-03-23 | 2025-03-31 | 15 | 9 | 6 | 2.5 | 2.5 | 2.75 | 1 | 1 | 1
hotel2.pm | 2025-01-01 | 2025-02-15 | 10 | 46 | 32 | 0.3125 | 0.25 | 0.5 | 1 | 1 | 1
hotel2.pf | 2025-02-16 | 2025-02-25 | 5 | 10 | 7 | 0.71429 | 0.5 | 0.75 | 1 | 1 | 1
tango2.pe | 2025-02-01 | 2025-02-16 | 50 | 16 | 10 | 5 | 5 | 5.25 | 1 | 1 | 1
tango2.pm | 2025-02-17 | 2025-09-15 | 150 | 211 | 150 | 1 | 1 | 1.25 | 1 | 1 | 1
tango2.pf | 2025-09-16 | 2025-10-01 | 30 | 16 | 12 | 2.5 | 2.5 | 2.75 | 1 | 1 | 1
uniform2.pe | 2025-05-01 | 2025-05-16 | 50 | 16 | 11 | 4.5455 | 4.5 | 4.75 | 1 | 1 | 1
uniform2.pm | 2025-05-17 | 2026-02-11 | 160 | 271 | 193 | 0.82902 | 0.75 | 1 | 1 | 1 | 1
uniform2.pf | 2026-02-12 | 2026-03-02 | 20 | 19 | 13 | 1.5385 | 1.5 | 1.75 | 1 | 1 | 1
Note on J1: Is task assign to an Expert?
Note on K1: Should task be included?
Note on L1: Are date OK?

## assign
Expert | Task | TRUE | TRUE
PM.Anthony | delta2.pf | 1 | 1
PM.Anthony | delta2.pm | 1 | 1
PM.Anthony | echo2.pf | 1 | 1
PM.Anthony | echo2.pm | 1 | 1
PM.Anthony | foxtrot2.pf | 1 | 1
PM.Anthony | foxtrot2.pm | 1 | 1
PM.Anthony | gamma2.pf | 1 | 1
PM.Anthony | gamma2.pm | 1 | 1
PM.Anthony | golf2.pf | 1 | 1
PM.Anthony | golf2.pm | 1 | 1
PM.Anthony | hotel2.pf | 1 | 1
PM.Anthony | hotel2.pm | 1 | 1
PM.Anthony | tango2.pe | 1 | 1
PM.Anthony | tango2.pf | 1 | 1
PM.Anthony | tango2.pm | 1 | 1
PM.Anthony | uniform2.pe | 1 | 1
PM.Anthony | uniform2.pf | 1 | 1
PM.Anthony | uniform2.pm | 1 | 1
Note on C1: Valid expert?
Note on D1: Valid task?

## xbday
Expert | Task | Start | End | Lower | Upper | TRUE | TRUE | TRUE
PM.Anthony | delta2.pm | 2025-01-01 | 2025-06-20 | 0 | 0.25 | TRUE | TRUE | TRUE
PM.Anthony | delta2.pf | 2025-06-21 | 2025-07-01 | 1.25 | 1.5 | TRUE | TRUE | TRUE
PM.Anthony | echo2.pm | 2025-01-01 | 2025-01-21 | 1.25 | 1.5 | TRUE | TRUE | TRUE
PM.Anthony | echo2.pf | 2025-01-22 | 2025-03-10 | 0.25 | 0.5 | TRUE | TRUE | TRUE
PM.Anthony | foxtrot2.pm | 2025-01-01 | 2025-03-22 | 0 | 0.25 | TRUE | TRUE | TRUE
PM.Anthony | foxtrot2.pf | 2025-03-23 | 2025-04-01 | 0.5 | 0.75 | TRUE | TRUE | TRUE
PM.Anthony | gamma2.pm | 2025-01-01 | 2025-01-21 | 1 | 1.25 | TRUE | TRUE | TRUE
PM.Anthony | gamma2.pf | 2025-01-22 | 2025-02-03 | 1 | 1.25 | TRUE | TRUE | TRUE
PM.Anthony | golf2.pm | 2025-01-01 | 2025-03-22 | 0.5 | 0.75 | TRUE | TRUE | TRUE
PM.Anthony | golf2.pf | 2025-03-23 | 2025-03-31 | 2.5 | 2.75 | TRUE | TRUE | TRUE
PM.Anthony | hotel2.pm | 2025-01-01 | 2025-02-15 | 0.25 | 0.5 | TRUE | TRUE | TRUE
PM.Anthony | hotel2.pf | 2025-02-16 | 2025-02-25 | 0.5 | 0.75 | TRUE | TRUE | TRUE
PM.Anthony | tango2.pe | 2025-02-01 | 2025-02-16 | 5 | 5.25 | TRUE | TRUE | TRUE
PM.Anthony | tango2.pm | 2025-02-17 | 2025-09-15 | 1 | 1.25 | TRUE | TRUE | TRUE
PM.Anthony | tango2.pf | 2025-09-16 | 2025-10-01 | 2.5 | 2.75 | TRUE | TRUE | TRUE
PM.Anthony | uniform2.pe | 2025-05-01 | 2025-05-16 | 4.5 | 4.75 | TRUE | TRUE | TRUE
PM.Anthony | uniform2.pm | 2025-05-17 | 2026-02-11 | 0.75 | 1 | TRUE | TRUE | TRUE
PM.Anthony | uniform2.pf | 2026-02-12 | 2026-03-02 | 1.5 | 1.75 | TRUE | TRUE | TRUE
Note on G1: Valid expert?
Note on H1: Valid task?
Note on I1: Are date OK?

## ubday
Expert | Start | End | Lower | Upper

## ebday
Expert | Start | End | Lower | Upper

## period
Name | Start | End | TRUE
Jan.25 | 2024-12-11 | 2025-01-15 | TRUE
Feb.25 | 2025-01-16 | 2025-02-13 | TRUE
Mar.25 | 2025-02-14 | 2025-03-16 | TRUE
Apr.25 | 2025-03-17 | 2025-04-14 | TRUE
May.25 | 2025-04-15 | 2025-05-18 | TRUE
Jun.25 | 2025-05-19 | 2025-06-18 | TRUE
Jul.25 | 2025-06-19 | 2025-07-17 | TRUE
Aug.25 | 2025-07-18 | 2025-08-17 | TRUE
Sep.25 | 2025-08-18 | 2025-09-15 | TRUE
Oct.25 | 2025-09-16 | 2025-10-15 | TRUE
Nov.25 | 2025-10-16 | 2025-11-12 | TRUE
Dec.25 | 2025-11-13 | 2025-12-11 | TRUE
Note on D1: Are dates OK?

## pbsum
Expert | Period | Lower | Upper | TRUE | TRUE
PM.Anthony | Jan.25 | 0 | 180 | TRUE | TRUE
PM.Anthony | Feb.25 | 0 | 180 | TRUE | TRUE
PM.Anthony | Mar.25 | 0 | 180 | TRUE | TRUE
PM.Anthony | Apr.25 | 0 | 180 | TRUE | TRUE
PM.Anthony | May.25 | 0 | 180 | TRUE | TRUE
PM.Anthony | Jun.25 | 0 | 180 | TRUE | TRUE
PM.Anthony | Jul.25 | 0 | 180 | TRUE | TRUE
PM.Anthony | Aug.25 | 0 | 180 | TRUE | TRUE
PM.Anthony | Sep.25 | 0 | 180 | TRUE | TRUE
PM.Anthony | Oct.25 | 0 | 180 | TRUE | TRUE
PM.Anthony | Nov.25 | 0 | 180 | TRUE | TRUE
PM.Anthony | Dec.25 | 0 | 180 | TRUE | TRUE
Note on E1: Valid expert?
Note on F1: Valid period?

## holiday
Date | TRUE
2025-01-01 | TRUE
2025-04-20 | TRUE
2025-05-01 | TRUE
Note on B1: Are dates OK?

## misc
Today | Hours per day | Solver | AMPL model | Last day
2024-12-30 | 8 | highs | solid | 2026-03-02

## img
For all charts | Width | Height | Dpi | Start | End | Is Start OK? | Is End OK?
| 6 | 3 | 150 | 2024-12-31 | 2025-01-20 | TRUE | TRUE
Formulas:
End = [Start]+20

## imgh
Hours per day | Bar:color | Bar:hatch | Bar:alpha
| #2ca02c | / | 0.3

## imgt
Tasks per day | Bar:color | Bar:hatch | Bar:alpha
| #d62728 | \ | 0.3

## imgs
Hours per day stacked | Bar:alpha
0.6

## imgg
Task's Gantt Chart | Barh:color | Barh:height | Barh:alpha
| #ff7f0e | 0.9 | 0.6

## imgw
Invoicing Periods Workload | Bar:color | Bar:ecolor | Bar:capsize
| #7BC8F6 | #EE0000 | 4

## imgb
Task with bounds | Fill:color | Fill:hatch | Fill:alpha | Plot:format | Plot:markeredgewidth | Step:linewidth
| #90EE90 | / | 0.2 | o | 0.5 | 0.5

## imge
Experts per day stacked | Bar:alpha
0.6